## Overview
Squark Dashboard — Project Record
Prepared by | Anant Gupta
Date | 26 August 2026
Period covered | 24 June 2026 – 26 August 2026
Live system | https://217.76.59.244.sslip.io
Repository | https://github.com/AnantSQIP/pdash
Phase 1 | Closed 12 August 2026 — 22 modules, live and in daily use
Phase 2 | Open since 12 August 2026 — 7 of 10 agreed items complete, 3 partial
Total commits | 223 (219 merged to main, 4 on an unmerged branch)
Pull requests | 102 raised, 97 merged
Working days | 38
API modules | 42
Automated checks | 409 passing
CONTENTS
Timeline | Dated milestones across both phases
Meetings & Communications | Every recorded discussion, instruction and delivery
Feedback Log | Client feedback by date, with delivery status
Phase 2 Status | The ten agreed timeline items
Modules Delivered | What each module does
Open Items | What remains, and what input is required
Bugs Found & Fixed | Defects located during testing and their impact
Pull Requests | All 102, with dates
Commits | All 223, with dates
Daily Activity | Commits per working day
Branches | Every branch and its last commit
Architecture — PID & Patents | How PIDs, clients and patents relate

## Timeline
Date | Phase | Milestone | Detail
2026-06-24 | Phase 1 | Project begins | First commit — SquarkIP pdash project management system
2026-06-25 | Phase 1 | Live API + real data | Collapsible sidebar, Kanban/Gantt/Calendar, progress colour scale
2026-06-28 | Phase 1 | Auth, RBAC, attendance, performance | The four foundations everything else depends on
2026-06-30 | Phase 1 | Ready for local testing | Demo requested from Yash Bhargava
2026-07-03 | Phase 1 | Hosted for review | Moved off the laptop so the team could use it in real time
2026-07-06 | Phase 1 | Production deploy | Docker stack, security hardening, Contabo server
2026-07-08 | Phase 1 | Opened to the team | Contabo, credentials issued to Basant, Neha, Khushi
2026-07-09 | Phase 1 | Deep audit | 87 of 88 findings remediated
2026-07-10 | Phase 1 | Permission matrix shared | Catalog and role summary delivered to Ajay Sharma
2026-07-13 | Phase 1 | Capacity & dual deadlines | Team capacity board, internal vs client deadlines, overdue alerts
2026-07-14 | Phase 1 | PII boundary | First-login profile collection; personal details restricted server-side
2026-07-15 | Phase 1 | Regularisation with HR approval | Attendance regularisation request flow
2026-07-17 | Phase 1 | Renamed to Squark Dashboard | Performance rework, expenses module, WFH as a work mode
2026-07-19 | Phase 1 | Collaboration + HR modules | Chat, presence, polls; announcements, policy library, org chart, appraisals
2026-07-20 | Phase 1 | Three-batch delivery plan agreed | Batch 1 Home/Projects/Tasks/Capacity; Batch 2 Calendar-People; Batch 3 Appraisals-Settings
2026-07-22 | Phase 1 | Project types + task templates | HML, Claim Chart, FTO, Novelty and the rest, each with a standard task list
2026-07-23 | Phase 1 | PID system + patent portal | SQ_26_27_nnn identifiers and the confidential patent portal
2026-07-24 | Phase 1 | 14-agent QA sweep | Four critical confidentiality issues found and closed the same day
2026-07-27 | Phase 1 | PID lifecycle + Log Time rebuild | Allocator with expiry and tail-reclaim; two-option time logging
2026-07-29 | Phase 1 | Feedback rounds 2 and 3 | Timesheet backfill windows, PID reopen, project chat mentions
2026-07-30 | Phase 1 | PID Ledger + daily digest | Lifecycle states, search, and the 10pm admin digest
2026-08-05 | Phase 1 | Delivery clients | One client, many PIDs; client identity access-restricted
2026-08-07 | Phase 1 | Technology domains | A second axis beside project type; project list ordering
2026-08-12 | — | PHASE 1 CLOSED | 22 modules live. Outstanding items formally recorded. Phase 2 opened the same day
2026-08-13 | Phase 2 | Clients & patents | Archive vs remove, tagging after creation, the client ledger, formerHandles
2026-08-13 | Phase 2 | Team spaces + BD pipeline | Somewhere for work that is not a client project; deals, stages, forecasting
2026-08-16 | Phase 2 | Measurement integration | Internal work counts in timesheets, capacity and performance
2026-08-17 | Phase 2 | Reporting lines established | The appraisal module works for the first time; 2026 holiday calendar
2026-08-19 | Phase 2 | Eight pull requests merged | BD role, departments, org chart, four concurrency races, performance metrics, ledger links
2026-08-23 | Phase 2 | Patent ID to number lookup | Three visibility tiers; feedback module; client ledger billing rate; self-as-PM
2026-08-25 | Phase 2 | Status report delivered | Phase 1 and 2 summary; shortened to 3 pages on request
2026-08-26 | Phase 2 | Defect hunt | PID/client split, IST timezone bug, December leave lockout — all fixed

## Meetings & Communications
Date | With | Type | Subject | Artefact / Outcome
2026-06-30 | Yash Bhargava | Message | Performance Dashboard ready for local testing; demo requested
2026-07-03 | Yash Bhargava | Review | Asked for it to be hosted rather than demoed on a laptop, 'so we can use it in realtime' | Cloudflare tunnel link + credentials shared
2026-07-03 | Yash Bhargava | Access | Non-admin login requested to see the user-end view; Basant, Neha, Khushi added to testing | SquarkIP-credentials.xlsx
2026-07-06 | Ajay Sharma | Meeting | First contact — joined meeting
2026-07-08 | Team | Deployment | Dashboard hosted on the Contabo server and opened for team testing | https://217.76.59.244.sslip.io
2026-07-10 | Ajay Sharma | Demo | Demo of the Task Tracker requested and given
2026-07-10 | Ajay Sharma | Document | Permission matrix, catalog and role summary shared | Permission-Matrix.xlsx
2026-07-10 | Yash Bhargava | Feedback | 'The profiles are wrong designation wise' | Led to the roster/designation alignment work
2026-07-13 | Ajay Sharma | Scheduling | Dashboard review deferred — 'currently packed with a bunch of stuff'
2026-07-14 | Ajay Sharma | Document | Patent classification assignment submitted; KT (knowledge transfer) prepared and shared | /kt-5d2bef8509/
2026-07-15 | Ajay Sharma | Meeting | Dashboard session held at 4 PM
2026-07-15 | Ajay Sharma | Instruction | Asked for an Excel of the changes being made — 'which feature we have introduced' | Meeting_Logs.xlsx shared
2026-07-15 | Ajay Sharma | Scope | Instruction to review every TeamNest feature and integrate the most required ones
2026-07-16 | Ajay Sharma | Planning | Asked for a batch-of-features plan with timeline targets; recurring meeting created | Agreed: batches of 3 modules per meeting
2026-07-16 | Ajay Sharma | Target | 'Lets target to upgrade and finalise this on the highest level by next week' | 4-5 more people to be added to testing
2026-07-17 | Ajay Sharma | Status | Progress status requested and delivered | Squark-Dashboard-Project-Status.pdf
2026-07-17 | Ajay Sharma | Scope | OneNote integration raised; Gurgaon team to begin testing
2026-07-20 | Ajay Sharma | Meeting | Call held at 12:00; three-batch delivery plan agreed
2026-07-20 | Ajay Sharma | Feedback | Tool observation workbook shared for integration in the next stage | Tool Observation - Ajay.xlsx
2026-07-22 | Ajay Sharma | Feedback | Punch-in section requested on Home; admin rights removed to see the user-end view
2026-07-22 | Ajay Sharma | Instruction | Profile data to be cleaned for the selected testers before team testing
2026-07-22 | Ajay Sharma | Scope | Training module recorded as a LAST-PHASE item (upload, access grant, head and reviewer allotment) | Still deferred as of Aug 2026
2026-07-23 | Ajay Sharma | Delivery | PID and Patent ID work reported complete; self-testing and a written summary requested
2026-07-24 | Ajay Sharma | Meeting | Team Capacity review — tentative/pending leave to be visible, project-style layout, click-a-day to allot
2026-07-24 | Ajay Sharma | Feedback | Capacity to be grouped Gurgaon / Jaipur, ordered A-Z
2026-07-24 | Ajay Sharma | Delivery | Changes completed and deployed live (21:53)
2026-07-30 | Ajay Sharma | Feedback | Feedback batch: PID reopen, PID ledger detail, timesheet calendar, expenses, punch locations, daily digest, backfill windows | See Feedback Log sheet
2026-08-04 | Ajay Sharma | Feedback | Feedback batch: timesheets real-time, attendance 24h glitch, comp-off, roles/capacity, projects, calendar, digest, colours | See Feedback Log sheet
2026-08-06 | Ajay Sharma | Feedback | Feedback batch: comp-off credit/debit, half-day leave, project tiles, PID generation, calendar Monday-start, reports | See Feedback Log sheet
2026-08-25 | Ajay Sharma | Status | Phase 1 & Phase 2 summary with timeline shared | Squark-Dashboard-Status-Report.pdf
2026-08-25 | Ajay Sharma | Feedback | 'This very big data. Unable to understand' — shorter version requested and delivered | Report cut from 5 pages to 3
2026-08-26 | Ajay Sharma | Question | Asked whether Phase 2 features are in development or need discussion | Training module integration flagged for discussion

## Feedback Log
Date | Module | Feedback / Request | Status
2026-07-20 | Attendance | Regularise — missing punch-in/out: route to HR or Manager | Delivered
2026-07-20 | Attendance | Regularise — show punch in/out timing when applied | Delivered
2026-07-20 | Attendance | Average punch in & punch out | Delivered
2026-07-20 | Projects | Standard task lists per type — HML (4 steps), CC from Client (3), CC New (3) | Delivered
2026-07-20 | Calendar | Finalise types; remove Milestone; names A-Z | Delivered — milestones removed entirely
2026-07-20 | Leaves | Leave rules per TeamNest — 1.5 CL, 0.5 SL, marriage leave, comp-off, optional holiday | Delivered
2026-07-20 | Leaves | Who can set holidays — HR or not; verify | Delivered
2026-07-20 | Leaves | Past leave cannot be requested | Delivered
2026-07-20 | Leaves | Two leave types on the same day / WFH on a CL day | Delivered
2026-07-20 | Leaves | Comp-off approval routing to HR / Yash / Manager; project ID optional | Delivered
2026-07-20 | Expenses | Who approves, type, verify the request is actually raised, how credited | Delivered
2026-07-20 | Reports | Editable but issue marking it done; rethink what a project report should achieve | Delivered
2026-07-20 | Appreciation | Should be part of the whole project system; count on Home; list of tasks/projects | Delivered
2026-07-20 | Discussion | Paste screenshots (SNIPPET); notify new members; show chat history; remove lock icons | Delivered
2026-07-20 | Company | Define the tab — appreciation, org chart, policy, directory | Delivered
2026-07-30 | PID | PID reopen reuses the same PID and flips the ledger back to Working | Delivered
2026-07-30 | PID | PID Ledger full detail + CSV export carrying every project field | Delivered
2026-07-30 | Timesheet | Colour-coded monthly fill calendar; enlarge; day logs on click | Delivered
2026-07-30 | Timesheet | 2-week reminder when a required day is unfilled | Delivered
2026-07-30 | Timesheet | Backfill windows — 1mo free / 1-3mo Super-Admin approval / >3mo blocked | Delivered
2026-07-30 | Expenses | Currency option removed — amounts are INR | Delivered
2026-07-30 | Attendance | HR / Super-Admin can see punch-in/out coordinates with map links | Delivered
2026-07-30 | Digest | Daily admin digest at 10pm IST summarising the day | Delivered
2026-07-30 | Projects | Optional task hours; admin PM delegation; custom project-type templates | Delivered
2026-07-30 | Projects | Subtasks restored on the task page | Delivered
2026-07-30 | Capacity | Task creation not working for the respective person; assignment not showing | Delivered
2026-08-04 | Timesheet | Fill calendar updates in real time; bigger tiles; clickable days; day detail panel | Delivered
2026-08-04 | Attendance | Fixed the 24-hour glitch — shifts capped at 16h; auto punch-out at 23:59 IST | Delivered
2026-08-04 | Attendance | First-login punch-in popup with WFH option | Delivered
2026-08-04 | Attendance | Area column reverse-geocoded; full column names; date picker; custom-range CSV export | Delivered
2026-08-04 | Comp-off | Half-day / full-day; reflected in attendance; becomes a required timesheet day | Delivered
2026-08-04 | Capacity | Role-first staffing — one person can hold PM + Reviewer + Analyst on one task | Delivered
2026-08-04 | Capacity | Single-person allocation window from the capacity board | Delivered
2026-08-04 | Projects | Save-as-template persists; project type shown as a tag; PID text bigger | Delivered
2026-08-04 | Calendar | Team Calendar frozen header/member column; celebrations (birthdays, anniversaries) | Delivered
2026-08-04 | Digest | Admin-editable send time; detailed /digest screen; deep links | Delivered
2026-08-04 | Home | Requests hub aggregating pending regularisations + comp-off claims | Delivered
2026-08-06 | Timesheet | Logged hours capped at 16 per entry, enforced server-side | Delivered
2026-08-06 | Attendance | Work past 23:59 requires a regularisation declaring the late-night hours | Delivered
2026-08-06 | Comp-off | Two movements — Avail (spend) and Credit (claim); balance panel rewritten | Delivered
2026-08-06 | Leaves | Half-day / full-day carried through balances, calendars and attendance | Delivered
2026-08-06 | Projects | PID never assigned automatically — must be deliberately generated | Delivered
2026-08-06 | Projects | Mark-complete only when every task is closed; client delivery date captured | Delivered
2026-08-06 | Calendar | Monday-Sunday everywhere; company holidays; tentative/pending leave visible | Delivered
2026-08-06 | Reports | Per-project report; search by PID or name; export per project | Delivered
2026-08-06 | Colours | Calendar palette replaced — previous colours not differentiable at a glance | Delivered
2026-07-22 | Training | Training module upload, access grant, head and reviewer allotment | DEFERRED — last phase, awaiting go-ahead
2026-07-30 | Permissions | 8 red 'to be discussed' cells in the Permission Matrix | Resolved — matrix now has zero red cells
2026-08-04 | Reports | Project Report — how should it look and what is the output? | Open — needs definition

## Phase 2 Status
Module | Item | Status | Remarks
Attendance | Work-from-home prompt on punch in | Complete | Was already in place
Project | Client and Patent IDs | Complete | Now linked to the ledgers
Project | Other teams — HR, Sales, BD | Partial | Sales not modelled separately
HR | Holidays | Complete | 2026 calendar with optional holidays
HR | Policies | Complete | Ten policies, with version control
Company | Feed, recognition, policies, directory | Complete | Organisation chart included
People | Departments | Complete | Full management screen
Appraisal | All six sub-items | Complete | Parameters fully editable
Performance | 360° project feedback | Partial | General feedback in place; project round pending
Productivity | Input; billable hours | Partial | Billable hours complete; "Input" undefined

## Modules Delivered
Area | Module | What it does | Phase
Access & identity | Login / sessions | Cookie + JWT login. Deactivating an account cuts a held token on the very next request | 1
Access & identity | RBAC | Nine roles over a four-level model — role presets, per-user grants, per-user denials, project membership | 1
Access & identity | Org passcode | Second factor on changes that cannot be walked back | 1
Access & identity | Audit log | Every significant action recorded with actor and time | 1
Delivery | Projects | Nine patent-analysis types, each with a standard task list created on the spot | 1
Delivery | PID system | SQ_26_27_nnn identifiers, multiple rounds under one PID, full ledger | 1
Delivery | Tasks & subtasks | Role-first staffing — one person can hold PM + Reviewer + Analyst on one task | 1
Delivery | Timesheets | Backdating windows: free under a month, approved to three, refused beyond | 1
Delivery | Patents & clients | Confidential portal; handles shown everywhere, real numbers restricted | 1
People ops | Attendance | Punch in/out, WFH as a work mode, 16h shift cap, auto punch-out at 23:59 IST | 1
People ops | Regularisation | Missing-punch requests routed to HR with approval | 1
People ops | Leave | Annual quotas, half days, business-day counting, holidays excluded | 1
People ops | Comp-off | Claim a worked weekend, HR approves, credit spent as CO leave | 1
People ops | Expenses | Submit to reimbursement; the submitter cannot approve their own | 1
People ops | People directory | Personal details restricted to Admin, Super Admin and HR — removed server-side | 1
People ops | Appraisals | Structured cycles: self-assessment, manager review, acknowledgement | 1
People ops | Policies | Library with version control, so an acknowledgement means something | 1
Insight | Performance | Output-based scoring, charts, contribution heatmap | 1
Insight | Team capacity | Who is free and when; click a day to allot | 1
Insight | Reports | Per-project and range reports, CSV and PDF export | 1
Insight | Daily digest | Admin summary at a configurable hour, everything deep-linked | 1
Insight | Calendars | Personal and team; holidays, leave, WFH, birthdays and anniversaries | 1
Clients | Client ledger | Work and value per client, recomputed live; billing rate makes value derived | 2
Clients | Client records | Contact, country, industry, account manager, rate, engagement start | 2
Non-delivery | Team spaces | Somewhere for HR/BD work — no PID, no client, out of both ledgers | 2
Non-delivery | BD pipeline | Deals, stages, activity history, forecasting, win/loss reporting | 2
Org | Departments | Full management screen with a named head | 2
Org | Org chart | Built from the reporting lines | 2
People ops | Feedback | Any colleague about any colleague; author, HR and reporting manager can read it | 2
Patents | Patent lookup | Handle to number and back, open to the whole firm; client stays restricted | 2

## Open Items
Ref | Item | Position | Status | Input required
Phase 2 / 7 | Training module | Deferred on instruction 22 Jul 2026. Nothing built | DEFERRED | Go-ahead, and what a training record holds
Phase 2 / 3 | Sales as a separate function | One BD role, no Sales role. Treated as one desk | Open — decision | Is Sales separate from BD?
Phase 2 / 11 | 360° project feedback | General feedback complete; the project-scoped round is not built. No longer blocked | Open — ready to build | Everyone rates each other, or manager rates team?
Phase 2 / 12 | Productivity "Input" | Billable hours complete. "Input" has never been defined | Open — needs definition | One sentence: what does Input count?
Phase 1 debt | 2027 holidays | Zero rows loaded. From 1 Jan 2027 every holiday counts as a working day | Open — HIGH, by 31 Dec 2026 | The dated list, and which are optional
Phase 1 debt | Email transport | Notifications are in-app only | Open | Do you want it? SMTP credentials?
Phase 1 debt | Exit process | Access is withdrawn immediately on deactivation; reassigning open work is manual | Open | Build a reassignment flow?
Phase 1 debt | Shared HR account | hr@squarkip.com acts with no individual attribution in the audit log | Open | Who inherits it, or keep as-is?
Phase 1 debt | Punch location retention | Home coordinates kept indefinitely on WFH punches | Open | Retention period — 90 days? 1 year?
Phase 1 debt | Fixed escalation address | Was hardcoded in source; now configurable by environment | Resolved 25 Aug 2026 | —
Phase 1 debt | Reporting lines | Were absent, blocking appraisals and the org chart | Resolved 17 Aug 2026 | —
Security | Legacy client codes | 6 of 11 codes derive from client names (MLK to Malikie). Script built and dry-runs clean | Open — your call | Approval to re-code; changes IDs on future documents
Delivery | Unmerged branch | 5 commits including two defect fixes affecting daily use | Awaiting merge | Approval to merge and deploy

## Bugs Found & Fixed
Found | Area | Defect | Impact | Status
2026-08-19 | Performance | Hours logged always zero — a NULL-unsafe filter excluded every ordinary entry | 1,509 hours invisible; one person ranked second having completed nothing | Fixed
2026-08-19 | Concurrency | Four races on check-then-write | The 16-hour daily cap could be breached; duplicate leave for one absence | Fixed
2026-08-19 | Auth | Signing out did not end the session | The access token stayed usable for up to fifteen minutes | Fixed
2026-08-19 | Deployment | A missing flag blanked every secret | Took the live site down; the on-screen error pointed at the database | Fixed
2026-08-23 | Projects | "May run a project" and "may mint a PID" were one flag | Managers and Senior Consultants told to hand their own matter to an Admin | Fixed
2026-08-23 | Patents | Number search validated the typed string, not the normalised one | "%%%" became a match-everything wildcard — the lookup handed out the list | Fixed
2026-08-23 | Patents | 404 for unknown vs 403 for not-yours | Told apart, the route became a directory of which patent IDs are real | Fixed
2026-08-24 | Patents | Seed wrote unpadded handles, the formatter minted padded ones | Typing Pat_MLK_001 failed to find Pat_MLK_1 — a patent plainly on screen | Fixed
2026-08-25 | Settings | Logo upload and Archive Organization were dead buttons | Clicking either did nothing but raise "coming soon" | Fixed
2026-08-26 | Architecture | One PID could end up meaning two different clients | Ledger billed round 1 to one client and round 2 to another under one identifier | Fixed
2026-08-26 | Attendance | Ten call sites used the UTC day instead of the IST day | For 5.5h every night: marking attendance for TODAY refused as "in the future" | Fixed
2026-08-26 | Leave | Quota year read from today, not from the leave | In December nobody could book January leave — refused against the old quota | Fixed
2026-08-26 | Patents | Deleted patents still listed as live tags on projects | A handle shown on screen that resolved to nothing | Fixed
2026-08-26 | Reporting | chainGaps counted a patent used when its only project was deleted | Two screens gave opposite answers about the same patent | Fixed

## Pull Requests
PR | Created | Merged | Title | Branch | Status
1 | 2026-06-25 | 2026-07-06 | Build out SquarkIP dashboard: live API integration, real seed data, c… | Admin---Module | Merged
2 | 2026-07-08 | 2026-07-08 | Squarkip dashboard snapshot | squarkip-dashboard-snapshot | Merged
3 | 2026-07-08 | 2026-07-08 | feat(auth): self-service change-password + org password-reset script | squarkip-dashboard-snapshot | Merged
4 | 2026-07-10 | 2026-07-10 | feat: file attachments/media + organization step-up passcode(after discussion with Ajay Sir) | fix/deep-audit-2026-07 | Merged
5 | 2026-07-13 | 2026-07-13 | Team capacity, dual deadlines, overdue alerts, project requests — plus 5 fixes | fix/deep-audit-2026-07 | Merged
6 | 2026-07-13 | 2026-07-13 | Password recovery that actually works, and un-freeze the task/project plan | fix/planning-and-password-recovery | Merged
7 | 2026-07-13 | 2026-07-13 | Harden Team Capacity for production: close a cross-tenant leak, fix edges, open it from projects | fix/capacity-hardening | Merged
8 | 2026-07-14 | 2026-07-14 | Roster: offboard Riya Bhola, intern-cohort designations, add Geetesh Rathore | chore/roster-2026-07 | Merged
9 | 2026-07-14 | 2026-07-14 | User profiles: collect joining details on first sign-in, with a hard PII boundary | feat/user-profile | Merged
10 | 2026-07-14 | 2026-07-14 | docs: knowledge-transfer guide for the whole system | docs/kt | Merged
11 | 2026-07-14 | 2026-07-14 | chore: never let dashboard screenshots reach the public repo | chore/ignore-kt-shots | Merged
12 | 2026-07-14 | 2026-07-14 | Fix: modal action buttons could scroll off-screen | fix/modal-overflow | Merged
13 | 2026-07-14 | 2026-07-14 | Make the data tables usable on mobile | fix/mobile-tables | Merged
14 | 2026-07-15 | 2026-07-15 | feat(attendance): regularization requests with HR approval + fixes | feat/attendance-regularization-holidays-notif-autoread | Merged
15 | 2026-07-15 | 2026-07-15 | feat(projects,capacity): completion lifecycle, deadline extend, emergency-leave coverage | feat/project-lifecycle-capacity-extend-coverage | Merged
16 | 2026-07-15 | 2026-07-15 | feat(capacity,attendance): retrospective view, comp-off, drop Overloaded | feat/capacity-history-compoff | Merged
17 | 2026-07-16 | 2026-07-16 | feat(capacity,tasks,auth): sticky dates, deadline cleanup, drill-down, idle logout, assigned-by | feat/capacity-deadlines-assignee-autologout | Merged
18 | 2026-07-17 | 2026-07-17 | feat(ui,projects): rename to Squark Dashboard, meaningful icons, billable review, cleanups | feat/rename-icons-billable-cleanups | Merged
19 | 2026-07-17 | 2026-07-17 | feat(performance): clearer layout, interactive donuts, explained metrics | feat/performance-charts-metrics | Merged
20 | 2026-07-17 | 2026-07-17 | fix(tasks,billable,capacity): dropdown overlay, subtask uncheck, plan align, billable inheritance, leave visibility | fix/task-panel-billable-capacity | Merged
21 | 2026-07-17 | 2026-07-17 | feat(projects,capacity): drop approval gate, fix designations, detach capacity date bar | feat/no-approval-designations-fixed-datebar | Merged
22 | 2026-07-17 | 2026-07-17 | feat(auth): recover a forgotten organization passcode via account password | feat/org-passcode-recovery | Merged
23 | 2026-07-17 | 2026-07-17 | chore(db): compile update-designations script into the prod image | chore/compile-designation-script | Merged
24 | 2026-07-17 | 2026-07-17 | feat(expenses,attendance,discuss): expense module, WFH work mode, punch validation, weekend comp-off, channel rename | feat/expenses-wfh-punch-compoff-rename | Merged
25 | 2026-07-22 | 2026-07-22 | fix: QA findings remediation — object-level authz, validation, cross-tenant scoping (P1–P8) | fixes-attendance-leaves-projects | Merged
26 | 2026-07-22 | 2026-07-22 | feat(rbac): add Senior Research Associate role + align roster to designations | roster-senior-research-associate | Merged
27 | 2026-07-22 | 2026-07-22 | chore(db): clear the 9 members' personal activity for a clean test slate | clear-seed-activity | Merged
28 | 2026-07-22 | 2026-07-22 | feat(home,timesheets): punch from Home + Timesheets sidebar module | feat-punch-home-timesheets-module | Merged
29 | 2026-07-22 | 2026-07-22 | docs(research): patent HML ranking + claim-chart system research brief | docs-patent-hml-research | Merged
30 | 2026-07-22 | 2026-07-22 | feat(projects): project type on creation + auto-generated task workflow | feat-project-types-templates | Merged
31 | 2026-07-22 | 2026-07-22 | fix(home): move the Punch In card to the top of the dashboard | fix-home-punch-top | Merged
32 | 2026-07-22 | 2026-07-22 | feat(patents,projects): PID + confidential Patent portal + project-module fixes | feat-pid-patent-portal | Merged
33 | 2026-07-23 | 2026-07-23 | feat(patents): patent documents (upload-to-create + attach) + passcode/home tweaks | feat-patent-documents | Merged
34 | 2026-07-23 | 2026-07-23 | fix(patents,documents): robustness — disk storage, dedup, re-creatable codes, doc passcode | fix-patent-robustness | Merged
35 | 2026-07-23 | 2026-07-23 | fix(patents): filename-gated uploads + editable client codes + non-stale project client | fix-patent-small-fixes | Merged
36 | 2026-07-24 | 2026-07-24 | feat: workspace rebuild — PID flow, offices, profile gate, capacity, timesheets | feat-rebuild-pid-offices-timesheets | Merged
37 | 2026-07-25 | 2026-07-25 | QA remediation: deep-test (P0/B/C) + Home module + 9-6 IST | qa-deeptest-workhours | Merged
38 | 2026-07-27 | 2026-07-27 | Timesheets "Other" category + QA Rounds 2-3 remediation (Patents + Tasks) | qa-deeptest-workhours | Merged
39 | 2026-07-27 | 2026-07-27 | Log Time: 2 options (Project task w/ Assign-PID-later toggle) + Other with Title | qa-deeptest-workhours | Merged
40 | 2026-07-27 | 2026-07-27 | Log Time: Project title + auto-filled mandatory PID | qa-deeptest-workhours | Merged
41 | 2026-07-27 | 2026-07-27 | Log Time: keep Project + Task when "Assign PID later" is on (hide only PID) | qa-deeptest-workhours | Merged
42 | 2026-07-27 | 2026-07-27 | PID lifecycle + PM picker + review-before-attach + role-based task staffing | qa-deeptest-workhours | Merged
43 | 2026-07-27 | 2026-07-27 | PID: continuing-series (destroy-on-expiry, tail-reclaim); drop give-back; hide type+PM from reviewer | qa-deeptest-workhours | Merged
44 | 2026-07-27 | 2026-07-27 | PID reviewer can set project type + manager on attach | qa-deeptest-workhours | Merged
45 | 2026-07-27 | 2026-07-27 | Fix PID Ledger crash on legacy/unknown reservation status | qa-deeptest-workhours | Merged
46 | 2026-07-27 | 2026-07-27 | reset-keep-one-project: delete all projects except one (keep users/RBAC) | qa-deeptest-workhours | Merged
47 | 2026-07-28 | 2026-07-28 | Task screen: single page, dropdown progress, auto-sum est. hours | qa-deeptest-workhours | Merged
48 | 2026-07-28 | 2026-07-28 | Task PM defaults to project manager; remove progress dropdown | qa-deeptest-workhours | Merged
49 | 2026-07-28 | 2026-07-28 | Enforce task-assignment for time logging + capacity/performance consistency | qa-deeptest-workhours | Merged
50 | 2026-07-28 | 2026-07-28 | Batch A: expense placeholder, capacity per-project filter, remove Discuss | qa-deeptest-workhours | Merged
51 | 2026-07-28 | 2026-07-28 | Batch B: PID export CSV + Super-Admin PID detail + re-initialize completed project | qa-deeptest-workhours | Merged
52 | 2026-07-28 | 2026-07-28 | Batch C: mandatory location on attendance punch in/out | qa-deeptest-workhours | Merged
53 | 2026-07-28 | 2026-07-28 | Batch D: new project-type task lists + custom project types | qa-deeptest-workhours | Merged
54 | 2026-07-28 | 2026-07-28 | RBAC: additive permission-matrix grants (calendar/issue/tasklist/timesheet) | qa-deeptest-workhours | Merged
55 | 2026-07-29 | 2026-07-29 | Second feedback round: PID reopen/detail, timesheet calendar+reminder, expense currency, punch locations, daily digest | qa-deeptest-workhours | Merged
56 | 2026-07-29 |  | Timesheet backfill windows + Super-Admin approval flow | qa-deeptest-workhours | Closed
57 | 2026-07-29 | 2026-07-29 | Timesheet backfill windows + Super-Admin approval flow | timesheet-backfill-approval | Merged
58 | 2026-07-29 | 2026-07-29 | Third feedback round: optional hours, graded/compact calendars, expense notify, subtasks, admin PM delegation, PID Ledger module | feedback-batch3-tasks-timesheets-pid | Merged
59 | 2026-07-29 | 2026-07-29 | Team Calendar tab + redesigned timesheet/attendance calendars | calendar-team-tab-ui-redesign | Merged
60 | 2026-07-29 | 2026-07-29 | Team Calendar: multi-month scrollable timeline (1mo back / 3mo ahead) | team-calendar-multimonth | Merged
61 | 2026-07-29 | 2026-07-29 | Subtasks: add / rename / delete from the task page | subtask-edit-delete | Merged
62 | 2026-07-29 | 2026-07-29 | Project chat: @mention project members in the Discussion tab | project-chat-mentions | Merged
63 | 2026-07-29 | 2026-07-29 | Permission Matrix (New): apply role permission removals | permission-matrix-removals | Merged
64 | 2026-07-30 | 2026-07-30 | PID Ledger: lifecycle states (completed/closed) + search by PID/client | pid-ledger-states-search | Merged
65 | 2026-07-30 | 2026-07-30 | Timesheets rewrite + attendance 24h fix + project fixes (batch 1 of feedback) | timesheets-attendance-projects-fixes | Merged
66 | 2026-07-30 | 2026-07-30 | Attendance team-location: area field, full labels, 1-year view + CSV export | attendance-team-location | Merged
67 | 2026-07-30 | 2026-07-30 | Team Calendar: frozen date bar rewrite + upcoming = this/next month | team-calendar-rewrite | Merged
68 | 2026-07-30 | 2026-07-30 | Profile wedding anniversary → birthdays/anniversaries in calendar + Jaipur area | profile-anniversary-celebrations | Merged
69 | 2026-07-30 | 2026-07-30 | Role-first task staffing (multi-role, per-role hours+deadline) + capacity assign + assign-error fix | roles-based-staffing | Merged
70 | 2026-07-30 | 2026-07-30 | Comp-off: half/full day + timesheet & attendance integration + pending asterisk | compoff-halfday-integration | Merged
71 | 2026-07-30 | 2026-07-30 | Daily digest: editable time + detail screen; login punch-in prompt | digest-punchprompt | Merged
72 | 2026-07-30 | 2026-07-30 | Colour consistency pass: align calendar + PID-ledger status palettes | color-consistency | Merged
73 | 2026-07-31 | 2026-07-31 | Fix 3 bugs: regularization enum, project/task date pickers, super-admin comp-off visibility | three-bug-fixes | Merged
74 | 2026-07-31 | 2026-07-31 | Capacity single-person allocation + dynamic attendance area + custom-range export | capacity-attendance-features | Merged
75 | 2026-07-31 | 2026-07-31 | Homepage requests hub + Reports project detail + range activity digest | requests-hub-reports | Merged
76 | 2026-08-04 | 2026-08-04 | Bigger Team Calendar cells + real-time/stale-data fixes | calendar-size-realtime | Merged
77 | 2026-08-04 | 2026-08-04 | Team Calendar: start on today + real ‹ › navigation (range model fix) | team-calendar-today-first | Merged
78 | 2026-08-04 |  | Calendar: collapsible Upcoming rail + remove Compact density | calendar-collapsible-rail | Closed
79 | 2026-08-04 | 2026-08-04 | Calendar: collapsible Upcoming rail + remove Compact density | calendar-rail-collapse-v2 | Merged
80 | 2026-08-04 | 2026-08-05 | 14-item feedback batch: attendance truth, calendar foundation, half-day leave & WFH, project/PID UX | feedback-batch-2026-08 | Merged
81 | 2026-08-11 | 2026-08-11 | One status for a task, wherever you look at it | matrix-and-module-fixes-2026-08 | Merged
82 | 2026-08-13 | 2026-08-19 | Phase 2 — clients and patents: identity, tagging, and a client ledger | phase2-clients-patents-ledger | Merged
83 | 2026-08-13 | 2026-08-19 | Squark Dashboard — clients & patents, team spaces, BD pipeline, calendar, appraisals | phase3-team-spaces | Merged
84 | 2026-08-19 | 2026-08-19 | Release 2026 08 19 | release-2026-08-19 | Merged
85 | 2026-08-19 | 2026-08-19 | Business Development is a role, and a manager is not a project manager | fix-bd-role-reporting-lines | Merged
86 | 2026-08-19 | 2026-08-19 | Departments you can actually manage, an org chart that exists, policies with something in them | departments-orgchart-policies | Merged
87 | 2026-08-19 |  | Four races that were one bug, and five smaller findings from testing | fix-races-and-test-findings | Closed
88 | 2026-08-19 | 2026-08-19 | Four races that were one bug, and five smaller findings from testing | fix-races-and-test-findings | Merged
89 | 2026-08-19 | 2026-08-19 | A runbook for deploying #85, #86 and #88 to Contabo | deploy-runbook-0819 | Merged
90 | 2026-08-19 |  | The deploy command was missing -f docker-compose.prod.yml | fix-deploy-runbook | Closed
91 | 2026-08-19 | 2026-08-19 | The deploy command was missing -f docker-compose.prod.yml | fix-deploy-runbook | Merged
92 | 2026-08-19 | 2026-08-19 | The env file is .env.production, and compose only auto-reads .env | fix-runbook-envfile2 | Merged
93 | 2026-08-19 | 2026-08-19 | The pipeline now says something back | bd-pipeline-intelligence | Merged
94 | 2026-08-19 | 2026-08-19 | Performance was measuring the wrong things, and one metric was always zero | performance-metric-fixes | Merged
95 | 2026-08-19 | 2026-08-19 | Parameters you can edit, policies that know what people agreed to, reports with a period | module-improvements | Merged
96 | 2026-08-19 | 2026-08-19 | The four ledgers were islands: connect them, and say where the chain breaks | connect-the-ledgers | Merged
97 | 2026-08-19 |  | One runbook covering everything on main, not just the first three PRs | runbook-complete | Closed
98 | 2026-08-19 | 2026-08-19 | One runbook covering everything on main, not just the first three PRs | runbook-complete-v2 | Merged
99 | 2026-08-19 | 2026-08-19 | The deploy that took the site down cannot happen again, and two other loose ends | close-open-issues | Merged
100 | 2026-08-23 | 2026-08-24 | The analyst could see the handle and never the patent it stood for | self-pm-feedback-ledger-patent-mapping | Merged
101 | 2026-08-24 | 2026-08-24 | Anyone can manage their own project, and anyone can resolve a patent ID | patent-directory-and-self-pm | Merged
102 | 2026-08-24 | 2026-08-24 | Fix the container build: the re-code script could not compile | fix-container-build-seed | Merged

## Commits
Date | SHA | Author | Subject
2026-06-24 | 5fb2e03 | Anant Gupta | Initial commit — SquarkIP pdash project management system
2026-06-25 | bb01082 | Anant Gupta | Build out SquarkIP dashboard: live API integration, real seed data, collapsible sidebar, interactive Kanban/Gantt/Calendar, progress color scale
2026-06-28 | 4f9a5b0 | Anant Gupta | Add auth, RBAC, attendance, and performance modules; live API + real Postgres
2026-07-06 | 3401e42 | Anant Gupta | Production deploy: Docker stack, security hardening, RBAC guards, health checks, migrations
2026-07-06 | c79e5dc | Anant Gupta | Add one-command Contabo deploy script + docs; harden web port to localhost bind
2026-07-06 | 7f9609a | Anant Gupta | contabo-deploy: keep current SSH port open in ufw (SSH is on 2222, not 22); make Caddy start non-fatal
2026-07-06 | 08f2db5 | Anant Gupta | fix(web): bake API_ORIGIN at build time so Next standalone proxies /api to the api service
2026-07-06 | cf36e52 | Anant Gupta | fix(seed): run ts-node with --skip-project so the DB seed works in the api container
2026-07-06 | c0b93e0 | Anant Gupta | fix(seed): pass ALLOW_PROD_SEED=true so the first-run seed clears the prod guard
2026-07-06 | 18a1396 | Anant Gupta | refactor(seed): compile the seed to JS at build time; run with plain node (no ts-node)
2026-07-07 | dd32cc8 | Anant Gupta | fix(ui): portal notifications + user menu; task assignee avatars + overflow; shared primitives
2026-07-08 | 975401b | Anant Gupta | fix(tasks): assignees tab + inline status/progress everywhere + real activity + a11y
2026-07-08 | 3b17d0a | Anant Gupta | fix(ui): use DateField for all date/time inputs (click anywhere opens picker)
2026-07-08 | 74d2c7b | AnantSQIP | Merge pull request #2 from AnantSQIP/squarkip-dashboard-snapshot
2026-07-08 | 748af24 | Anant Gupta | feat(auth): self-service change-password + org password-reset script
2026-07-08 | 5a36632 | AnantSQIP | Merge pull request #3 from AnantSQIP/squarkip-dashboard-snapshot
2026-07-09 | d4e3d50 | Anant Gupta | fix(audit): remediate deep-audit findings (~87/88)
2026-07-10 | 53f623d | Anant Gupta | feat: file attachments/media + organization step-up passcode
2026-07-11 | e0978ef | AnantSQIP | Merge pull request #4 from AnantSQIP/fix/deep-audit-2026-07
2026-07-13 | d66c041 | Anant Gupta | fix(ops): supervisor could never restart the app after a reboot
2026-07-13 | 4fe96a3 | Anant Gupta | feat: team capacity, dual deadlines, overdue alerts, project requests
2026-07-13 | 92c08e7 | Anant Gupta | fix(deadlines): a date could never be removed once set
2026-07-13 | 89b1637 | Anant Gupta | fix(deploy): make permission re-grants runnable in prod, and stop pinning the stale branch
2026-07-13 | 119d4f5 | Anant Gupta | fix(rbac): regrant-roles could deny every live user mid-run
2026-07-13 | c32d40a | Anant Gupta | fix(security): the step-up passcode shipped as a known default in a public repo
2026-07-13 | b1582f5 | AnantSQIP | Merge pull request #5 from AnantSQIP/fix/deep-audit-2026-07
2026-07-13 | 3e02da1 | Anant Gupta | fix(auth): a password reset did not actually let anyone back in
2026-07-13 | 9c14592 | Anant Gupta | fix(planning): a task's and a project's plan were frozen at creation
2026-07-13 | 00b1b5b | AnantSQIP | Merge pull request #6 from AnantSQIP/fix/planning-and-password-recovery
2026-07-13 | 2411969 | Anant Gupta | fix(capacity): production hardening — close a cross-tenant leak, plus edges; open it from projects
2026-07-14 | a0cbc7e | AnantSQIP | Merge pull request #7 from AnantSQIP/fix/capacity-hardening
2026-07-14 | 2a59792 | Anant Gupta | chore(roster): offboard Riya Bhola; intern cohort designations; add Geetesh Rathore
2026-07-14 | 6cd7ab8 | AnantSQIP | Merge pull request #8 from AnantSQIP/chore/roster-2026-07
2026-07-14 | 03ac5d4 | Anant Gupta | feat(profile): collect joining details on first sign-in, with a hard PII boundary
2026-07-14 | d7b0d3e | AnantSQIP | Merge pull request #9 from AnantSQIP/feat/user-profile
2026-07-14 | f35e108 | Anant Gupta | docs: knowledge-transfer guide for the whole system
2026-07-14 | eb416ab | AnantSQIP | Merge pull request #10 from AnantSQIP/docs/kt
2026-07-14 | ec49016 | Anant Gupta | chore: never let dashboard screenshots reach the public repo
2026-07-14 | c0c3ddf | AnantSQIP | Merge pull request #11 from AnantSQIP/chore/ignore-kt-shots
2026-07-14 | 26a83d2 | Anant Gupta | fix(ui): modal action buttons could scroll off-screen — bound every dialog
2026-07-14 | 201719a | AnantSQIP | Merge pull request #12 from AnantSQIP/fix/modal-overflow
2026-07-14 | 84fea12 | Anant Gupta | fix(mobile): make the data tables usable on a phone
2026-07-14 | 9f2c7ec | AnantSQIP | Merge pull request #13 from AnantSQIP/fix/mobile-tables
2026-07-15 | 579aad6 | AnantSQIP | feat(attendance): regularization requests with HR approval + fixes (#14)
2026-07-15 | 09e66a2 | AnantSQIP | feat(projects,capacity): completion lifecycle, deadline extend, emergency-leave coverage (#15)
2026-07-16 | 5cee74a | AnantSQIP | feat(capacity,attendance): retrospective view, comp-off, drop Overloaded (#16)
2026-07-16 | 55e2184 | AnantSQIP | feat(capacity,tasks,auth): sticky dates, deadline cleanup, drill-down, idle logout, assigned-by (#17)
2026-07-17 | dc64342 | AnantSQIP | feat(ui,projects): rename to Squark Dashboard, meaningful icons, billable review, cleanups (#18)
2026-07-17 | fa8a4b9 | AnantSQIP | feat(performance): clearer layout, interactive donuts, explained metrics (#19)
2026-07-17 | f918c12 | AnantSQIP | fix(tasks,billable,capacity): dropdown overlay, subtask uncheck, plan align, billable inheritance, leave visibility (#20)
2026-07-17 | f43d53c | AnantSQIP | feat(projects,capacity): drop project approval gate, fix designations, detach capacity date bar (#21)
2026-07-17 | 36456b1 | AnantSQIP | feat(auth): recover a forgotten organization passcode via account password (#22)
2026-07-17 | f499e50 | AnantSQIP | chore(db): compile update-designations script into the prod image (#23)
2026-07-17 | 7ea44ae | AnantSQIP | feat(expenses,attendance,discuss): expense module, WFH work mode, punch validation, weekend comp-off, channel rename (#24)
2026-07-19 | 6d860e3 | Anant Gupta | feat(discuss,presence,search,calendar,attendance): Teams-inspired Phase 1 + WFH request flow
2026-07-19 | fffb7b3 | Anant Gupta | feat(discuss,calendar): Phase 2 — polls, saved messages, recurring meetings, meeting notes/chat, ICS export
2026-07-19 | e613478 | Anant Gupta | feat(discuss,settings): Phase 3 — voice clips, @channel/tag mentions, read receipts, governance
2026-07-19 | bcb6410 | Anant Gupta | feat(lifecycle): TeamNest TN Phase 1 — employee onboarding, offboarding & HR letters
2026-07-19 | 88fbfea | Anant Gupta | feat(company): TeamNest TN Phase 2 — announcements, HR policy library & org chart
2026-07-20 | 83dd8da | Anant Gupta | feat(appraisals): TeamNest TN Phase 3 — structured performance appraisal cycles
2026-07-20 | 0dfce04 | Anant Gupta | revert(lifecycle): remove the Employee Lifecycle module; enforce @squarkip.com on add-member
2026-07-20 | 165c747 | Anant Gupta | feat(attendance): avg punch in/out, regularisation routes to HR+Yash only, show punch times
2026-07-20 | e72e782 | Anant Gupta | feat(leaves,compoff): rename leave heading, one-leave-per-day guard, comp-off PID + HR/Manager/Yash routing
2026-07-20 | b79a4ec | Anant Gupta | feat(billable): projects billable by default; each person sets billability on their own time
2026-07-20 | b75e23a | Anant Gupta | feat(projects): remove milestones entirely (model + logic)
2026-07-20 | 1334228 | Anant Gupta | feat(issues): repurpose Issues as technical issues → non-billable time entries
2026-07-20 | 66aa6a6 | Anant Gupta | feat(ui): alphabetical people lists everywhere + bottom-left notification pop-ups
2026-07-20 | 83cb84f | Anant Gupta | feat(company): replace Org chart with a Company Directory (name, designation, email, contact)
2026-07-20 | cc40a91 | Anant Gupta | feat(discuss): remove lock icons, discoverable rename, paste screenshots (SNIPPET)
2026-07-20 | 4128bb3 | Anant Gupta | feat(company): Recognition / Rewards tab (per financial year, visible to all)
2026-07-20 | 1935e34 | Anant Gupta | fix(search): guardrail global search — never surface results a user can't access
2026-07-22 | ed4ede7 | AnantSQIP | fix: QA findings remediation — object-level authz, validation, cross-tenant scoping (P1-P8) (#25)
2026-07-22 | d4b8de9 | AnantSQIP | feat(rbac): add Senior Research Associate role + align roster to designations (#26)
2026-07-22 | 0569ced | AnantSQIP | chore(db): clear the 9 members' personal activity for a clean test slate (#27)
2026-07-22 | e507cf0 | AnantSQIP | feat(home,timesheets): punch from Home + Timesheets sidebar module (#28)
2026-07-22 | 524728b | Anant Gupta | docs(research): patent HML ranking + claim-chart system research brief
2026-07-22 | f5ed3ec | AnantSQIP | Merge pull request #29 from AnantSQIP/docs-patent-hml-research
2026-07-22 | 85d315c | AnantSQIP | feat(projects): project type on creation + auto-generated task workflow (#30)
2026-07-22 | 771c90a | AnantSQIP | fix(home): move the Punch In card to the top of the dashboard (#31)
2026-07-23 | feb9271 | AnantSQIP | feat(patents,projects): PID + confidential Patent portal + project-module fixes (#32)
2026-07-23 | 9955034 | AnantSQIP | feat(patents): patent documents + passcode/home tweaks (#33)
2026-07-23 | 9f69ec5 | AnantSQIP | fix(patents,documents): robustness — disk storage, dedup, re-creatable codes, doc passcode (#34)
2026-07-23 | 955eeb8 | AnantSQIP | fix(patents): filename-gated uploads + editable client codes + non-stale project client (#35)
2026-07-24 | 78bbd9c | AnantSQIP | feat: workspace rebuild — PID flow, offices, profile gate, capacity, timesheets (#36)
2026-07-24 | 5aea39f | Anant Gupta | chore(hours): set the working day to 9am–6pm IST (8 working hrs) for capacity + performance
2026-07-24 | 19ff0de | Anant Gupta | docs(qa): deep-test plan + Squark IP domain brief
2026-07-24 | aec8caf | Anant Gupta | docs(qa): Batch 1 (Projects) findings — 4 HIGH, 6 MED + verified-good
2026-07-24 | 39afc2f | Anant Gupta | docs(qa): Batches 2-5 findings (Patents CRIT x2, Timesheets/Attendance HIGH, HR)
2026-07-24 | a5c54e4 | Anant Gupta | docs(qa): complete 8-agent deep-test sweep — synthesis + fix plan
2026-07-24 | 1492cbc | Anant Gupta | docs(qa): launch second agent wave (6 agents: 4 gap-closing + 2 dedicated capacity)
2026-07-24 | 4b95f1b | Anant Gupta | docs(qa): complete second wave (6 agents) — full 14-agent sweep synthesis
2026-07-24 | 41037be | Anant Gupta | fix(security): P0 batch — close the 4 CRIT confidentiality holes + 2 integrity bypasses
2026-07-24 | 6254bdc | Anant Gupta | docs(qa): mark P0 fix batch done (commit 41037be)
2026-07-24 | 0991785 | Anant Gupta | fix(security): Batch B (1/2) — search scoping, departments authz, admin-reset rank, calendar
2026-07-24 | dc34ab6 | Anant Gupta | fix(capacity,tasks,rewards): Batch B (2/2) — capacity load-math, retrospective, workflow, rewards
2026-07-24 | e5c1ac4 | Anant Gupta | feat(aws): Batch C1 — health 503, background-job runner gate, boot-migrate gate (config-gated)
2026-07-24 | 6776f94 | Anant Gupta | feat(aws): Batch C2 — pluggable document storage with an S3 driver (config-gated)
2026-07-24 | b4c935c | Anant Gupta | docs(qa): mark Batch B + C done; document AWS-readiness env switches
2026-07-25 | 34c10f3 | Anant Gupta | fix(home): root-cause Home-module QA remediation (28-tester sweep)
2026-07-25 | 27abd6c | AnantSQIP | QA remediation: deep-test (P0/B/C) + Home module + 9-6 IST (#37)
2026-07-27 | 5e50029 | Anant Gupta | feat(timesheets)+fix(qa): "Other" non-project time + Rounds 2-3 QA remediation
2026-07-27 | e501d85 | AnantSQIP | Timesheets "Other" category + QA Rounds 2-3 remediation (#38)
2026-07-27 | 4a01184 | Anant Gupta | feat(timesheets): 2-option Log Time — Project task (w/ Assign-PID-later toggle) + Other (titled)
2026-07-27 | 0768067 | AnantSQIP | Log Time: 2 options — Project task (Assign-PID-later toggle) + Other with Title (#39)
2026-07-27 | 74dc6bd | Anant Gupta | fix(timesheets): Project-task layout — Project title + auto-filled mandatory PID
2026-07-27 | 26f150f | AnantSQIP | Merge pull request #40 from AnantSQIP/qa-deeptest-workhours
2026-07-27 | 2646372 | Anant Gupta | fix(timesheets): keep Project + Task when "Assign PID later" is on — hide only the PID
2026-07-27 | 74aeb95 | AnantSQIP | Merge pull request #41 from AnantSQIP/qa-deeptest-workhours
2026-07-27 | ab1a20e | Anant Gupta | feat(projects,tasks): PID lifecycle + PM picker + review-before-attach + role-based task staffing
2026-07-27 | d0340d0 | AnantSQIP | Merge pull request #42 from AnantSQIP/qa-deeptest-workhours
2026-07-27 | 01e9c3b | Anant Gupta | feat(pid): continuing-series allocator (destroy-on-expiry, tail-reclaim); drop give-back; hide type+PM from reviewer
2026-07-27 | 6bdf598 | AnantSQIP | Merge pull request #43 from AnantSQIP/qa-deeptest-workhours
2026-07-27 | 7180a4d | Anant Gupta | fix(pid): reviewer can set the project type + project manager on the PID attach screen
2026-07-27 | 1d7851d | AnantSQIP | Merge pull request #44 from AnantSQIP/qa-deeptest-workhours
2026-07-27 | ae24f0b | Anant Gupta | fix(pid): PID Ledger no longer crashes on a legacy/unknown reservation status
2026-07-27 | 21a627d | AnantSQIP | Merge pull request #45 from AnantSQIP/qa-deeptest-workhours
2026-07-27 | ec26c3b | Anant Gupta | chore(db): reset-keep-one-project script — delete all projects except one, keep users/RBAC
2026-07-28 | 2e10c09 | AnantSQIP | Merge pull request #46 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | b8bc72e | Anant Gupta | feat(tasks): single-page task screen — dropdown progress, auto-sum est. hours, tidier layout
2026-07-28 | 9f8af12 | AnantSQIP | Merge pull request #47 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | cddb023 | Anant Gupta | feat(tasks): task PM defaults to the project manager; remove the progress dropdown
2026-07-28 | 3c75e79 | AnantSQIP | Merge pull request #48 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | 62ff4f1 | Anant Gupta | fix(timesheets,capacity,performance): enforce task-assignment for time logging + consistency fixes
2026-07-28 | 1a734ad | AnantSQIP | Merge pull request #49 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | 0b15557 | Anant Gupta | feat(batch-a): expense placeholder, capacity per-project filter, remove Discuss
2026-07-28 | 5d2e09d | AnantSQIP | Merge pull request #50 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | fbe891a | Anant Gupta | feat(batch-b): PID export CSV + Super-Admin PID detail + re-initialize completed project
2026-07-29 | aeb1d46 | AnantSQIP | Merge pull request #51 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | bf97f67 | Anant Gupta | feat(batch-c): mandatory location capture on attendance punch in/out
2026-07-29 | ed74ad6 | AnantSQIP | Merge pull request #52 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | 6b3138f | Anant Gupta | feat(batch-d): new project-type task lists + custom project types (one-off or saved org-wide)
2026-07-29 | 5aebe2e | AnantSQIP | Merge pull request #53 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | e0cf6ce | Anant Gupta | feat(rbac): apply additive permission-matrix grants (calendar/issue/tasklist/timesheet)
2026-07-29 | ffc399e | AnantSQIP | Merge pull request #54 from AnantSQIP/qa-deeptest-workhours
2026-07-29 | 3d3e149 | AnantSQIP | Second feedback round: PID reopen/detail, timesheet calendar, expense currency, punch locations, daily digest (#55)
2026-07-29 | 9ffde6c | AnantSQIP | Timesheet backfill windows + Super-Admin approval flow (#57)
2026-07-29 | 13d1f1c | AnantSQIP | Third feedback round: hours/calendars/expenses/subtasks/PM-delegation/PID-ledger (#58)
2026-07-29 | 23d48d3 | AnantSQIP | Team Calendar tab + redesigned timesheet/attendance calendars (#59)
2026-07-29 | 439f4f8 | AnantSQIP | Team Calendar: multi-month scrollable timeline (#60)
2026-07-29 | d2ad351 | AnantSQIP | Subtasks: add / rename / delete from the task page (#61)
2026-07-29 | 70d972c | AnantSQIP | Project chat: @mention project members (#62)
2026-07-29 | 9adcaef | AnantSQIP | Permission Matrix (New): apply role permission removals (#63)
2026-07-30 | 4495206 | AnantSQIP | PID Ledger: lifecycle states + search (#64)
2026-07-30 | bec21cd | AnantSQIP | Timesheets rewrite + attendance 24h fix + project fixes (#65)
2026-07-30 | f665401 | AnantSQIP | Attendance team-location: area, full labels, 1-year view + CSV (#66)
2026-07-30 | 936f0a7 | AnantSQIP | Team Calendar: frozen date bar rewrite + upcoming scope (#67)
2026-07-30 | 2bafbaa | AnantSQIP | Profile wedding anniversary + calendar celebrations + Jaipur area (#68)
2026-07-30 | 5c7db42 | AnantSQIP | Role-first task staffing + capacity assign + assign-error fix (#69)
2026-07-30 | 8ffcb2e | AnantSQIP | Comp-off: half/full day + timesheet & attendance integration (#70)
2026-07-30 | 946f42f | AnantSQIP | Daily digest detail screen + editable time + login punch prompt (#71)
2026-07-30 | c37c846 | AnantSQIP | Colour consistency pass: calendars + PID ledger (#72)
2026-07-31 | 98ec416 | AnantSQIP | Fix 3 bugs: regularization enum, date pickers, super-admin comp-off visibility (#73)
2026-07-31 | 9777b11 | AnantSQIP | Capacity single-person allocation + dynamic attendance area + custom-range export (#74)
2026-07-31 | 8b6027f | AnantSQIP | Homepage requests hub + Reports project detail + range digest (#75)
2026-08-04 | 3a0137d | AnantSQIP | Bigger Team Calendar cells + real-time/stale-data fixes (#76)
2026-08-04 | ac4a12a | AnantSQIP | Team Calendar: start on today + real navigation (#77)
2026-08-04 | fbcdbe6 | AnantSQIP | Calendar: collapsible Upcoming rail + remove Compact density (#79)
2026-08-05 | e718252 | AnantSQIP | Attendance truth, calendars, leave, projects, Daily Digest module, multi-round PIDs (#80)
2026-08-05 | db3b9df | Anant Gupta | Project type never reached the cards; task groups could not be renamed
2026-08-05 | 669cd89 | Anant Gupta | Multi-round consistency: capacity, timesheet↔ledger reconciliation, performance attribution
2026-08-05 | a9da94c | Anant Gupta | One bar per task group, and the new-project form captures the full detail
2026-08-05 | 5946250 | Anant Gupta | A PID with live work no longer reads as closed or retired
2026-08-05 | 0eea5f1 | Anant Gupta | Remove the empty "General" group that sat above every typed project's real work
2026-08-05 | b5327e9 | Anant Gupta | Delivery clients: one client, many PIDs, code shareable and identity restricted (backend)
2026-08-05 | 34b353d | Anant Gupta | Client ledger UI: codes across the dashboard, identity behind a lock
2026-08-05 | db7cb90 | Anant Gupta | A project's client can be changed after creation
2026-08-05 | bf0c9cc | Anant Gupta | Take the Gurgaon client system off main — it is a local demo, not a Contabo deploy
2026-08-07 | 4cac73a | Anant Gupta | Multi-project PIDs for everyone, one end state instead of two, and one colour for WFH
2026-08-07 | 54a8a63 | Anant Gupta | Leaves, Attendance and Expenses in the shape the team already reads
2026-08-07 | 5a17850 | Anant Gupta | Link a person's page across to their roles and permissions
2026-08-07 | c5edac4 | Anant Gupta | Comp-off moves in Credit and Debit, and the balance card says what it means
2026-08-07 | 682f890 | Anant Gupta | Leave is whole days and half days, and nothing in between
2026-08-07 | 7e267a9 | Anant Gupta | Technology domains, an order for the project list, client-call time, and no more encashment
2026-08-11 | d642707 | Anant Gupta | One status for a task, wherever you look at it
2026-08-11 | 73ddb4a | Anant Gupta | Leave you no longer need can be called off, by you or by HR
2026-08-12 | e5ff124 | Anant Gupta | Saying where your work has got to is not editing the task
2026-08-12 | dc8dfbf | Anant Gupta | The PID ledger asks two questions about hours, not three
2026-08-12 | fa0b0f4 | Anant Gupta | Who issues a PID, who can be a Project Manager, and who sees the capacity board
2026-08-12 | 29dc114 | Anant Gupta | "Send now" sends now
2026-08-12 | 44e1e0b | Anant Gupta | Working from home is a button again, not a form
2026-08-12 | 8e220e8 | Anant Gupta | Work from home is asked once, when the day starts
2026-08-12 | 830c618 | Anant Gupta | The roster decides the roles, not the seed
2026-08-12 | bcfdd69 | Anant Gupta | A job title is not a permission
2026-08-12 | d272ad1 | Anant Gupta | Three things found by actually using the thing
2026-08-12 | 4af65c0 | Anant Gupta | Phase 1 is closed; write down where the line falls
2026-08-12 | 79c4a9b | Anant Gupta | Put the Phase 1 paperwork under version control
2026-08-13 | fb42c2d | Anant Gupta | A client is more than a code on a patent
2026-08-13 | bc554bd | Anant Gupta | Somewhere for work that is not a client project
2026-08-13 | 30cb3a0 | Anant Gupta | Three bugs the review found, one of them mine from an hour ago
2026-08-13 | 2cbb7f3 | Anant Gupta | Team spaces: the module, not just the tables
2026-08-13 | b397828 | Anant Gupta | A pipeline is a forecast, not a promise
2026-08-13 | 2f5d56b | Anant Gupta | Write down what Phase 3 turned into
2026-08-13 | 74db31e | Anant Gupta | Withdraw the "Phase 3" label — this is Phase 2, part two
2026-08-16 | 7bc41bc | Anant Gupta | Internal work counts, without pretending to be client work
2026-08-16 | 6d13a46 | Anant Gupta | Everything agreed for Phase 2 is now built
2026-08-16 | 35db28e | Anant Gupta | No, it was not complete: team tasks could never be closed
2026-08-16 | 14ed82f | Anant Gupta | A plan for appraisals, and the reason it cannot start yet
2026-08-17 | 60b8efd | Anant Gupta | The real 2026 calendar, and optional holidays that are actually optional
2026-08-17 | a96c6b0 | Anant Gupta | Reporting lines, and the appraisal module works for the first time
2026-08-17 | 74d3d82 | Anant Gupta | Appraisals: what people are rated on, not just a number
2026-08-18 | 3d2a958 | Anant Gupta | Keep the source calendar next to the data derived from it
2026-08-18 | 7f99833 | Anant Gupta | The reporting-lines script would not have existed in production
2026-08-18 | 3b7d9fe | Anant Gupta | A runbook for this release, in the order the steps actually depend on
2026-08-19 | c006c3d | Anant Gupta | The appraisal screen — the part that made the rest usable
2026-08-19 | 40c4bb7 | AnantSQIP | Clients & patents, team spaces, the BD pipeline, the 2026 calendar and appraisals (#83)
2026-08-19 | 73aaffc | AnantSQIP | Business Development is a role, and a manager is not a project manager (#85)
2026-08-19 | e7f4995 | AnantSQIP | Departments you can actually manage, an org chart that exists, policies with something in them (#86)
2026-08-19 | d2fda5f | AnantSQIP | Four races that were one bug, and five smaller findings from testing (#88)
2026-08-19 | 0bcf201 | AnantSQIP | A runbook for deploying #85, #86 and #88 to Contabo (#89)
2026-08-19 | 6d59d0c | AnantSQIP | The deploy command was missing -f docker-compose.prod.yml (#91)
2026-08-19 | b06c76c | AnantSQIP | The env file is .env.production, and compose only auto-reads .env (#92)
2026-08-19 | 6c509d8 | AnantSQIP | The pipeline now says something back (#93)
2026-08-19 | 6644a42 | AnantSQIP | Performance was measuring the wrong things, and one metric was always zero (#94)
2026-08-19 | 7bce2da | AnantSQIP | Parameters you can edit, policies that know what people agreed to, reports with a period (#95)
2026-08-19 | e532adf | AnantSQIP | The four ledgers were islands: connect them, and say where the chain breaks (#96)
2026-08-19 | 5185e92 | AnantSQIP | One runbook covering everything on main, not just the first three PRs (#98)
2026-08-19 | ecd707c | AnantSQIP | The deploy that took the site down cannot happen again, and two other loose ends (#99)
2026-08-24 | e7a9419 | AnantSQIP | Patent ID to number mapping, feedback, client ledger detail, self-as-PM (#100)
2026-08-24 | 7ad581d | AnantSQIP | Anyone can manage their own project, and anyone can resolve a patent ID (#101)
2026-08-24 | 6c47219 | AnantSQIP | Fix the container build: the re-code script could not compile (#102)2026-08-25¦da77a6e¦Anant Gupta¦Two dead buttons in Settings, and an address that needed a release to change
2026-08-25 | 5e7a4cd | Anant Gupta | Cut the status report from five pages to three
2026-08-26 | 482b09a | Anant Gupta | One PID could end up meaning two different clients
2026-08-26 | 788dde5 | Anant Gupta | Between midnight and 05:30 IST the system used yesterday's date
2026-08-26 | a943cd4 | Anant Gupta | In December, nobody could book January's leave

## Daily Activity
Date | Commits | Phase
2026-06-24 | 1 | Phase 1
2026-06-25 | 1 | Phase 1
2026-06-28 | 1 | Phase 1
2026-07-06 | 7 | Phase 1
2026-07-07 | 1 | Phase 1
2026-07-08 | 5 | Phase 1
2026-07-09 | 1 | Phase 1
2026-07-10 | 1 | Phase 1
2026-07-11 | 1 | Phase 1
2026-07-13 | 11 | Phase 1
2026-07-14 | 13 | Phase 1
2026-07-15 | 2 | Phase 1
2026-07-16 | 2 | Phase 1
2026-07-17 | 7 | Phase 1
2026-07-19 | 5 | Phase 1
2026-07-20 | 12 | Phase 1
2026-07-22 | 8 | Phase 1
2026-07-23 | 4 | Phase 1
2026-07-24 | 15 | Phase 1
2026-07-25 | 2 | Phase 1
2026-07-27 | 17 | Phase 1
2026-07-28 | 13 | Phase 1
2026-07-29 | 12 | Phase 1
2026-07-30 | 9 | Phase 1
2026-07-31 | 3 | Phase 1
2026-08-04 | 3 | Phase 1
2026-08-05 | 10 | Phase 1
2026-08-07 | 6 | Phase 1
2026-08-11 | 2 | Phase 1
2026-08-12 | 11 | Phase 2
2026-08-13 | 7 | Phase 2
2026-08-16 | 4 | Phase 2
2026-08-17 | 3 | Phase 2
2026-08-18 | 3 | Phase 2
2026-08-19 | 14 | Phase 2
2026-08-24 | 3 | Phase 2
2026-08-25 | 2 | Phase 2
2026-08-26 | 3 | Phase 2

## Branches
Branch | Last commit | Subject
cmp/admin | 2026-06-25 | Build out SquarkIP dashboard: live API integration, real seed data, collapsible sidebar, interactive Kanban/Gantt/Calendar, progress color scale
cmp/main | 2026-06-24 | Initial commit — SquarkIP pdash project management system
origin/Admin---Module | 2026-06-25 | Build out SquarkIP dashboard: live API integration, real seed data, collapsible sidebar, interactive Kanban/Gantt/Calendar, progress color scale
origin/attendance-team-location | 2026-07-30 | feat(attendance): team-location area + full Punch In/Out labels + 1-year view + CSV export
origin/calendar-collapsible-rail | 2026-08-04 | feat(calendar): collapsible Upcoming rail + drop the Compact density
origin/calendar-rail-collapse-v2 | 2026-08-04 | feat(calendar): collapsible Upcoming rail + drop the Compact density
origin/calendar-size-realtime | 2026-08-04 | fix(calendar,realtime): bigger readable Team Calendar cells + close the stale-data gaps
origin/calendar-team-tab-ui-redesign | 2026-07-29 | feat(calendar,timesheets,attendance): Team Calendar tab + redesigned calendar layouts
origin/capacity-attendance-features | 2026-07-31 | feat(attendance): dynamic area from punch coords (reverse-geocode) + custom-range CSV export
origin/chore/compile-designation-script | 2026-07-17 | chore(db): compile update-designations script into the prod image
origin/chore/ignore-kt-shots | 2026-07-14 | chore: never let dashboard screenshots reach the public repo
origin/chore/roster-2026-07 | 2026-07-14 | chore(roster): offboard Riya Bhola; intern cohort designations; add Geetesh Rathore
origin/clear-seed-activity | 2026-07-22 | chore(db): also clear the 9 members' personal activity/content for a clean test slate
origin/client-system-demo | 2026-08-05 | A project's client can be changed after creation
origin/color-consistency | 2026-07-30 | style(colors): align status palettes so the same meaning is the same colour
origin/compoff-halfday-integration | 2026-07-30 | feat(compoff): half/full day + timesheet & attendance integration + pending asterisk
origin/digest-punchprompt | 2026-07-30 | feat(attendance): first-login-of-the-day punch-in prompt (with "punch in later")
origin/docs-patent-hml-research | 2026-07-22 | docs(research): Squark IP full service-domain brief (FTO, invalidity/novelty, RE, risk & strategy)
origin/docs/kt | 2026-07-14 | docs: knowledge-transfer guide for the whole system
origin/feat-patent-documents | 2026-07-23 | feat(patents): patent documents (upload-to-create + attach) + friendlier passcode & home tweaks

## Architecture — PID & Patents
Concept | Format / rule | Explanation
Client | Code of 2–5 characters | The grouping a patent belongs to. New codes are OPAQUE so they say nothing about the client
Client identity | Super Admin only | Which company a code stands for is the confidential fact this system protects
Patent handle | Pat_<clientCode>_<serial> | The shareable identifier. Appears in task titles, pickers and project pages
Patent number | e.g. US 10,123,456 | NOT confidential in itself — patents are published documents. The client ASSOCIATION is what is secret
formerHandles | Array of retired handles | A client-code rename re-mints every handle; the old ones stay resolvable so documents already sent still work
PID | SQ_<FY>_<serial> | The Project ID quoted on reports and invoices. Never auto-assigned — someone generates it deliberately
PID rounds | Same code, roundSeq 1..N | A returning client's next job is a new project under the SAME PID. Every round is one client's work
RULE | One PID, one client | Enforced on both write paths. Previously a round could be re-tagged to another client, splitting the PID
RULE | One project, one client | All patents tagged to a project must belong to the same client
RULE | Tagged patents decide the client | With patents, the client is derived and locked. With none, it is named directly
Visibility tier 1 | patent.view — every role but HR | Handle only, plus resolve one patent either direction. Never the client
Visibility tier 2 | Members of the project | The full list of that project's patents with numbers. Never the client
Visibility tier 3 | patent.manage + passcode | Browse the portfolio, see the client, export. Super Admin only
Anti-harvest | 120 lookups per person per hour | Counted from the audit log, so it survives restarts and cannot be reset by logging out
Audit | Count and project, never numbers | A log that quotes the secret has copied the leak somewhere longer-lived
NOTE | Actual number-to-handle pairs are deliberately NOT reproduced in this workbook | Putting the mapping in a shared spreadsheet would defeat the confidentiality design it documents. It is available in the system to those entitled to it

## QA Findings
# | Severity | Module | Batch | Finding | Category | Where | Reproduced
1 | High | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Regularization approval accepts check-in/check-out on unrelated dates, writing corrupt totalHours (441h) onto a single day | data-integrity | POST /attendance/me/regularize + /regularizations/:id/approve | yes
2 | High | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Designated hr@squarkip.com account is role-stacked (HR+Manager+Senior Consultant) and can reach delivery surfaces HR must not | rbac | roles / POST /projects, POST /tasks | yes
3 | Medium | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Privileged row-level regularize does not validate reason or newStatus (inconsistent with the employee request path) | ab-inconsistency | POST /attendance/:id/regularize | yes
4 | Medium | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Admin manual mark accepts arbitrary/empty attendance status with no validation, silently corrupting reports | data-integrity | POST /attendance/mark | yes
5 | Medium | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | POST /attendance/mark accepts arbitrary/invalid status strings (no enum validation) | validation | POST /attendance/mark | yes
6 | Medium | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | POST /attendance/mark has no self-action guard and accepts future dates — attendance-manager can fabricate attendance | rbac | POST /attendance/mark | yes
7 | Medium | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Regularization request check-in/out times are not constrained to the day being regularized | validation | POST /attendance/me/regularize | yes
8 | Medium | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Regularization accepts check-in/check-out on arbitrary dates with no hours cap; on approval a single day gets absurd totalHours | data-integrity | POST /attendance/me/regularize | yes
9 | Medium | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Missing required date field crashes with HTTP 500 instead of a clean 400 (systemic across attendance/leave write endpoints) | validation | POST /attendance/me/regularize (also POST /attendance/wfh, POST /leave/compoff, POST /leave/requests) | yes
10 | Medium | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Leave-request creation notifies no approver, while WFH / comp-off / regularization all push a notification to their reviewers | ab-inconsistency | POST /leave/requests | yes
11 | Medium | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | POST /leave/requests accepts an arbitrary leaveType not in the org's leave types (quota bypass) | data-integrity | POST /leave/requests | yes
12 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | GET /attendance/me/month (and users/:userId/month) crashes with 500 for out-of-range year values | validation | GET /attendance/me/month | yes
13 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | HALF_DAY is counted as a full present day in attendance rate and hours summary | logic | GET /attendance/me/month and GET /attendance/org/summary
14 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Half-day is counted as a full present day in attendanceRate | domain | GET /attendance/me/month, GET /attendance/org/summary
15 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Org summary with from > to returns all-zero rows instead of a validation error | validation | GET /attendance/org/summary | yes
16 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | A user on approved leave for an entire window shows attendanceRate 0% instead of N/A | ux | GET /attendance/org/summary
17 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | GET /attendance/org/summary with from > to silently returns all-zero rows instead of a validation error | validation | GET /attendance/org/summary | yes
18 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | org-scoped attendance/leave endpoints trust a client-supplied organizationId/userId with no check it matches the caller's org | rbac | GET /attendance/org/summary
19 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Org-scoped read endpoints trust a client-supplied organizationId / path userId instead of the session org (latent horizontal-auth gap) | rbac | GET /attendance/org/summary, GET /attendance/users/:userId/month
20 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | GET /projects and /projects/:id are ungated — pure HR (no project.view) can read the full delivery project list/details | rbac | GET /projects | yes
21 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Regularization request accepts check-in/out unbound to the request date and not reconciled with requested status (bogus multi-day totalHours on approval) | data-integrity | POST /attendance/me/regularize | yes
22 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Regularization can mark weekends/holidays as PRESENT and has no lower bound on how old a date can be | logic | POST /attendance/me/regularize | yes
23 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Regularization requestType is a free-form string (no enum); requestType=WFH records workMode WFH on approval, bypassing the dedicated WFH approval routing | ab-inconsistency | POST /attendance/me/regularize
24 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Missing required date field returns HTTP 500 instead of a clean 400 across every attendance/leave create endpoint | validation | POST /attendance/me/regularize (and /attendance/wfh, /leave/requests, /leave/compoff, /leave/holidays) | yes
25 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Regularization request/approve lacks the ON_LEAVE/HOLIDAY guard that punch() enforces — can silently overwrite an approved-leave/holiday day | ab-inconsistency | POST /attendance/me/regularize + POST /attendance/regularizations/:id/approve
26 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Missing required 'date' field returns unhandled HTTP 500 on several attendance/leave write endpoints | validation | POST /attendance/me/regularize, POST /attendance/mark, POST /leave/holidays | yes
27 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Missing/negative required date fields return 500 Internal Server Error instead of 400 across attendance & leave endpoints | validation | POST /attendance/me/regularize, POST /attendance/wfh, POST /leave/requests, GET /attendance/me/month | yes
28 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | WFH↔Leave overlap guard is one-directional (leave create does not check WFH; WFH ignores pending leave) | ab-inconsistency | POST /attendance/wfh vs POST /leave/requests | yes
29 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Comp-off claim accepts negative hoursWorked and an unbounded past workDate, with no server-side proof of work | validation | POST /leave/compoff | yes
30 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | POST /leave/holidays returns 500 (not 400) when 'date' is missing | validation | POST /leave/holidays | yes
31 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Leave quota is enforced for comp-off (CO) at request time but NOT for normal leave types (CL/SL/EL) | ab-inconsistency | POST /leave/requests | yes
32 | Low | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Leave request accepts an arbitrary/unknown leaveType string (no validation against configured leave types) | data-integrity | POST /leave/requests | yes
33 | Info | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | HALF_DAY counts as a full present day in attendance-rate and 'present' tally | domain | GET /attendance/me/month (summary) and GET /attendance/org/summary
34 | Info | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | GET /attendance/org/summary does not validate from<=to (returns zero-filled rows for a reversed range) | validation | GET /attendance/org/summary | yes
35 | Info | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Regularization approval reach is wider than the stated 'HR + Yash only' routing | ab-inconsistency | GET /attendance/regularizations/pending, POST /attendance/regularizations/:id/approve
36 | Info | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Read/summary endpoints trust client-supplied organizationId/userId with no org-membership check (mitigated: single-org deployment) | rbac | GET /leave/types, GET /leave/holidays, GET /attendance/org/summary, GET /attendance/users/:id/month
37 | Info | attendance | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | POST /attendance/mark accepts an arbitrary, unvalidated status string | validation | POST /attendance/mark
38 | High | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Non-comp-off leave has no quota enforcement: an employee can request far more days than the annual quota, and the balance display silently hides the overage | logic | POST /leave/requests | yes
39 | High | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | TOCTOU race lets an employee create multiple overlapping leaves on the same day, defeating the one-leave-per-day rule | data-integrity | POST /leave/requests | yes
40 | High | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Employee can cancel an already-approved, entirely-past leave — deletes the ON_LEAVE attendance and refunds the balance | logic | POST /leave/requests/:id/cancel
41 | High | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Cancelling an approved leave leaves an orphaned LEAVE calendar event (person still shows as on-leave on the shared calendar) | data-integrity | POST /leave/requests/:id/cancel | yes
42 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Delivery-surface read endpoints are not permission-gated — HR (and every authenticated role) can read all projects/tasks/issues | rbac | GET /projects, GET /projects/:id, GET /tasks, GET /tasks/:id, GET /issues | yes
43 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Comp-off claimable for a non-working day the employee never actually worked (no timesheet/attendance verification) | domain | POST /leave/compoff | yes
44 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | leaveType is free text and never validated — leave can be applied against a non-existent leave type | validation | POST /leave/requests | yes
45 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No balance/quota enforcement on regular leave types — a user can request far more days than their annual entitlement | logic | POST /leave/requests | yes
46 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | leaveType is free-text and not validated against the org leave-type catalog | validation | POST /leave/requests | yes
47 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | leaveType is not validated against the org's leave types — arbitrary and empty strings are accepted | validation | POST /leave/requests | yes
48 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No quota or maximum-range enforcement for non-CO leave (CO is enforced but CL/SL/EL are not) — 259-day request accepted | ab-inconsistency | POST /leave/requests | yes
49 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Applying for leave notifies no approver — no routing at all (inconsistent with comp-off, which does notify) | ab-inconsistency | POST /leave/requests
50 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | leaveType is never validated against the org's leave-type catalog — arbitrary types accepted and become invisible in balances | validation | POST /leave/requests | yes
51 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | leaveType is not validated against the org's LeaveType catalog — bogus leave types are accepted | validation | POST /leave/requests | yes
52 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Annual leave quota/balance is not enforced and leave duration is unbounded (only comp-off checks credits) | logic | POST /leave/requests | yes
53 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Omitting startDate/endDate (or workDate) returns 500 Internal Server Error instead of a clean 400 | validation | POST /leave/requests, POST /leave/compoff | yes
54 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Missing required date field returns 500 (TypeError) instead of a 400 validation error on 3 leave endpoints | validation | POST /leave/requests, POST /leave/compoff, POST /leave/holidays | yes
55 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Omitting a required date field crashes /leave/* create endpoints with HTTP 500 instead of a 400 | validation | POST /leave/requests, POST /leave/compoff, POST /leave/holidays | yes
56 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Cancelling an APPROVED leave leaves a stale 'on leave' calendar event on the shared calendar | data-integrity | POST /leave/requests/:id/cancel
57 | Medium | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Cancelling an approved leave leaves a stale 'on leave' event on the shared calendar | data-integrity | POST /leave/requests/:id/cancel | yes
58 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Org-scoped leave reads/writes trust a client-supplied organizationId with no actor-org check | rbac | GET /leave/requests/org
59 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Org-scoped leave endpoints trust a client-supplied organizationId instead of deriving it from the session actor (latent cross-tenant path; /types and /holidays have no permission gate) | rbac | GET /leave/requests/org, GET /leave/types, GET /leave/holidays, POST /leave/holidays
60 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | GET /leave/types and /leave/holidays trust a client-supplied organizationId without scoping to the actor's org | rbac | GET /leave/types, GET /leave/holidays
61 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Comp-off claim accepts a negative hoursWorked value | validation | POST /leave/compoff | yes
62 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Negative hoursWorked accepted on a comp-off claim | validation | POST /leave/compoff | yes
63 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Comp-off hoursWorked accepts negative / zero values | validation | POST /leave/compoff | yes
64 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Comp-off submission routing (HR/Manager/Yash) does not match approval authorization (leave.approve, which also includes Admin) | ab-inconsistency | POST /leave/compoff, POST /leave/compoff/:id/approve
65 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Holiday can be created with an empty name | validation | POST /leave/holidays | yes
66 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Backdated (partially-past) leave is accepted, debiting balance for business days that have already elapsed | domain | POST /leave/requests | yes
67 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Leave 'reason' has no length limit — a ~12,000-character reason is accepted and stored | validation | POST /leave/requests | yes
68 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Create-leave endpoint is not gated by the leave.request permission (permission defined in catalog + matrix but never enforced) | rbac | POST /leave/requests
69 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Missing required fields on create-leave returns HTTP 500 instead of a clean 400 | validation | POST /leave/requests | yes
70 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No length cap on leave reason — ~5000-char reason accepted | validation | POST /leave/requests | yes
71 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | POST /leave/requests is not gated by the leave.request permission (only authentication) | rbac | POST /leave/requests
72 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No maximum leave duration; business-day counter loops one calendar day at a time with no cap | validation | POST /leave/requests | yes
73 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Leave 'reason' free-text has no maximum length | validation | POST /leave/requests | yes
74 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Leave can be partially back-dated — a request whose start is in the past is accepted as long as it is not entirely past | domain | POST /leave/requests | yes
75 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Missing required date fields return 500 (unhandled crash) instead of a clean 400 | validation | POST /leave/requests, POST /leave/compoff | yes
76 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Any leave.approve holder can approve/reject any user's leave org-wide; reporting line (user_manager) is ignored (no team scoping) | rbac | POST /leave/requests/:id/approve
77 | Low | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No admin/HR path to revoke or cancel an already-APPROVED leave | domain | POST /leave/requests/:id/cancel, POST /leave/requests/:id/reject
78 | Info | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | GET /leave/types and /leave/holidays are ungated and trust a client-supplied organizationId; leave.request/leave.view.own permissions are never enforced on the self routes | rbac | GET /leave/types, GET /leave/holidays, POST /leave/requests
79 | Info | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Comp-off hoursWorked is stored without validation | validation | POST /leave/compoff
80 | Info | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Past-date rule only blocks entirely-past leave; a backdated leave ending today/future is accepted and retroactively writes ON_LEAVE attendance on approval | logic | POST /leave/requests
81 | Info | leaves | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | POST /leave/requests has no @RequirePermission — the catalog's leave.request permission is not enforced | rbac | POST /leave/requests
82 | Medium | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | POST /leave/compoff returns HTTP 500 (unhandled TypeError) for missing or wrong-typed workDate/reason instead of a 400 | validation | POST /leave/compoff | yes
83 | Medium | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Comp-off can be claimed for an arbitrarily old weekend/holiday — no lower date bound and no actual-work verification | logic | POST /leave/compoff | yes
84 | Medium | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Reason and Project ID (PID) accept unbounded length; 20,000+ char values stored and broadcast verbatim in notifications to all reviewers | validation | POST /leave/compoff | yes
85 | Medium | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Omitting required workDate returns 500 (unhandled TypeError) instead of a clean 400 | validation | POST /leave/compoff | yes
86 | Medium | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | hoursWorked accepts negative, zero, and absurdly large values; a negative-hours claim can be fully approved | validation | POST /leave/compoff | yes
87 | Medium | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No check that the employee actually worked the claimed day — comp-off can be farmed for weekends never worked | logic | POST /leave/compoff (requestCompOff, attendance.module.ts:790-800) | yes
88 | Medium | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Comp-off accepts a fabricated Project ID (PID) — no validation against any real project | validation | POST /leave/compoff (requestCompOff, attendance.module.ts:792) | yes
89 | Medium | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Comp-off can be claimed and approved for a non-working day the employee never actually worked | domain | POST /leave/compoff / approveCompOff | yes
90 | Medium | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | POST /leave/compoff returns 500 (not 400) when workDate is missing or non-string | validation | POST /leave/compoff — requestCompOff | yes
91 | Medium | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Comp-off is credited for a non-working day the employee never actually worked (no proof-of-work check) | domain | requestCompOff eligibility (attendance.module.ts:790-800) | yes
92 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | hoursWorked is stored with no validation — negative and absurdly large values accepted | data-integrity | POST /leave/compoff | yes
93 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | projectRef (PID) and reason are length-unbounded — 3000-char PID accepted | validation | POST /leave/compoff | yes
94 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Comp-off can be claimed and approved for any past weekend/holiday with zero proof of work | domain | POST /leave/compoff | yes
95 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Missing or non-string workDate crashes with 500 instead of a clean 400 | validation | POST /leave/compoff | yes
96 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | hoursWorked accepts negative and physically-impossible values | data-integrity | POST /leave/compoff | yes
97 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No cooldown on resubmission after reject/cancel — approver notification spam | logic | POST /leave/compoff | yes
98 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | projectRef (mandatory PID) is unvalidated free text and seeded projects have no code to enter | data-integrity | POST /leave/compoff | yes
99 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No length cap on reason field | validation | POST /leave/compoff | yes
100 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Comp-off notification routing (role-name based) diverges from approval authorization (permission based) — a Super Admin approver never gets pinged | ab-inconsistency | POST /leave/compoff (notify) vs POST /leave/compoff/:id/approve (authz)
101 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | reason field has no maximum length (10,000-char reason accepted) | validation | POST /leave/compoff (requestCompOff, attendance.module.ts:791,802) | yes
102 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | hoursWorked accepts negative, zero, and absurd values (e.g. -50, 0, 100000) | validation | POST /leave/compoff (requestCompOff, attendance.module.ts:802) | yes
103 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Comp-off approve/reject are not organization-scoped (latent cross-org IDOR) | rbac | POST /leave/compoff/:id/approve, POST /leave/compoff/:id/reject
104 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | hoursWorked accepts negative and absurd values | validation | requestCompOff (attendance.module.ts:790,802) | yes
105 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | reason field has no maximum length | validation | requestCompOff (attendance.module.ts:791,802) | yes
106 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Mandatory projectRef (PID) accepts any free-text string — not validated against real projects | validation | requestCompOff (attendance.module.ts:792,802) | yes
107 | Low | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No lower bound on comp-off work date — claims for weekends years in the past are eligible | domain | requestCompOff (attendance.module.ts:793-798)
108 | Info | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Manager comp-off approval is org-wide with no team scoping — a Manager can approve claims of peers and more-senior staff | rbac | GET /leave/compoff/pending, POST /leave/compoff/:id/approve
109 | Info | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No lower bound on how old a claimed workDate may be | domain | POST /leave/compoff
110 | Info | compoff | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | approve/reject comp-off does not verify the request belongs to the actor's organization (latent cross-org gap) | rbac | POST /leave/compoff/:id/approve, /reject
111 | High | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Cancelling an APPROVED WFH leaves a stale 'Working from home' event on the shared calendar | data-integrity | AttendanceService.cancelWfh (attendance.module.ts:412-419) vs approveWfh:375-382 | yes
112 | Medium | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Missing startDate/endDate in WFH request returns 500 Internal Server Error instead of a clean 400 | validation | AttendanceService.requestWfh (attendance.module.ts:300-301) | yes
113 | Medium | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Missing or wrong-type startDate/endDate returns HTTP 500 instead of a clean 400 | validation | POST /attendance/wfh | yes
114 | Medium | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | WFH reason field has no maximum length — 5000+ (observed 72000) chars accepted and stored | validation | POST /attendance/wfh | yes
115 | Medium | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | POST /attendance/wfh returns HTTP 500 when a date field is missing or wrong type | validation | POST /attendance/wfh (AttendanceService.requestWfh) | yes
116 | Medium | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Missing or wrong-typed body fields cause HTTP 500 instead of a clean 400 | validation | POST /attendance/wfh (AttendanceService.requestWfh, attendance.module.ts:298-300) | yes
117 | Medium | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Leave can be booked over an already-APPROVED WFH day (asymmetric double-booking) | ab-inconsistency | POST /attendance/wfh vs leave create
118 | Medium | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Cancelling an approved WFH request leaves the shared-calendar 'Working from home' event behind | data-integrity | apps/api/src/modules/attendance/attendance.module.ts:412 | yes
119 | Low | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | WFH reason has no maximum length — 6000+ character reason accepted and persisted | validation | AttendanceService.requestWfh (attendance.module.ts:299-320) | yes
120 | Low | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | WFH-vs-leave overlap check only considers APPROVED leave, not PENDING leave | ab-inconsistency | POST /attendance/wfh
121 | Low | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | WFH can be requested for weekend/holiday-only ranges (no working-day eligibility check) | domain | POST /attendance/wfh (requestWfh) | yes
122 | Low | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | WFH reason has no length cap — 20,000+ character reason accepted | validation | POST /attendance/wfh (requestWfh, attendance.module.ts:299,320) | yes
123 | Low | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Invalid calendar date is silently coerced instead of rejected | data-integrity | POST /attendance/wfh date parsing (parseDay) | yes
124 | Low | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No maximum length on WFH reason — arbitrarily large text accepted and stored | validation | POST /attendance/wfh reason field | yes
125 | Low | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | A/B inconsistency: malformed date returns 400 but missing/wrong-typed fields return 500 | ab-inconsistency | POST /attendance/wfh validation path | yes
126 | Low | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | approveWfh/rejectWfh lack an org-scope check (by-id lookup), unlike the org-scoped pending queue | rbac | POST /attendance/wfh/:id/approve¦reject
127 | Low | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | approve/reject WFH not scoped to reviewer's organization | rbac | approveWfh/rejectWfh (attendance.module.ts:352-353,393-394)
128 | Low | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No maximum length on WFH reason — 21,000-character reason accepted and stored | validation | apps/api/src/modules/attendance/attendance.module.ts:299 | yes
129 | Low | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | POST /attendance/wfh returns 500 (not 400) when startDate/endDate is missing or a non-string type | validation | apps/api/src/modules/attendance/attendance.module.ts:300 | yes
130 | Info | wfh | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Cancel endpoint leaks request existence: 404 for unknown id vs 403 for another user's id | rbac | POST /attendance/wfh/:id/cancel | yes
131 | High | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Project timesheet view (?projectId=) leaks all members' entries with no membership/ownership guard | rbac | GET /timesheets?projectId= | yes
132 | High | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Future-dated timesheets accepted — billable hours can be logged for dates that have not occurred | data-integrity | POST /timesheets (dto.ts date @IsDateString only) | yes
133 | Medium | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Employee cannot delete their own timesheet (Employee role lacks timesheet.delete) | ab-inconsistency | DELETE /timesheets/:id | yes
134 | Medium | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Self-scope on ?userId is bypassable via ?projectId — project view exposes every user's entries + billable flags with no ownership/relationship check | ab-inconsistency | GET /timesheets (listForProject vs listForUser) | yes
135 | Medium | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | listForProject applies no project-membership gate - full timesheet ledger readable by any timesheet.view holder | rbac | GET /timesheets?projectId (timesheets.service.ts:51-73)
136 | Medium | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Project timesheet view (?projectId) has no membership check — any user reads all colleagues' hours/billable/notes on projects they're not on | rbac | GET /timesheets?projectId — TimesheetsService.listForProject (timesheets.service.ts:51-73) | yes
137 | Medium | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Project time view exposes every user's entries (hours, billable flag, notes) with no project-membership check, while ?userId=other is 403 | ab-inconsistency | GET /timesheets?projectId — listForProject vs listForUser | yes
138 | Medium | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Future-dated timesheets accepted — no upper bound on date, inflates Task.actualHours and time reports | validation | POST /timesheets (CreateTimesheetDto.date) | yes
139 | Medium | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Duplicate identical timesheet entries allowed with no dedup or warning (double-billing risk) | domain | POST /timesheets (create) | yes
140 | Medium | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Time can be logged for arbitrary future dates (no upper date bound) | validation | POST /timesheets (create) / dto.ts date field | yes
141 | Medium | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Any user can log time against tasks they are not assigned to / projects they are not a member of | rbac | POST /timesheets (create) — no assignment/membership check | yes
142 | Medium | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Future-dated timesheets accepted with no upper date bound | validation | POST /timesheets (date) | yes
143 | Medium | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Employee can log time against tasks they are not assigned to, in projects they don't belong to | domain | POST /timesheets (taskId) | yes
144 | Medium | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No date bounds on timesheet create — far-future (year 3000) and far-past (1990) entries accepted | validation | POST /timesheets — CreateTimesheetDto.date (dto.ts:14, only @IsDateString) | yes
145 | Medium | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No per-day hours cap and no duplicate detection — 40h logged on one task on one day, identical entries created twice | domain | POST /timesheets — TimesheetsService.create (timesheets.service.ts:87-119) | yes
146 | Low | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Asymmetric CRUD grant for HR: can create and edit own timesheets but cannot delete even own entries | ab-inconsistency | DELETE /timesheets/:id (timesheet.delete permission) | yes
147 | Low | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Manager persona can create and edit own timesheets but cannot delete them (no timesheet.delete grant) | ab-inconsistency | DELETE /timesheets/:id — permission scope | yes
148 | Low | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | RBAC CRUD inconsistency — Senior Research Associate can create and edit their own timesheet hours but cannot delete even their own entry | ab-inconsistency | DELETE /timesheets/:id — timesheet.delete permission grant | yes
149 | Low | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Issue-raised (non-billable) entries can be flipped to billable via PATCH | data-integrity | PATCH /timesheets/:id (timesheets.service.ts:121-137)
150 | Low | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No duplicate-entry detection - identical task+date+hours logged repeatedly | data-integrity | POST /timesheets | yes
151 | Low | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Far-past dates accepted with no lower bound (e.g. year 2001) | validation | POST /timesheets (date) | yes
152 | Low | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | notes field has no length cap | validation | POST /timesheets (notes) | yes
153 | Low | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No duplicate detection and no per-day aggregate hour cap | domain | POST /timesheets business rules | yes
154 | Low | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No duplicate/overlap guard or per-day total cap — same task+date logged repeatedly and unlimited tasks each up to 24h/day | domain | POST /timesheets business rules
155 | Low | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | notes has no maximum length - 100k-char note accepted | validation | POST /timesheets notes field (dto.ts:26-28) | yes
156 | Low | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | notes field has no length limit — 20,000-char note accepted | validation | POST /timesheets — CreateTimesheetDto.notes (dto.ts:26-28, @IsString @IsOptional only) | yes
157 | Low | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | notes field is unbounded — 5000-character note accepted | validation | POST/PATCH /timesheets (dto.ts notes — @IsString @IsOptional, no @MaxLength) | yes
158 | Low | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No max length on notes — 6000-character note stored without error | validation | POST/PATCH /timesheets (notes) | yes
159 | Info | timesheets | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No approval or period-lock workflow exists for timesheets — nothing for an approver to review, lock, or sign off | domain | timesheets module (service/controller) — no approve/submit/lock endpoints
160 | Medium | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | receiptDocumentId stored without existence or ownership validation (IDOR into document blobs) | validation | POST /expenses | yes
161 | Medium | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No duplicate-submission guard — identical expenses accepted repeatedly (double-claim vector) | domain | POST /expenses | yes
162 | Medium | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | receiptDocumentId accepted with no existence or ownership validation | data-integrity | POST /expenses (submit, expenses.module.ts:54) | yes
163 | Medium | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | receiptDocumentId accepts arbitrary / another user's document with no existence or ownership check | data-integrity | POST /expenses receiptDocumentId | yes
164 | Medium | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | markReimbursed() lacks the self-review guard that approve/reject enforce (SoD gap + A/B inconsistency) | ab-inconsistency | POST /expenses/:id/reimburse
165 | Medium | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Reimburse step lacks the self-review guard that approve/reject enforce — an approver can mark their OWN expense as reimbursed | ab-inconsistency | POST /expenses/:id/reimburse (markReimbursed, expenses.module.ts:105) | yes
166 | Medium | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Segregation of duties: HR (people-ops) can both approve AND reimburse expenses single-handed | rbac | expenses approval routing | yes
167 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Invalid status query on /expenses/org returns 200 [] instead of validating the enum | validation | GET /expenses/org (expenses.module.ts:78) | yes
168 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | GET /expenses/org?status=<invalid> silently returns [] instead of validating the status filter | validation | GET /expenses/org (forOrg, expenses.module.ts:77-80) | yes
169 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | amount has no upper bound | data-integrity | POST /expenses | yes
170 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Sub-paisa amounts accepted (no minimum / rounding) | data-integrity | POST /expenses | yes
171 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | currency field not validated against an allow-list and not length-capped | validation | POST /expenses | yes
172 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | description length not capped (12k chars accepted) | validation | POST /expenses | yes
173 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No amount upper bound or currency-precision limit (sub-paise fractions accepted) | validation | POST /expenses (expenses.module.ts:42) | yes
174 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No maximum length on description (and reviewNote) — 20k+ chars accepted | validation | POST /expenses (expenses.module.ts:43,54) | yes
175 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Unknown category silently coerced to OTHER instead of rejected | domain | POST /expenses (expenses.module.ts:45) | yes
176 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Currency field not validated — arbitrary long non-ISO string accepted | validation | POST /expenses (expenses.module.ts:53) | yes
177 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No upper bound on expense amount (999,999,999,999 accepted) | validation | POST /expenses amount | yes
178 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | amount accepts sub-paisa precision (0.001) — no currency rounding | data-integrity | POST /expenses amount | yes
179 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | currency field accepts arbitrary non-ISO strings | validation | POST /expenses currency | yes
180 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | currency field accepts arbitrary non-ISO strings (no allow-list) | validation | POST /expenses currency | yes
181 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | No maximum length on expense description (20,000-char body accepted) | validation | POST /expenses description | yes
182 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | description has no maximum length (20,000-char body accepted) | validation | POST /expenses description | yes
183 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | spentOn accepts absurd past dates (year 1900) while future is blocked | validation | POST /expenses spentOn | yes
184 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | decide()/markReimbursed() fetch by id only, no organization scoping | rbac | POST /expenses/:id/approve¦reject¦reimburse
185 | Low | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Approve/reject/reimburse/cancel look up expense by id only, not scoped to actor's organization | rbac | decide/markReimbursed/cancel (expenses.module.ts:84,106,121)
186 | Info | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | GET /expenses/org with an invalid status returns 200 [] instead of 400 | ab-inconsistency | GET /expenses/org status filter | yes
187 | Info | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | spentOn has no lower bound | domain | POST /expenses | yes
188 | Info | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | spentOn accepts arbitrarily old dates (e.g. 1900-01-01) | domain | POST /expenses (expenses.module.ts:48) | yes
189 | Info | expenses | Batch 1 — Time & Attendance complete (30/30 agents · attendance · leaves · comp-off · WFH · timesheets · expenses) | Sub-paisa fractional amounts accepted (0.0001) | domain | POST /expenses amount | yes
190 | High | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | GET /projects list returns ALL org projects, not just the caller's memberships | rbac | GET /projects (projects.controller.ts:19-22; service list() projects.service.ts:156-188) | yes
191 | High | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | IDOR read: GET /:id returns any project's full detail to a non-member | rbac | GET /projects/:id (projects.controller.ts line 39; service get()/getRaw) | yes
192 | High | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | GET /projects/:id has no membership gate — any authenticated user can read any project (no permission decorator, no member/org scoping) | rbac | GET /projects/:id (projects.controller.ts:39-42, projects.service.ts:257-260 -> getRaw) | yes
193 | High | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | IDOR: any authenticated user can read any project by id (GET /:id has no membership or permission gate) | rbac | GET /projects/:id (projects.controller.ts:39-42; service get()->getRaw() projects.service.ts:238-260) | yes
194 | High | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | IDOR write: PATCH /:id (and lifecycle/member ops) mutate projects the actor is not a member/manager of | rbac | PATCH /projects/:id + /complete¦/close¦/reopen + /members (service update/complete/close/reopen/removeMember) | yes
195 | High | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | addMember is completely broken — no user can ever be added to a project | logic | POST /projects/:id/members (projects.service.ts addMember, line ~459) | yes
196 | High | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | addMember is completely broken — every add fails with 'User is not in this project's organization' | logic | POST /projects/:id/members (projects.service.ts:455-461) | yes
197 | High | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | GET /projects/:id has no permission guard and no membership check — any authenticated user reads any project (IDOR read) | rbac | projects.controller.ts:39 get() / projects.service.ts get()->getRaw() | yes
198 | High | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | GET /projects returns every project in the org to a non-member (membership gating absent) | rbac | projects.service.ts list() / GET /projects | yes
199 | High | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | PATCH /projects/:id lets a non-member edit any project (only global project.update checked, no member/manager gate) | rbac | projects.service.ts:262 update() | yes
200 | High | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | POST /projects/:id/members can never add a member — org-equality check compares against a non-existent Project.organizationId | data-integrity | projects.service.ts:459 addMember() | yes
201 | High | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | hr@ people-ops account is role-stacked with Manager + Senior Consultant, granting full delivery write surface | rbac | seeded user_role assignments for hr@squarkip.com | yes
202 | Medium | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | GET /projects returns all projects for a client-supplied organizationId with no auth scoping (membership bypass + cross-tenant read surface) | rbac | GET /projects?organizationId= (projects.controller.ts:19-22, projects.service.ts:156-188) | yes
203 | Medium | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | PATCH projectPhase bypasses the lifecycle state machine and skips timestamps/notifications | logic | PATCH /projects/:id update() (projects.service.ts:277-293; UpdateProjectDto.projectPhase dto.ts:76-78)
204 | Medium | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | PATCH /projects/:id (and lifecycle endpoints) enforce only the global project.update permission, not project membership | rbac | PATCH /projects/:id, POST /:id/complete¦close¦reopen (projects.service.ts:262, controller uses @RequirePermission only) | yes
205 | Medium | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | create() does not validate dueDate >= startDate (inconsistent with update()) | ab-inconsistency | POST /projects (projects.service.ts create, lines 86-89) | yes
206 | Medium | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Inverted date range (dueDate before startDate) accepted on CREATE but rejected on UPDATE (A/B inconsistency) | ab-inconsistency | POST /projects create() (projects.service.ts:85-112) vs PATCH update() (projects.service.ts:266-270) | yes
207 | Medium | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Project create does not validate dueDate >= startDate (update does) — inverted date range persists | ab-inconsistency | POST /projects vs PATCH /projects/:id (projects.service.ts:86-89 vs 262-270) | yes
208 | Medium | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | GET /projects/:id has no membership or permission check — any employee can read a project they are not a member of | rbac | projects.controller.ts GET :id / projects.service.ts get()/getRaw() | yes
209 | Medium | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | create() accepts an inverted date range (startDate after dueDate) that update() rejects | ab-inconsistency | projects.service.ts create() vs update() | yes
210 | Low | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Project priority accepts arbitrary free-string (no enum validation) | validation | CreateProjectDto.priority / UpdateProjectDto.priority (dto.ts:38-40, 72-74) | yes
211 | Low | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Project create accepts an arbitrary priority value outside the enum | validation | POST /projects (CreateProjectDto priority) | yes
212 | Low | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Whitespace-only project title accepted | validation | POST /projects (CreateProjectDto title validation) | yes
213 | Low | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | priority accepts arbitrary free-text (no enum validation) on project create | validation | dto.ts CreateProjectDto.priority | yes
214 | Low | projects | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | GET /projects list is org-scoped, not membership-scoped — employee sees every project in the org | rbac | projects.service.ts list() | yes
215 | High | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | IDOR read: any authenticated user can read any task / any project's task list (no permission or membership check) | rbac | GET /tasks/:id and GET /tasks?projectId= (tasks.controller.ts:26-29,15-24 — no @RequirePermission) | yes
216 | High | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | IDOR write: task.update lets a non-member edit tasks in projects they are not on (and corrupts that project's progress rollup) | rbac | PATCH /tasks/:id (tasks.controller.ts:31-34; tasks.service.ts update() — no membership/ownership scope) | yes
217 | High | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | IDOR: employee can edit, re-title, set completion and CLOSE any task in a project they are not a member of | rbac | PATCH /tasks/:id, PUT /tasks/:id/status (tasks.service.ts update/setStatus, tasks.controller.ts:31-39) | yes
218 | High | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | IDOR create + membership bypass: task.create writes into any project and assigns non-members | rbac | POST /tasks (tasks.controller.ts:10-13; tasks.service.ts create() — validates only that taskListId belongs to projectId, never that the actor or assignees are members) | yes
219 | High | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Subtask endpoints ignore the parent :id — any subtask can be closed/reopened/deleted by id alone (IDOR) | rbac | POST /tasks/:id/subtasks/:subtaskId/close¦reopen and DELETE (tasks.controller.ts:63-76; service closeSubtask/reopenSubtask/softDeleteSubtask look up by subtaskId only) | yes
220 | High | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | IDOR status transition: non-member can close/reopen any task, force 100% and cascade-close its subtasks | rbac | PUT /tasks/:id/status (tasks.controller.ts:36-39; tasks.service.ts setStatus()) | yes
221 | Medium | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Read endpoints have no permission guard: any authenticated user can read any task and list any user's/project's tasks | rbac | GET /tasks, GET /tasks/:id, GET /tasks/:id/subtasks | yes
222 | Medium | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Task read endpoints have no authorization: any user can read any task and enumerate any user's full workload | rbac | GET /tasks/:id, GET /tasks?userId=, GET /tasks?projectId= (tasks.controller.ts:15-29, no @RequirePermission) | yes
223 | Medium | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Task can be assigned to a user who is not a member of the project | domain | POST /tasks (assigneeIds), PUT /tasks/:id/assignees | yes
224 | Medium | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Membership bypass: employee can create tasks inside any project they are not a member of | rbac | POST /tasks (tasks.service.ts create:26-108) | yes
225 | Medium | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Manager can create/update/delete tasks in projects they are not a member of | rbac | POST /tasks, PATCH /tasks/:id, DELETE /tasks/:id | yes
226 | Medium | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | hr@squarkip.com is role-stacked (HR + Manager + Senior Consultant), defeating the people-ops delivery boundary | rbac | auth/roles — hr@ account | yes
227 | Medium | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Ungated GET endpoints let pure HR (no delivery surface) read any task and any project's task list | rbac | tasks.controller.ts GET / , GET /:id , GET /:id/subtasks | yes
228 | Medium | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Subtask close/reopen/delete ignore the parent task id in the URL path (IDOR / integrity) | logic | tasks.controller.ts:63-76 / tasks.service.ts:363-380 (closeSubtask/reopenSubtask/softDeleteSubtask) | yes
229 | Medium | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | No project-membership check on task create or assignee-set — cross-matter access/assignment | rbac | tasks.service.ts create() / setAssignees() | yes
230 | Medium | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | No project-membership gate: tasks can be created in a project you don't belong to and assigned to non-members | rbac | tasks.service.ts:26-108 (create) / :256-284 (setAssignees) | yes
231 | Low | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | No startDate <= dueDate ordering validation — task can start after it is due | validation | CreateTaskDto / UpdateTaskDto (dto.ts:45-54,90-99 — dates validated individually, never relative) | yes
232 | Low | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | priority accepts arbitrary strings (no enum validation) — stores raw markup verbatim | validation | CreateTaskDto.priority / CreateSubtaskDto.priority (dto.ts:36-37,131-132 — @IsString only) | yes
233 | Low | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | No cross-field validation: dueDate can be earlier than startDate | validation | POST /tasks, PATCH /tasks/:id | yes
234 | Low | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Task priority accepts arbitrary free-text (no enum validation) | validation | POST /tasks, dto.ts CreateTaskDto.priority (@IsString only, line 36-37) | yes
235 | Low | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Subtask close/reopen/delete ignore the parent task id in the path (broken object reference / IDOR) | logic | POST /tasks/:id/subtasks/:subtaskId/close¦reopen, DELETE /tasks/:id/subtasks/:subtaskId | yes
236 | Low | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | priority accepts arbitrary free-text (no enum validation) | validation | dto.ts:36-37 (CreateTaskDto.priority @IsString only) | yes
237 | Low | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Task reads (GET / and GET /:id) have no permission guard and expose any user's task list | rbac | tasks.controller.ts:15-29 (list/get have no @RequirePermission); DeadlineVisibilityService injected at tasks.service.ts:18 but never used in reads
238 | Low | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Task create response reports projectTasks:[] though the project link is created in the same transaction | logic | tasks.service.ts create() lines 59-92 | yes
239 | Low | tasks | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | dueDate before startDate is accepted (no cross-field date sanity check) | validation | tasks.service.ts:56,64-56 / dto.ts:45-54 (startDate/dueDate) | yes
240 | Medium | capacity | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Team board row totals don't reconcile — committed + free wildly exceeds capacity, masking a catastrophically overloaded person as ~83% busy | data-integrity | GET /capacity/team (capacity.module.ts:275-321) | yes
241 | Medium | capacity | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | hr@ people-ops account is role-stacked (Manager + Senior Consultant), giving it capacity.view plus full project/task/issue write access — breaking the HR delivery-surface boundary | rbac | seed/role assignment (user_role for hr@squarkip.com) | yes
242 | Low | capacity | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | coverage-risks surfaces tasks that were already overdue BEFORE the leave started as 'due while they're out' | domain | CapacityService.atRiskTasks / coverageRisks task filter (capacity.module.ts) | yes
243 | Low | capacity | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | coverage-risks labels an in-progress leave booked 22 days in advance as an emergency short-notice coverage risk | domain | CapacityService.isShortNotice / coverageRisks (capacity.module.ts ~L465-520)
244 | Low | capacity | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | coverage-risks lists tasks already overdue BEFORE the leave starts as 'risks caused by' that leave | logic | GET /capacity/coverage-risks (capacity.module.ts:531) | yes
245 | Low | capacity | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Field name 'utilization' has two incompatible scales in the same API — 0–1 fraction at day level, 0–100 percentage at row level, and the day-level value is unclamped (can be 8.05 = 805%) | ab-inconsistency | GET /capacity/team (capacity.module.ts:282 vs 321) | yes
246 | Low | capacity | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | GET /capacity/history ignores its documented 30-day default and falls back to 14 days | logic | apps/api/src/modules/capacity/capacity.module.ts:611-613 | yes
247 | Low | capacity | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | GET /capacity/history with no days param returns a 14-day window, contradicting the service's own 30-day default and the 'Past 30 days' range intent | ab-inconsistency | apps/api/src/modules/capacity/capacity.module.ts:611-613 (controller) vs :342 (teamHistory default=30) | yes
248 | Info | capacity | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | team/history/coverage/project silently ignore unsupported from/to query params (only days is honored), returning the default window with no 400 | validation | CapacityController @Query('days') (capacity.module.ts ~L560-640) | yes
249 | Info | capacity | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | team/history/coverage endpoints silently ignore from/to query params (only `days` is honored) — no 400 on bad/reversed dates | validation | GET /capacity/* controllers (capacity.module.ts:603,611,622) | yes
250 | Info | capacity | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Employee/HR RBAC on capacity module is correctly enforced (clean 403, guard runs before param parsing) — no bug | rbac | apps/api/src/modules/capacity/capacity.module.ts (all @RequirePermission('capacity.view')) | yes
251 | Info | capacity | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | No client-deadline leakage and no cross-tenant/out-of-org leakage in capacity responses | domain | apps/api/src/modules/capacity/capacity.module.ts:104-119, 149-183, 515-563
252 | High | performance | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | hr@ seed account is role-stacked and holds full delivery-write + org-analytics permissions, defeating the 'HR = people-ops, no delivery surfaces' boundary | rbac | RBAC / seed role config (cross-cuts performance org endpoints + projects/tasks/issues) | yes
253 | Medium | performance | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Org performance/rebuild endpoints trust a client-supplied organizationId (cross-tenant read; unscoped when omitted) | rbac | GET /performance/org, /org-heatmap, /org/breakdowns, /org/trend, POST /performance/snapshots/rebuild | yes
254 | Medium | performance | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Intern (via Manager role) is exposed to full org-wide performance data and can trigger snapshot rebuilds | rbac | performance /org, /users/:id, /snapshots/rebuild | yes
255 | Low | performance | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Heatmap accepts negative/zero days and silently returns empty instead of clamping (inconsistent with other endpoints) | validation | GET /performance/heatmap/:userId | yes
256 | Low | performance | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | periodDays query param silently ignored; only 'days' is honored | ab-inconsistency | GET /performance/me and related derived-metric endpoints | yes
257 | Low | performance | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | getUserPerformance user lookup has no deletedAt/organization filter | data-integrity | GET /performance/users/:userId (+ /breakdowns, /heatmap)
258 | Low | performance | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Snapshot rebuild (a heavy write/recompute) is gated by a read-only 'view' permission | rbac | POST /performance/snapshots/rebuild
259 | Low | performance | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | getUserPerformance / assertCanView is not org-scoped (potential cross-org read for a privileged actor) | rbac | apps/api/src/modules/performance/performance.service.ts:61-73
260 | Low | performance | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | assertCanView / getUserPerformance apply no same-organization filter on the target userId | rbac | apps/api/src/modules/performance/performance.service.ts:61-73
261 | Low | performance | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Heatmap days param lacks lower-bound clamping; negative/zero yield empty 200 while non-numeric yields opaque 400 | validation | performance.module.ts heatmap route | yes
262 | Low | performance | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Org performance endpoints trust client-supplied organizationId and return all-orgs data when it is omitted | data-integrity | performance.module.ts org/org-heatmap/org/breakdowns/org/trend/snapshots/rebuild | yes
263 | Low | performance | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | heatmap and breakdowns endpoints return 200 with fabricated/empty data for a non-existent userId instead of 404 (inconsistent with /performance/users/:userId) | ab-inconsistency | performance.service.ts getUserHeatmap / getUserBreakdowns vs getUserPerformance | yes
264 | Info | performance | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | days query param clamps invalid values silently instead of 400 (defensive, minor UX) | validation | apps/api/src/modules/performance/performance.service.ts (windowRange/days handling) | yes
265 | Info | performance | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Pure-Employee performance boundaries are correctly enforced (positive control) | rbac | performance endpoints as a non-privileged Employee | yes
266 | High | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | IDOR: any user can read issues (and their descriptions) of projects they are not a member of | rbac | GET /issues, GET /issues/:id (issues.service.ts list/get, issues.controller.ts) | yes
267 | High | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | GET /issues and GET /issues/:id have no permission guard and no project scoping — any authenticated user can read every project's issues | rbac | GET /issues, GET /issues/:id — issues.controller.ts:10-18; issues.service.ts:34-48 | yes
268 | High | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Non-creator can edit (and, with the delete grant, delete) any other user's issue | rbac | PATCH /issues/:id — IssuesService.update (issues.service.ts:74-86); softDelete (89-97) | yes
269 | High | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Any user can raise an issue (and log non-billable time) against a project they are not a member of / cannot see | rbac | POST /issues — IssuesService.create (issues.service.ts:51-72) | yes
270 | High | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Issue read endpoints (GET /issues, GET /issues/:id) have NO permission guard — any authenticated user reads all delivery issues in any project | rbac | issues.controller.ts GET / and GET /:id | yes
271 | High | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | GET /issues and GET /issues/:id have no permission guard or project-membership check — any authenticated user reads every project's issues | rbac | issues.controller.ts GET / and GET /:id (list/get in issues.service.ts) | yes
272 | High | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | GET /issues and GET /issues/:id have no permission guard and no membership filter — any authenticated user can read every project's issues + reporter PII | rbac | issues.controller.ts list()/get() | yes
273 | High | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | POST /issues does not verify project membership — user can raise an issue and self-log a non-billable timesheet in a project they cannot access | rbac | issues.service.ts create() (no membership check on dto.projectId) | yes
274 | Medium | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | No ownership/membership check on update or delete — any holder of issue.update/issue.delete can edit or delete anyone's issue in any project | rbac | PATCH /issues/:id, DELETE /issues/:id (issues.service.ts update/softDelete)
275 | Medium | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | IDOR write: user can raise an issue in a project they are not a member of, injecting a non-billable timesheet against themselves | data-integrity | POST /issues (issues.service.ts create) | yes
276 | Medium | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Issue accepts an arbitrary future date, writing a future-dated non-billable timesheet | data-integrity | POST /issues date handling — issues.service.ts:54,61-63 | yes
277 | Medium | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | 'HR Admin' (hr@) account is role-stacked with Manager + Senior Consultant, granting full delivery write on issues/projects/tasks — contradicts HR-has-no-delivery-surface design | ab-inconsistency | RBAC seed / user_role for hr@squarkip.com | yes
278 | Medium | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | PATCH accepts an empty title, though create rejects it (validation asymmetry) | validation | UpdateIssueDto.title — dto.ts (no @MinLength) vs CreateIssueDto.title (@MinLength(1)) | yes
279 | Medium | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | PATCH /issues/:id accepts empty title — issue title can be blanked (create forbids it) | data-integrity | dto.ts UpdateIssueDto.title | yes
280 | Medium | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | GET issue endpoints enforce no permission — issue.view is never checked | rbac | issues.controller.ts GET list/get
281 | Medium | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Issue (and its non-billable timesheet) can be dated arbitrarily in the future | validation | issues.service.ts create() date handling / dto.ts date | yes
282 | Medium | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | No project-membership check on issue create/update/delete — holder can raise/edit issues in projects they don't belong to | logic | issues.service.ts create()/update() (lines 51-86) | yes
283 | Low | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Future-dated non-billable time entries accepted (no upper bound on issue date) | validation | POST /issues (dto.ts date, issues.service.ts create) | yes
284 | Low | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Invalid projectId returns a raw DB constraint message | ux | POST /issues — FK on issue.projectId | yes
285 | Low | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | UpdateIssueDto.title lacks MinLength — an update can blank an issue's title | validation | dto.ts UpdateIssueDto
286 | Low | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | No project-membership gate on issue creation (superadmin and any issue.create holder can raise issues in projects they aren't a member of) | rbac | issues.service.ts create() | yes
287 | Low | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Repurposed issue API leaks stale bug-tracker fields (severity/status/assigneeId/dueDate) with misleading defaults | data-integrity | issues.service.ts shape()/include (spreads all issue columns) | yes
288 | Low | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Any issue.update holder can edit issues raised by other users (no creator/ownership check) | rbac | issues.service.ts update() lines 74-86 | yes
289 | Info | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Validation and non-billable timesheet linkage behave correctly (positive verification) | validation | dto.ts + issues.service.ts create/softDelete | yes
290 | Info | issues | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Legacy bug-tracker fields (severity/status/assigneeId/dueDate) still returned by the repurposed issues API | domain | issues.service.ts include / issue schema
291 | Medium | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Event `type` field accepts arbitrary unvalidated strings (no enum guard) | validation | POST /calendar-events — create | yes
292 | Medium | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Event with endDate before startDate (negative duration) accepted | validation | POST /calendar-events — create | yes
293 | Medium | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | hr@ (people-ops) account is role-stacked with Manager + Senior Consultant, granting delivery-adjacent calendar.create/update it should not have | ab-inconsistency | RBAC — account role assignment vs HR design
294 | Medium | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Event with endDate before startDate is accepted (negative-duration event) | validation | apps/api/src/modules/events/dto.ts CreateEventDto/UpdateEventDto | yes
295 | Medium | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | joinUrl accepts arbitrary non-URL strings including javascript: scheme | validation | apps/api/src/modules/events/dto.ts joinUrl (@IsString only, no @IsUrl)
296 | Medium | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Events accept endDate earlier than startDate (negative-duration events) on both create and update | validation | apps/api/src/modules/events/events.service.ts create()/update() + dto CreateEventDto/UpdateEventDto | yes
297 | Medium | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Recurring event silently capped at 60 occurrences regardless of recurrenceUntil | logic | apps/api/src/modules/events/events.service.ts:103 generateOccurrences | yes
298 | Medium | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | List/get trust client-supplied organizationId while free-busy/export derive it from the session (A/B inconsistency + tenant-isolation risk) | ab-inconsistency | events.controller.ts list() vs freeBusy()/exportIcs()
299 | Medium | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | GET /calendar-events/:id has no organization scoping — cross-tenant event read (IDOR) | rbac | events.service.ts get()
300 | Low | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Any org member can read full details (joinUrl, description, notes) of events they are not invited to via GET /calendar-events/:id | rbac | GET /calendar-events/:id (events.service.ts findOne) | yes
301 | Low | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Cross-org create leaks DB internals ('foreign key constraint') instead of clean 403 | other | POST /calendar-events — organizationId scoping | yes
302 | Low | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Recurrence silently capped (~61 occurrences) — recurrenceUntil ignored/misleading for long series | data-integrity | POST /calendar-events — recurrence generation | yes
303 | Low | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | RSVP/notes to a nonexistent event returns 403 'not invited' instead of 404 | ux | POST /calendar-events/:id/respond | yes
304 | Low | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Event 'type' is an unvalidated free-form string (accepts HTML/script) | validation | apps/api/src/modules/events/dto.ts type (@IsOptional @IsString, no @IsIn) | yes
305 | Low | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | list / get / create trust the client-supplied organizationId with no session-org enforcement (latent cross-org scoping gap) | rbac | apps/api/src/modules/events/events.controller.ts list(); events.service.ts get()/list()/create()
306 | Low | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | recurrenceUntil earlier than startDate is silently accepted | validation | apps/api/src/modules/events/events.service.ts generateOccurrences | yes
307 | Low | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | free-busy leaks meeting titles (incl. confidential client-matter names) for arbitrary users | domain | events.service.ts freeBusy() / controller freeBusy | yes
308 | Info | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | Reversed date window (from > to) returns 200 with empty array instead of a 400 validation error | validation | GET /calendar-events?from=&to= | yes
309 | Info | calendar | Batch 2 — Delivery complete (30/30 agents · projects · tasks · capacity · performance · issues · calendar) | RSVP to a non-existent event returns 403 'not invited' instead of 404 | logic | events.service.ts respond() | yes
310 | High | calendar | Home dashboard complete (5/5 personas) | analytics/projects is ungated: confidential client-matter descriptions leak firm-wide to any employee | rbac | GET /analytics/projects (analytics.controller.ts:18-20) | yes
311 | High | calendar | Home dashboard complete (5/5 personas) | analytics/projects is ungated: full client-matter project list leaks to any employee (member of zero projects) | rbac | GET /analytics/projects (apps/api/src/modules/analytics/analytics.controller.ts:18-21) | yes
312 | High | calendar | Home dashboard complete (5/5 personas) | analytics endpoints ignore org scoping: omitting organizationId disables the org filter and returns ALL organizations' data | data-integrity | apps/api/src/modules/analytics/analytics.service.ts:8-114 (getDashboard/getProjectStats) | yes
313 | High | calendar | Home dashboard complete (5/5 personas) | IDOR: /tasks?userId= and /tasks/:id return any colleague's tasks to a regular Employee | rbac | tasks endpoint (backs 'my tasks' home widget) | yes
314 | High | calendar | Home dashboard complete (5/5 personas) | GET /users is not permission-gated: full staff roster with phone numbers leaks to any authenticated user (no user.view) | rbac | users / home people & admin widgets | yes
315 | Medium | calendar | Home dashboard complete (5/5 personas) | analytics/dashboard is ungated: firm-wide aggregate stats returned to any authenticated user | rbac | GET /analytics/dashboard (analytics.controller.ts:13-16); home widget apps/web/components/home/sections.tsx:64 gated only by client-side can('project.view') | yes
316 | Medium | calendar | Home dashboard complete (5/5 personas) | analytics/projects exposes raw clientDueDate that the /projects module deliberately redacts (A/B redaction bypass) | ab-inconsistency | GET /analytics/projects vs GET /projects | yes
317 | Medium | calendar | Home dashboard complete (5/5 personas) | User directory (all employees' mobile numbers + role assignments) is fully open regardless of user.view | rbac | GET /users and GET /users/:id (users.module.ts:328-339) | yes
318 | Medium | calendar | Home dashboard complete (5/5 personas) | 'My Projects' home widget shows ALL org projects, not the user's; backing GET /projects is not membership-scoped | data-integrity | MyProjectsCard sections.tsx:201-214 -> api.projects.list(org.id) -> GET /projects | yes
319 | Medium | calendar | Home dashboard complete (5/5 personas) | Org-wide firm aggregates leak to a permission-less Employee via ungated /analytics/dashboard and /analytics/projects | rbac | analytics dashboard/projects (home org-summary widgets) | yes
320 | Medium | calendar | Home dashboard complete (5/5 personas) | Client-supplied organizationId trusted with no actor-org check; omitting it drops the Prisma filter entirely | data-integrity | analytics.dashboard/projects, /users, /projects org scoping
321 | Medium | calendar | Home dashboard complete (5/5 personas) | Ungated analytics endpoints leak org-wide project confidentials (titles, client descriptions, hours, overdue counts) to a permission-less Employee | rbac | analytics/dashboard, analytics/projects (home KPI + project widgets) | yes
322 | Medium | calendar | Home dashboard complete (5/5 personas) | Firm-wide KPI aggregates leak to a permission-less employee via ungated /analytics/dashboard while every other org-wide widget correctly 403s | rbac | apps/api/src/modules/analytics/analytics.controller.ts:13-16 | yes
323 | Medium | calendar | Home dashboard complete (5/5 personas) | GET /analytics/projects returns full project list (titles, descriptions, priority, dates) with NO permission check, unlike project.view-gated GET /projects | rbac | apps/api/src/modules/analytics/analytics.controller.ts:18-21 (projects) vs projects controller (project.view)
324 | Low | calendar | Home dashboard complete (5/5 personas) | Employee directory exposes phone numbers and joining dates of all staff to any Employee | domain | /users (people/admin widget data) | yes
325 | Low | calendar | Home dashboard complete (5/5 personas) | analytics/dashboard leaks org-wide aggregates to permission-less employees | rbac | GET /analytics/dashboard (analytics.controller.ts:12-16) | yes
326 | Low | calendar | Home dashboard complete (5/5 personas) | Ungated analytics endpoints accept a client-supplied organizationId with no membership check | rbac | GET /analytics/dashboard, GET /analytics/projects
327 | Low | calendar | Home dashboard complete (5/5 personas) | analytics/timesheets silently returns empty for a reversed date range instead of validating | validation | GET /analytics/timesheets (analytics.controller.ts:23-31) | yes
328 | Low | calendar | Home dashboard complete (5/5 personas) | Analytics and users endpoints accept a client-supplied organizationId with no scoping to the actor's org (latent cross-tenant read) | data-integrity | analytics.service getDashboard / users.service list
329 | Low | calendar | Home dashboard complete (5/5 personas) | analytics endpoints trust client-supplied organizationId with no actor-to-org validation | rbac | analytics.service.ts:8-18 (getDashboard/getProjectStats use the query organizationId verbatim in the Prisma where)
330 | Low | calendar | Home dashboard complete (5/5 personas) | attendance/me/month returns 500 Internal Server Error on out-of-range year (unvalidated date params) | validation | attendance controller/service — GET /attendance/me/month | yes
331 | Low | calendar | Home dashboard complete (5/5 personas) | Home 'Project Requests' approval widget is permanently dead after the approval gate was removed | ux | home ProjectApprovalsCard / projects/pending-approvals | yes
332 | Low | calendar | Home dashboard complete (5/5 personas) | 'My projects' home widget endpoint (/projects) returns all org projects regardless of membership | rbac | projects list (home 'my projects' widget) | yes
333 | Info | calendar | Home dashboard complete (5/5 personas) | Positive: org/approval home endpoints are correctly server-gated for Employee | rbac | attendance/org, leave/org, performance/org, capacity, roles, analytics/timesheets | yes

## Security Audit
# | Severity | Verdict | Finding | Area | Source
1 | Critical | Confirmed | Internet-facing live deployment runs with NODE_ENV unset, so all production hardening is silently disabled and the API signs JWTs with a weak dev secret | infra / runtime-config | Deep audit (verified) 2026-07-09
2 | High | Confirmed | HR (the designated onboarding role) cannot assign the Employee role or any delivery role — new-user onboarding is broken | rbac / user access management | Deep audit (verified) 2026-07-09
3 | High | Confirmed | Generic /approvals/:id/actions endpoint is unguarded and trusts a client-supplied userId — any authenticated user can approve/reject any Approval and forge the actor | approvals | Deep audit (verified) 2026-07-09
4 | High | Confirmed | The 'Admin' role can self-promote to real Super Admin by renaming any role to 'Super Admin' (updateRole unguarded; by-name detection; no system-role protection) | rbac / roles | Deep audit (verified) 2026-07-09
5 | High | Confirmed | Role/group permission and membership setters (rbac.service) still lack the anti-escalation subset check that the user setters enforce (C1 residual) | rbac / roles & groups | Deep audit (verified) 2026-07-09
6 | High | Confirmed | Milestones and non-default Task Lists are entirely unreachable from the UI — no api.milestones client, no milestone/tasklist creation UI, hierarchy collapses to one hardcoded list | milestones / tasklists | Deep audit (verified) 2026-07-09
7 | High | Confirmed | Discuss channel messages load the OLDEST 50 (orderBy asc + take), so once a channel passes 50 messages new messages never appear | collab/channels | Deep audit (verified) 2026-07-09
8 | High | Confirmed | Timesheets module has zero authorization and trusts a client-supplied userId — any authenticated user can log/inflate/edit/delete anyone's billable hours | timesheets | Deep audit (verified) 2026-07-09
9 | High | Confirmed | Performance 'tasks completed' counts EVERY task.status_changed event, not just completions — snapshots, trend lines, org rollup and sparklines are all inflated and disagree with the KPI tile | events / performance | Deep audit (verified) 2026-07-09
10 | High | Confirmed | Org performance leaderboard is O(users) N+1: one dashboard load fires 14N+2 Prisma queries (~394 for 28 users) | performance | Deep audit (verified) 2026-07-09
11 | High | Confirmed | rebuildSnapshots serializes up to days×users UserMetricDaily upserts (365×28 ≈ 10k) with await inside a nested loop | performance | Deep audit (verified) 2026-07-09
12 | Medium | Confirmed | Project approval workflow is unreachable from the UI — created projects are stuck PENDING/PLANNING forever, rejection is an unrecoverable dead-end, and tasks can be added to unapproved projects | projects | Deep audit (verified) 2026-07-09
13 | Medium | Confirmed | New Project button and modal are shown to every user but hard-fail with 403 for Employees/Consultants, who lack project.create | projects | Deep audit (verified) 2026-07-09
14 | Medium | Confirmed | Changing an Open task's status silently wipes its 100% progress back to 0% | tasks | Deep audit (verified) 2026-07-09
15 | Medium | Confirmed | Punching in on an approved-leave / holiday / admin-marked-absent day silently overwrites the day to PRESENT while the leave balance stays deducted | attendance | Deep audit (verified) 2026-07-09
16 | Medium | Confirmed | Clock-out across the UTC midnight boundary is impossible — an overnight shift leaves the prior day permanently open and opens a phantom new day | attendance | Deep audit (verified) 2026-07-09
17 | Medium | Confirmed | Overlapping/duplicate leave requests double-deplete the balance, and neither create nor approve enforces the remaining quota | attendance | Deep audit (verified) 2026-07-09
18 | Medium | Confirmed | Leave can be requested for entirely past dates; approval retroactively debits the balance and back-writes ON_LEAVE that silently no-ops on days already present | attendance | Deep audit (verified) 2026-07-09
19 | Medium | Confirmed | Regularized / manual attendance times are stored in an ambiguous timezone (offset-less strings parsed server-local) while punch stores the true instant | attendance | Deep audit (verified) 2026-07-09
20 | Medium | Confirmed | Approved leave never appears on the Calendar — leave writes only ON_LEAVE attendance rows, which the calendar doesn't read | attendance/leave | Deep audit (verified) 2026-07-09
21 | Medium | Confirmed | Activity-feed audit.view gate is bypassable: any employee can read confidential permission/role change activity for any targeted user via entityId | audit | Deep audit (verified) 2026-07-09
22 | Medium | Confirmed | mustResetPassword is enforced only in the browser; the API grants a fully-privileged session and never blocks a temp-password user | auth | Deep audit (verified) 2026-07-09
23 | Medium | Confirmed | No password-recovery / invite-link flow exists: the AuthToken model is dead code and the signup page promises a non-existent 'invite link to set your password' | auth | Deep audit (verified) 2026-07-09
24 | Medium | Confirmed | Delete-own-comment button in the project Discussion tab 403s silently for every non-admin — comment.delete is Admin/Super-Admin-only | collab/comments | Deep audit (verified) 2026-07-09
25 | Medium | Confirmed | Issue Delete (all roles) and status-change (Employees) buttons 403 and fail SILENTLY — issue.delete is Admin/Super-Admin-only and errors are swallowed by empty catch | collab/issues | Deep audit (verified) 2026-07-09
26 | Medium | Confirmed | Assigning an issue to a user never notifies them (no parity with task assignment, which does notify) | collab/issues | Deep audit (verified) 2026-07-09
27 | Medium | Confirmed | Posting a comment creates NO notification and @mentions are entirely unimplemented, despite Settings advertising 'Comments & mentions' | collab/notifications | Deep audit (verified) 2026-07-09
28 | Medium | Confirmed | Task table has no index on updatedAt / dueDate / currentWorkflowStatusId — every performance & analytics aggregation scans tasks | db | Deep audit (verified) 2026-07-09
29 | Medium | Confirmed | Task dependency subsystem is schema-only: dependencies can never be created, are never enforced in setStatus, and are never displayed | dependencies / tasks | Deep audit (verified) 2026-07-09
30 | Medium | Confirmed | Calendar-event update and delete have no permission or organizer-ownership check — any authenticated user can edit or cancel anyone's meeting | events (calendar) | Deep audit (verified) 2026-07-09
31 | Medium | Confirmed | Audit/activity/analytics feed is incomplete: TASK_UPDATED, TASK_ASSIGNED, SUBTASK_*, PROJECT_UPDATED, COMMENT_DELETED, APPROVAL_ACTION are defined but never emitted | events / audit | Deep audit (verified) 2026-07-09
32 | Medium | Confirmed | No global exception filter: raw Prisma errors (P2025/P2002/P2003) and any non-HttpException become an opaque HTTP 500 instead of 404/409/400 | infra / error-handling | Deep audit (verified) 2026-07-09
33 | Medium | Confirmed | Rate limiting covers only /auth/login and /auth/refresh; the global throttler is inert and every other endpoint is unthrottled | infra / throttling | Deep audit (verified) 2026-07-09
34 | Medium | Confirmed | Seed ships denormalized completion percentages that violate the app's own derivation rule; milestones seed at 0% despite completed tasks, and db:seed never runs the reconciliation backfill | packages/db (seed) | Deep audit (verified) 2026-07-09
35 | Medium | Confirmed | Org trend & contribution-heatmap read UserMetricDaily snapshots that are never auto-refreshed; after the first 'Rebuild snapshots' they freeze and diverge from the live charts | performance | Deep audit (verified) 2026-07-09
36 | Medium | Confirmed | Per-user contribution heatmap live fallback caps activity at 1 per day and never accumulates, so every active day renders as the lowest intensity and the actions total is undercounted | performance | Deep audit (verified) 2026-07-09
37 | Medium | Confirmed | Project/Milestone completionPercentage has two conflicting writers (manual edit + task rollup) that silently clobber each other — manual edits from Reports revert on the next task activity | projects/milestones/tasks | Deep audit (verified) 2026-07-09
38 | Medium | Confirmed | Settings → General 'Save Changes' reports success but silently discards Timezone and Brand Color; Logo & Archive are alert() stubs | settings | Deep audit (verified) 2026-07-09
39 | Medium | Confirmed | Subtasks can never be reopened; completing a parent task cascade-closes them irreversibly | tasks | Deep audit (verified) 2026-07-09
40 | Medium | Confirmed | Rollup recomputes (project %, milestone %, task actualHours) are non-transactional read-modify-writes → lost updates leave permanently wrong totals | tasks/timesheets | Deep audit (verified) 2026-07-09
41 | Medium | Confirmed | Timesheet submit/approve workflow does not exist — time can be logged but never submitted or approved | timesheets | Deep audit (verified) 2026-07-09
42 | Medium | Confirmed | List endpoints return the entire table with no pagination; the project Timesheets tab fetches all rows and renders them unvirtualized | timesheets | Deep audit (verified) 2026-07-09
43 | Medium | Confirmed | An admin cannot reset another user's password from the app — no endpoint and no UI exist | users/auth | Deep audit (verified) 2026-07-09
44 | Medium | Confirmed | Home dashboard attendance cards use a different query-key namespace than the Attendance page, so punch/regularize/leave-approval never refresh them | web/attendance | Deep audit (verified) 2026-07-09
45 | Medium | Confirmed | A transient failure of /me/effective-permissions silently collapses the whole app to a 'no access' shell with no error and no recovery | web/state-providers | Deep audit (verified) 2026-07-09
46 | Medium | Confirmed | Task status/progress/assignee changes only refresh the list they were made from; the same task stays stale in the other list | web/tasks | Deep audit (verified) 2026-07-09
47 | Medium | Confirmed | Workflow engine is inert: transitions/allowedRoles/conditions are never evaluated and there is no API to create/edit/delete workflow statuses | workflows / statuses | Deep audit (verified) 2026-07-09
48 | Low | Confirmed | Account lockout never resets failedLoginCount when the lock expires, so a single wrong attempt after cooldown re-locks the account immediately | auth | Deep audit (verified) 2026-07-09
49 | Low | Confirmed | Role.name has no uniqueness constraint; duplicate role names collapse in the resolver and cause RolesTab to check/assign every same-named role | rbac / roles | Deep audit (verified) 2026-07-09
50 | Low | Confirmed | No UI to edit, deactivate, reactivate or suspend a user; user list also hides every non-ACTIVE user, making them permanently unmanageable | users | Deep audit (verified) 2026-07-09
51 | Low | Confirmed | People 'Departments' tab is fabricated from job-title strings and ignores the real Department/DepartmentMember model; labels an arbitrary member as 'Head' | users | Deep audit (verified) 2026-07-09
52 | Low | Confirmed | Adding a user already in a department returns HTTP 500 (unhandled Prisma P2002) instead of 409 | departments | Deep audit (verified) 2026-07-09
53 | Low | Confirmed | No way to add or remove project members — no endpoint, no client method, no UI; the creator is the sole permanent member of every project | projects | Deep audit (verified) 2026-07-09
54 | Low | Confirmed | Tasks can be created against a soft-deleted (archived) project because softDelete does not cascade taskLists/milestones | projects | Deep audit (verified) 2026-07-09
55 | Low | Confirmed | No cross-field date validation: dueDate can be earlier than startDate, and NewProjectModal never captures startDate | projects | Deep audit (verified) 2026-07-09
56 | Low | Confirmed | Project decide() allows self-approval — no segregation of duties between requester and approver | projects | Deep audit (verified) 2026-07-09
57 | Low | Confirmed | Milestone auto-complete/revert (D1) is dead: RollupService is an empty stub, no AutomationEngine exists, the rule is never seeded, milestones are created with no workflow, and milestone status never advances | rollup / milestones / automation | Deep audit (verified) 2026-07-09
58 | Low | Confirmed | Soft-deleting a milestone or task list orphans its ProjectTask join rows (SetNull only fires on hard delete) | milestones | Deep audit (verified) 2026-07-09
59 | Low | Confirmed | Task List view hardcodes the list header to 'General', mislabeling projects whose default list has another name | tasks-ui | Deep audit (verified) 2026-07-09
60 | Low | Confirmed | A task with no workflow status is invisible on the Kanban board | tasks-ui | Deep audit (verified) 2026-07-09
61 | Low | Confirmed | Approval-requested notifications are never sent: project creation auto-opens a PENDING approval but no approver is notified | collab/notifications | Deep audit (verified) 2026-07-09
62 | Low | Confirmed | Adding a holiday on a date that already has one throws an unhandled Prisma P2002 (HTTP 500); organizationId is taken from the client body | attendance | Deep audit (verified) 2026-07-09
63 | Low | Confirmed | attendanceRate counts ON_LEAVE days in the denominator, penalizing employees on approved leave — contradicts the availability-normalized model | attendance | Deep audit (verified) 2026-07-09
64 | Low | Confirmed | Reports 'Tasks' column and CSV/PDF export overcount soft-deleted tasks (analytics.getProjectStats _count.projectTasks is unfiltered) | analytics | Deep audit (verified) 2026-07-09
65 | Low | Confirmed | Estimated-vs-actual bullet chart sums all-time and soft-deleted timesheet hours for 'actual' instead of non-deleted hours in the selected window | performance | Deep audit (verified) 2026-07-09
66 | Low | Confirmed | createTransition writes the raw (unresolved) workflowId and never validates the from/to statuses belong to that workflow | workflows | Deep audit (verified) 2026-07-09
67 | Low | Confirmed | EventService.emit is non-transactional across its three sinks and silently drops all events when no actor is in context — sinks can diverge | audit-events (event spine) | Deep audit (verified) 2026-07-09
68 | Low | Confirmed | Leave Approvals card is gated on leave.approve but its data endpoint requires leave.view.organization — an approve-only role sees a false 'no pending requests' and cannot approve | web/home-dashboard | Deep audit (verified) 2026-07-09
69 | Low | Confirmed | Home dashboard formats date-only fields in local time instead of the UTC-safe helper, shifting the displayed day by one in negative-UTC-offset zones | web/home-dashboard | Deep audit (verified) 2026-07-09
70 | Low | Confirmed | Home stat cards read ['analytics-dashboard'] which no project/task mutation invalidates, so counts stay stale after create/delete | web/home-dashboard | Deep audit (verified) 2026-07-09
71 | Low | Confirmed | Attribution columns store user ids as free strings with NO foreign key (AnalyticsEvent.userId, Approval.requestedBy, ApprovalAction.userId, *createdBy/uploadedBy/grantedBy) — inconsistent with Activity, no referential integrity | packages/db (schema) | Deep audit (verified) 2026-07-09
72 | Low | Confirmed | DocumentVersion lacks @@unique([documentId, versionNumber]) and an index; WorkflowTransition lacks any unique/index — duplicate versions/transitions can be persisted | packages/db (schema) | Deep audit (verified) 2026-07-09
73 | Low | Confirmed | Prod compose starts web before the API is ready (no healthcheck/condition), yielding 502s on /api/* during the migrate+boot window | infra / docker-compose | Deep audit (verified) 2026-07-09
74 | Low | Confirmed | Deleting a user is impossible from the app — no DELETE route and no UI (only status can be toggled) | users | Deep audit (verified) 2026-07-09
75 | Low | Confirmed | ProjectTask/Milestone/TaskList sequence assigned from a COUNT read outside the transaction — concurrent creates get duplicate ordering | tasks/milestones/tasklists | Deep audit (verified) 2026-07-09
76 | Low | Confirmed | Issue status-change, issue delete, and timesheet delete swallow errors with empty catch{} — failed mutations look like they succeeded | web/projects | Deep audit (verified) 2026-07-09
77 | Low | Confirmed | Projects list computes avatar initials via user.lastName[0], bypassing the safe helper — members with no surname render 'Xundefined' | web/projects | Deep audit (verified) 2026-07-09
78 | Low | Confirmed | api.departments.list return type mismatch — DepartmentSummary.memberCount is never populated (backend returns _count.members) | departments | Deep audit (verified) 2026-07-09
79 | Low | Confirmed | WorkflowStatus.sequence (and project-list currentStatus.type) are typed required but never returned by the task/project selects | tasks/projects | Deep audit (verified) 2026-07-09
80 | Low | Confirmed | FilesTab is a dead module: fully mock file data + alert() stubs, rendered from an unreachable branch | projects | Deep audit (verified) 2026-07-09
81 | Low | Confirmed | Four fake Settings tabs (Notifications/Workflows/Integrations/Billing) remain in the file as dead code with hardcoded fake data | settings | Deep audit (verified) 2026-07-09
82 | Low | Confirmed | POST /attendance/:id/regularize has no permission gate and no ownership check (IDOR write on attendance rows) | attendance | Deep audit (verified) 2026-07-09
83 | Low | Confirmed | Gantt and Kanban render every task row/node with no virtualization; whole-timeline DOM is built up front | web/projects | Deep audit (verified) 2026-07-09
84 | Low | Confirmed | No mutation ever invalidates the Activity feeds; the TaskDetailPanel Activity tab has no auto-refetch so it silently lags | web/activity | Deep audit (verified) 2026-07-09
85 | Low | Confirmed | Logging/deleting time recomputes Task.actualHours server-side but the client only invalidates the timesheets query | web/timesheets | Deep audit (verified) 2026-07-09
86 | Medium | Plausible | Migration/schema drift: 6 indexes declared in schema.prisma are absent from the only migration (0_init), so prod (migrate deploy) never creates them while dev (db push) has them | packages/db (migrations vs schema) | Deep audit (verified) 2026-07-09
87 | Medium | Plausible | UI/API authorization mismatch: user.view-only personas see enabled role/permission/override Save controls that 403, and the Save handlers swallow the error silently | web admin / user detail | Deep audit (verified) 2026-07-09
88 | Medium | Plausible | Leave request Submit and Cancel swallow backend rejections — the form silently does nothing with no error shown | web/attendance | Deep audit (verified) 2026-07-09
89 | Medium | Plausible | RBAC edits never refresh the live permission gate — two different query keys cache the same effective-permissions data | web/permissions | Deep audit (verified) 2026-07-09
90 | Low | Plausible | User-list projection ships every user's full base64 profile photo (up to 900KB each) and is fetched app-wide on every page | users | Deep audit (verified) 2026-07-09
91 | High | Refuted | New Project creation is broken — createdBy is threaded through as the user's email, backend requires a user id | web/projects | Deep audit (verified) 2026-07-09

## Permission Matrix
Permission code | Area | Description | Roles holding it
analytics.view.organization | analytics | View Org-wide on Analytics | Admin, Manager, Super Admin
analytics.view.own | analytics | View Own on Analytics | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
announcement.manage | announcement | Manage on Announcements | Admin, HR, Super Admin
appraisal.manage | appraisal | Manage on Appraisals | Admin, HR, Super Admin
attendance.manage | attendance | Manage on Attendance | Admin, HR, Super Admin
attendance.regularize | attendance | Regularize on Attendance | Admin, HR, Super Admin
attendance.view.organization | attendance | View Org-wide on Attendance | Admin, HR, Manager, Super Admin
attendance.view.own | attendance | View Own on Attendance | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
audit.export | audit | Export on Audit Log | Admin, Super Admin
audit.view | audit | View on Audit Log | Admin, Super Admin
calendar.create | calendar | Create on Calendar | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
calendar.delete | calendar | Delete on Calendar | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
calendar.update | calendar | Edit / Update on Calendar | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
calendar.view | calendar | View on Calendar | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
capacity.view | capacity | View on Team Capacity | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
channel.create | channel | Create on Channels | Admin, Business Development, Consultant, Employee, Manager, Senior Consultant, Senior Research Associate, Super Admin
channel.delete | channel | Delete on Channels | Admin, Super Admin
channel.update | channel | Edit / Update on Channels | Admin, Super Admin
channel.view | channel | View on Channels | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
comment.create | comment | Create on Discussion | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
comment.delete | comment | Delete on Discussion | Admin, Super Admin
comment.view | comment | View on Discussion | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
dashboard.view | dashboard | View on Dashboard | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
deadline.view.client | deadline | View Client Deadline on Client Deadlines | Admin, Manager, Senior Consultant, Super Admin
deal.manage | deal | Manage on BD Pipeline | Admin, Business Development, Manager, Super Admin
deal.view | deal | View on BD Pipeline | Admin, Business Development, Manager, Super Admin
department.create | department | Create on Departments | Admin, HR, Super Admin
department.delete | department | Delete on Departments | Admin, Super Admin
department.update | department | Edit / Update on Departments | Admin, HR, Super Admin
department.view | department | View on Departments | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
document.create | document | Create on Files & Media | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
document.delete | document | Delete on Files & Media | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
document.view | document | View on Files & Media | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
expense.approve | expense | Approve on Expenses | Admin, HR, Super Admin
expense.submit | expense | submit on Expenses | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
expense.view.organization | expense | View Org-wide on Expenses | Admin, HR, Super Admin
expense.view.own | expense | View Own on Expenses | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
group.create | group | Create on Permission Groups | Admin, Super Admin
group.delete | group | Delete on Permission Groups | Admin, Super Admin
group.manage_members | group | Manage Members on Permission Groups | Admin, Super Admin
group.update | group | Edit / Update on Permission Groups | Admin, Super Admin
group.view | group | View on Permission Groups | Admin, Super Admin
holiday.manage | holiday | Manage on Holidays | Admin, HR, Super Admin
holiday.view | holiday | View on Holidays | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
issue.create | issue | Create on Issues | Admin, Business Development, Consultant, Employee, Manager, Senior Consultant, Senior Research Associate, Super Admin
issue.delete | issue | Delete on Issues | Admin, Business Development, Consultant, Employee, Manager, Senior Consultant, Senior Research Associate, Super Admin
issue.update | issue | Edit / Update on Issues | Admin, Business Development, Consultant, Employee, Manager, Senior Consultant, Senior Research Associate, Super Admin
issue.view | issue | View on Issues | Admin, Business Development, Consultant, Employee, Manager, Senior Consultant, Senior Research Associate, Super Admin
leave.approve | leave | Approve on Leave | Admin, HR, Super Admin
leave.request | leave | Request on Leave | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
leave.view.organization | leave | View Org-wide on Leave | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
leave.view.own | leave | View Own on Leave | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
patent.manage | patent | Manage on Clients & Patents | Super Admin
patent.view | patent | View on Clients & Patents | Admin, Business Development, Consultant, Employee, Manager, Senior Consultant, Senior Research Associate, Super Admin
performance.view.organization | performance | View Org-wide on Performance | Admin, HR, Super Admin
performance.view.own | performance | View Own on Performance | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
permission.view | permission | View on Permissions | Admin, Super Admin
policy.manage | policy | Manage on HR Policies | Admin, HR, Super Admin
profile.update.any | profile | Edit Anyone's on User Profiles | Admin, HR, Super Admin
profile.view | profile | View on User Profiles | Admin, HR, Manager, Senior Consultant, Super Admin
profile.view.personal | profile | View Personal Details on User Profiles | Admin, HR, Super Admin
project.approve | project | Approve on Projects | Admin, Manager, Senior Consultant, Super Admin
project.create | project | Create on Projects | Admin, Business Development, Consultant, Employee, Manager, Senior Consultant, Senior Research Associate, Super Admin
project.delete | project | Delete on Projects | Admin, Super Admin
project.generate_pid | project | Generate PID on Projects | Admin, Super Admin
project.update | project | Edit / Update on Projects | Admin, Manager, Senior Consultant, Super Admin
project.view | project | View on Projects | Admin, Business Development, Consultant, Employee, Manager, Senior Consultant, Senior Research Associate, Super Admin
report.export | report | Export on Reports | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
report.view | report | View on Reports | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
reward.give | reward | give on Recognition | Admin, HR, Manager, Super Admin
role.create | role | Create on Roles | Admin, Super Admin
role.delete | role | Delete on Roles | Super Admin
role.update | role | Edit / Update on Roles | Admin, Super Admin
role.view | role | View on Roles | Admin, Super Admin
settings.update | settings | Edit / Update on Settings | Admin, Super Admin
settings.view | settings | View on Settings | Admin, Super Admin
task.assign | task | Assign on Tasks | Admin, Manager, Senior Consultant, Super Admin
task.create | task | Create on Tasks | Admin, Consultant, Manager, Senior Consultant, Senior Research Associate, Super Admin
task.delete | task | Delete on Tasks | Admin, Manager, Senior Consultant, Super Admin
task.update | task | Edit / Update on Tasks | Admin, Consultant, Manager, Senior Consultant, Senior Research Associate, Super Admin
task.view | task | View on Tasks | Admin, Business Development, Consultant, Employee, Manager, Senior Consultant, Senior Research Associate, Super Admin
tasklist.create | tasklist | Create on Task Lists | Admin, Consultant, Manager, Senior Consultant, Senior Research Associate, Super Admin
tasklist.delete | tasklist | Delete on Task Lists | Admin, Manager, Senior Consultant, Super Admin
tasklist.update | tasklist | Edit / Update on Task Lists | Admin, Consultant, Manager, Senior Consultant, Senior Research Associate, Super Admin
tasklist.view | tasklist | View on Task Lists | Admin, Business Development, Consultant, Employee, Manager, Senior Consultant, Senior Research Associate, Super Admin
team.manage | team | Manage on Team Spaces | Admin, HR, Manager, Super Admin
team.view | team | View on Team Spaces | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
timesheet.create | timesheet | Create on Timesheets | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
timesheet.delete | timesheet | Delete on Timesheets | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
timesheet.update | timesheet | Edit / Update on Timesheets | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
timesheet.view | timesheet | View on Timesheets | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin
user.create | user | Create on Users | Admin, HR, Super Admin
user.delete | user | Delete on Users | Admin, Super Admin
user.manage_access | user | Manage Access on Users | Admin, HR, Super Admin
user.update | user | Edit / Update on Users | Admin, HR, Super Admin
user.view | user | View on Users | Admin, Business Development, Consultant, Employee, HR, Manager, Senior Consultant, Senior Research Associate, Super Admin

## Roles
Role | Permissions | What it means
Super Admin | 96 | Everything, including client identity and the patent portal
Admin | 94 | Everything except a small number of Super-Admin-only surfaces
Manager | 57 | Runs projects and people; sees the client-committed deadline
HR | 51 | People operations only — deliberately excludes the delivery surfaces
Senior Consultant | 51 | Runs projects; same delivery reach as a Manager
Consultant | 44 | Delivery work; cannot approve or run a project for others
Senior Research Associate | 44 | Delivery work plus task assignment and issue updates
Business Development | 42 | Employee rights plus the BD pipeline (deal.view, deal.manage)
Employee | 40 | The baseline — own work, own time, own profile

## Deployment History
Date | Runbook | Covers | Regrant needed
2026-08-18 | DEPLOY_2026-08-18.md | Deploying this release to Contabo | yes
2026-08-19 | DEPLOY_2026-08-19.md | Deploying to Contabo | yes
| DEPLOY-PR100.md | Contabo deploy — PR #100 | yes
| REBUILD_2026-07_DEPLOY.md | Rebuild 2026-07 — deploy runbook | yes

## Documents Index
Document | Location | What it covers
Squark-Dashboard-Phase-1-Guide.pdf | pdash | The 22 Phase 1 modules described for the user
Squark-Dashboard-Phase-1-Summary.pdf | pdash docs | One-page Phase 1 summary
Squark-Dashboard-Status-Report.pdf | pdash | Current 3-page status report — phases, timeline, outstanding
Squark-Dashboard-Phase2-Status.pdf | pdash | Phase 2 status against the twelve-row timeline
Squark-Dashboard-Phase2-Closing-Position.pdf | pdash | What is done, what is not, and what each pending item needs
Squark-Dashboard-Test-Findings.pdf | pdash | Test findings and remediation
Squark-Dashboard-Changes-Summary.pdf | pdash docs | Change summary
Squark-Dashboard-Permission-Matrix.pdf | pdash docs | The full permission matrix
PID-Patent-System-Summary.pdf | pdash docs | How the PID and patent system works
PID-Patent-System-Health-Check.pdf | pdash docs | Health check of the PID/patent data
PID-Patent-System-v1-vs-v2.pdf | pdash docs | V1 vs V2 design comparison
PATENTS-QA-Findings-and-Fixes.pdf | pdash docs | Patents module QA
PROJECTS-QA-Findings-and-Fixes.pdf | pdash docs | Projects module QA
TASKS-QA-Findings-and-Fixes.pdf | pdash docs | Tasks module QA
QA-Issues-and-Fixes.pdf | pdash docs | QA issues and their fixes
Squark-QA-Findings-and-Fixes-Consolidated.pdf | pdash docs | Consolidated QA findings
PHASES.md | repo | The authority on which phase work belongs to (388 lines)
PHASE-SUMMARY.md | repo | Short version of both phases
QA_TEST_FINDINGS.md | repo | 333 findings from the multi-agent QA sweep (2,073 lines)
DEEP_AUDIT_VERIFIED_2026-07-09.md | repo | 91 verified audit findings
docs/KNOWLEDGE_TRANSFER.md | repo | Knowledge transfer guide for the whole system
docs/ARCHITECTURE.md | repo | System architecture
docs/AUTH_ARCHITECTURE.md | repo | Authentication and session design
docs/TEAMS_FEATURES.md | repo | Teams-inspired feature port (1,333 lines)
docs/TEAMNEST_FEATURES.md | repo | TeamNest feature port
docs/zoho-projects-complete-spec.md | repo | The original frozen spec (6,205 lines)
docs/APPRAISAL_PLAN.md | repo | Appraisal cycle design
DEPLOY-PR100.md | repo | Deployment runbook for PR #100
Permission-Matrix.xlsx | pdash | The permission matrix as maintained by the business
SquarkIP-credentials.xlsx | pdash | Team login credentials — do not modify