## Overview
Squark Dashboard — Project Record
Prepared by | Anant Gupta
Date | 26 August 2026
Period covered | 24 June 2026 – 26 August 2026
Live system | https://217.76.59.244.sslip.io
Repository | https://github.com/AnantSQIP/pdash
Phase 1 | Closed 12 August 2026 — 22 modules, live and in daily use
Phase 2 | Open since 12 August 2026 — 7 of 10 agreed items complete, 3 partial
Total commits | 223 (219 merged to main, 4 on an unmerged branch)
Pull requests | 102 raised, 97 merged
Working days | 38
API modules | 42
Automated checks | 409 passing
CONTENTS
Timeline | Dated milestones across both phases
Meetings & Communications | Every recorded discussion, instruction and delivery
Feedback Log | Client feedback by date, with delivery status
Phase 2 Status | The ten agreed timeline items
Modules Delivered | What each module does
Open Items | What remains, and what input is required
Bugs Found & Fixed | Defects located during testing and their impact
Pull Requests | All 102, with dates
Commits | All 223, with dates
Daily Activity | Commits per working day
Branches | Every branch and its last commit
Architecture — PID & Patents | How PIDs, clients and patents relate

## Timeline
Date | Phase | Milestone | Detail
2026-06-24 | Phase 1 | Project begins | First commit — SquarkIP pdash project management system
2026-06-25 | Phase 1 | Live API + real data | Collapsible sidebar, Kanban/Gantt/Calendar, progress colour scale
2026-06-28 | Phase 1 | Auth, RBAC, attendance, performance | The four foundations everything else depends on
2026-06-30 | Phase 1 | Ready for local testing | Demo requested from Yash Bhargava
2026-07-03 | Phase 1 | Hosted for review | Moved off the laptop so the team could use it in real time
2026-07-06 | Phase 1 | Production deploy | Docker stack, security hardening, Contabo server
2026-07-08 | Phase 1 | Opened to the team | Contabo, credentials issued to Basant, Neha, Khushi
2026-07-09 | Phase 1 | Deep audit | 87 of 88 findings remediated
2026-07-10 | Phase 1 | Permission matrix shared | Catalog and role summary delivered to Ajay Sharma
2026-07-13 | Phase 1 | Capacity & dual deadlines | Team capacity board, internal vs client deadlines, overdue alerts
2026-07-14 | Phase 1 | PII boundary | First-login profile collection; personal details restricted server-side
2026-07-15 | Phase 1 | Regularisation with HR approval | Attendance regularisation request flow
2026-07-17 | Phase 1 | Renamed to Squark Dashboard | Performance rework, expenses module, WFH as a work mode
2026-07-19 | Phase 1 | Collaboration + HR modules | Chat, presence, polls; announcements, policy library, org chart, appraisals
2026-07-20 | Phase 1 | Three-batch delivery plan agreed | Batch 1 Home/Projects/Tasks/Capacity; Batch 2 Calendar-People; Batch 3 Appraisals-Settings
2026-07-22 | Phase 1 | Project types + task templates | HML, Claim Chart, FTO, Novelty and the rest, each with a standard task list
2026-07-23 | Phase 1 | PID system + patent portal | SQ_26_27_nnn identifiers and the confidential patent portal
2026-07-24 | Phase 1 | 14-agent QA sweep | Four critical confidentiality issues found and closed the same day
2026-07-27 | Phase 1 | PID lifecycle + Log Time rebuild | Allocator with expiry and tail-reclaim; two-option time logging
2026-07-29 | Phase 1 | Feedback rounds 2 and 3 | Timesheet backfill windows, PID reopen, project chat mentions
2026-07-30 | Phase 1 | PID Ledger + daily digest | Lifecycle states, search, and the 10pm admin digest
2026-08-05 | Phase 1 | Delivery clients | One client, many PIDs; client identity access-restricted
2026-08-07 | Phase 1 | Technology domains | A second axis beside project type; project list ordering
2026-08-12 | — | PHASE 1 CLOSED | 22 modules live. Outstanding items formally recorded. Phase 2 opened the same day
2026-08-13 | Phase 2 | Clients & patents | Archive vs remove, tagging after creation, the client ledger, formerHandles
2026-08-13 | Phase 2 | Team spaces + BD pipeline | Somewhere for work that is not a client project; deals, stages, forecasting
2026-08-16 | Phase 2 | Measurement integration | Internal work counts in timesheets, capacity and performance
2026-08-17 | Phase 2 | Reporting lines established | The appraisal module works for the first time; 2026 holiday calendar
2026-08-19 | Phase 2 | Eight pull requests merged | BD role, departments, org chart, four concurrency races, performance metrics, ledger links
2026-08-23 | Phase 2 | Patent ID to number lookup | Three visibility tiers; feedback module; client ledger billing rate; self-as-PM
2026-08-25 | Phase 2 | Status report delivered | Phase 1 and 2 summary; shortened to 3 pages on request
2026-08-26 | Phase 2 | Defect hunt | PID/client split, IST timezone bug, December leave lockout — all fixed

## Meetings & Communications
Date | With | Type | Subject | Artefact / Outcome
2026-06-30 | Yash Bhargava | Message | Performance Dashboard ready for local testing; demo requested
2026-07-03 | Yash Bhargava | Review | Asked for it to be hosted rather than demoed on a laptop, 'so we can use it in realtime' | Cloudflare tunnel link + credentials shared
2026-07-03 | Yash Bhargava | Access | Non-admin login requested to see the user-end view; Basant, Neha, Khushi added to testing | SquarkIP-credentials.xlsx
2026-07-06 | Ajay Sharma | Meeting | First contact — joined meeting
2026-07-08 | Team | Deployment | Dashboard hosted on the Contabo server and opened for team testing | https://217.76.59.244.sslip.io
2026-07-10 | Ajay Sharma | Demo | Demo of the Task Tracker requested and given
2026-07-10 | Ajay Sharma | Document | Permission matrix, catalog and role summary shared | Permission-Matrix.xlsx
2026-07-10 | Yash Bhargava | Feedback | 'The profiles are wrong designation wise' | Led to the roster/designation alignment work
2026-07-13 | Ajay Sharma | Scheduling | Dashboard review deferred — 'currently packed with a bunch of stuff'
2026-07-14 | Ajay Sharma | Document | Patent classification assignment submitted; KT (knowledge transfer) prepared and shared | /kt-5d2bef8509/
2026-07-15 | Ajay Sharma | Meeting | Dashboard session held at 4 PM
2026-07-15 | Ajay Sharma | Instruction | Asked for an Excel of the changes being made — 'which feature we have introduced' | Meeting_Logs.xlsx shared
2026-07-15 | Ajay Sharma | Scope | Instruction to review every TeamNest feature and integrate the most required ones
2026-07-16 | Ajay Sharma | Planning | Asked for a batch-of-features plan with timeline targets; recurring meeting created | Agreed: batches of 3 modules per meeting
2026-07-16 | Ajay Sharma | Target | 'Lets target to upgrade and finalise this on the highest level by next week' | 4-5 more people to be added to testing
2026-07-17 | Ajay Sharma | Status | Progress status requested and delivered | Squark-Dashboard-Project-Status.pdf
2026-07-17 | Ajay Sharma | Scope | OneNote integration raised; Gurgaon team to begin testing
2026-07-20 | Ajay Sharma | Meeting | Call held at 12:00; three-batch delivery plan agreed
2026-07-20 | Ajay Sharma | Feedback | Tool observation workbook shared for integration in the next stage | Tool Observation - Ajay.xlsx
2026-07-22 | Ajay Sharma | Feedback | Punch-in section requested on Home; admin rights removed to see the user-end view
2026-07-22 | Ajay Sharma | Instruction | Profile data to be cleaned for the selected testers before team testing
2026-07-22 | Ajay Sharma | Scope | Training module recorded as a LAST-PHASE item (upload, access grant, head and reviewer allotment) | Still deferred as of Aug 2026
2026-07-23 | Ajay Sharma | Delivery | PID and Patent ID work reported complete; self-testing and a written summary requested
2026-07-24 | Ajay Sharma | Meeting | Team Capacity review — tentative/pending leave to be visible, project-style layout, click-a-day to allot
2026-07-24 | Ajay Sharma | Feedback | Capacity to be grouped Gurgaon / Jaipur, ordered A-Z
2026-07-24 | Ajay Sharma | Delivery | Changes completed and deployed live (21:53)
2026-07-30 | Ajay Sharma | Feedback | Feedback batch: PID reopen, PID ledger detail, timesheet calendar, expenses, punch locations, daily digest, backfill windows | See Feedback Log sheet
2026-08-04 | Ajay Sharma | Feedback | Feedback batch: timesheets real-time, attendance 24h glitch, comp-off, roles/capacity, projects, calendar, digest, colours | See Feedback Log sheet
2026-08-06 | Ajay Sharma | Feedback | Feedback batch: comp-off credit/debit, half-day leave, project tiles, PID generation, calendar Monday-start, reports | See Feedback Log sheet
2026-08-25 | Ajay Sharma | Status | Phase 1 & Phase 2 summary with timeline shared | Squark-Dashboard-Status-Report.pdf
2026-08-25 | Ajay Sharma | Feedback | 'This very big data. Unable to understand' — shorter version requested and delivered | Report cut from 5 pages to 3
2026-08-26 | Ajay Sharma | Question | Asked whether Phase 2 features are in development or need discussion | Training module integration flagged for discussion

## Feedback Log
Date | Module | Feedback / Request | Status
2026-07-20 | Attendance | Regularise — missing punch-in/out: route to HR or Manager | Delivered
2026-07-20 | Attendance | Regularise — show punch in/out timing when applied | Delivered
2026-07-20 | Attendance | Average punch in & punch out | Delivered
2026-07-20 | Projects | Standard task lists per type — HML (4 steps), CC from Client (3), CC New (3) | Delivered
2026-07-20 | Calendar | Finalise types; remove Milestone; names A-Z | Delivered — milestones removed entirely
2026-07-20 | Leaves | Leave rules per TeamNest — 1.5 CL, 0.5 SL, marriage leave, comp-off, optional holiday | Delivered
2026-07-20 | Leaves | Who can set holidays — HR or not; verify | Delivered
2026-07-20 | Leaves | Past leave cannot be requested | Delivered
2026-07-20 | Leaves | Two leave types on the same day / WFH on a CL day | Delivered
2026-07-20 | Leaves | Comp-off approval routing to HR / Yash / Manager; project ID optional | Delivered
2026-07-20 | Expenses | Who approves, type, verify the request is actually raised, how credited | Delivered
2026-07-20 | Reports | Editable but issue marking it done; rethink what a project report should achieve | Delivered
2026-07-20 | Appreciation | Should be part of the whole project system; count on Home; list of tasks/projects | Delivered
2026-07-20 | Discussion | Paste screenshots (SNIPPET); notify new members; show chat history; remove lock icons | Delivered
2026-07-20 | Company | Define the tab — appreciation, org chart, policy, directory | Delivered
2026-07-30 | PID | PID reopen reuses the same PID and flips the ledger back to Working | Delivered
2026-07-30 | PID | PID Ledger full detail + CSV export carrying every project field | Delivered
2026-07-30 | Timesheet | Colour-coded monthly fill calendar; enlarge; day logs on click | Delivered
2026-07-30 | Timesheet | 2-week reminder when a required day is unfilled | Delivered
2026-07-30 | Timesheet | Backfill windows — 1mo free / 1-3mo Super-Admin approval / >3mo blocked | Delivered
2026-07-30 | Expenses | Currency option removed — amounts are INR | Delivered
2026-07-30 | Attendance | HR / Super-Admin can see punch-in/out coordinates with map links | Delivered
2026-07-30 | Digest | Daily admin digest at 10pm IST summarising the day | Delivered
2026-07-30 | Projects | Optional task hours; admin PM delegation; custom project-type templates | Delivered
2026-07-30 | Projects | Subtasks restored on the task page | Delivered
2026-07-30 | Capacity | Task creation not working for the respective person; assignment not showing | Delivered
2026-08-04 | Timesheet | Fill calendar updates in real time; bigger tiles; clickable days; day detail panel | Delivered
2026-08-04 | Attendance | Fixed the 24-hour glitch — shifts capped at 16h; auto punch-out at 23:59 IST | Delivered
2026-08-04 | Attendance | First-login punch-in popup with WFH option | Delivered
2026-08-04 | Attendance | Area column reverse-geocoded; full column names; date picker; custom-range CSV export | Delivered
2026-08-04 | Comp-off | Half-day / full-day; reflected in attendance; becomes a required timesheet day | Delivered
2026-08-04 | Capacity | Role-first staffing — one person can hold PM + Reviewer + Analyst on one task | Delivered
2026-08-04 | Capacity | Single-person allocation window from the capacity board | Delivered
2026-08-04 | Projects | Save-as-template persists; project type shown as a tag; PID text bigger | Delivered
2026-08-04 | Calendar | Team Calendar frozen header/member column; celebrations (birthdays, anniversaries) | Delivered
2026-08-04 | Digest | Admin-editable send time; detailed /digest screen; deep links | Delivered
2026-08-04 | Home | Requests hub aggregating pending regularisations + comp-off claims | Delivered
2026-08-06 | Timesheet | Logged hours capped at 16 per entry, enforced server-side | Delivered
2026-08-06 | Attendance | Work past 23:59 requires a regularisation declaring the late-night hours | Delivered
2026-08-06 | Comp-off | Two movements — Avail (spend) and Credit (claim); balance panel rewritten | Delivered
2026-08-06 | Leaves | Half-day / full-day carried through balances, calendars and attendance | Delivered
2026-08-06 | Projects | PID never assigned automatically — must be deliberately generated | Delivered
2026-08-06 | Projects | Mark-complete only when every task is closed; client delivery date captured | Delivered
2026-08-06 | Calendar | Monday-Sunday everywhere; company holidays; tentative/pending leave visible | Delivered
2026-08-06 | Reports | Per-project report; search by PID or name; export per project | Delivered
2026-08-06 | Colours | Calendar palette replaced — previous colours not differentiable at a glance | Delivered
2026-07-22 | Training | Training module upload, access grant, head and reviewer allotment | DEFERRED — last phase, awaiting go-ahead
2026-07-30 | Permissions | 8 red 'to be discussed' cells in the Permission Matrix | Resolved — matrix now has zero red cells
2026-08-04 | Reports | Project Report — how should it look and what is the output? | Open — needs definition

## Phase 2 Status
Module | Item | Status | Remarks
Attendance | Work-from-home prompt on punch in | Complete | Was already in place
Project | Client and Patent IDs | Complete | Now linked to the ledgers
Project | Other teams — HR, Sales, BD | Partial | Sales not modelled separately
HR | Holidays | Complete | 2026 calendar with optional holidays
HR | Policies | Complete | Ten policies, with version control
Company | Feed, recognition, policies, directory | Complete | Organisation chart included
People | Departments | Complete | Full management screen
Appraisal | All six sub-items | Complete | Parameters fully editable
Performance | 360° project feedback | Partial | General feedback in place; project round pending
Productivity | Input; billable hours | Partial | Billable hours complete; "Input" undefined

## Modules Delivered
Area | Module | What it does | Phase
Access & identity | Login / sessions | Cookie + JWT login. Deactivating an account cuts a held token on the very next request | 1
Access & identity | RBAC | Nine roles over a four-level model — role presets, per-user grants, per-user denials, project membership | 1
Access & identity | Org passcode | Second factor on changes that cannot be walked back | 1
Access & identity | Audit log | Every significant action recorded with actor and time | 1
Delivery | Projects | Nine patent-analysis types, each with a standard task list created on the spot | 1
Delivery | PID system | SQ_26_27_nnn identifiers, multiple rounds under one PID, full ledger | 1
Delivery | Tasks & subtasks | Role-first staffing — one person can hold PM + Reviewer + Analyst on one task | 1
Delivery | Timesheets | Backdating windows: free under a month, approved to three, refused beyond | 1
Delivery | Patents & clients | Confidential portal; handles shown everywhere, real numbers restricted | 1
People ops | Attendance | Punch in/out, WFH as a work mode, 16h shift cap, auto punch-out at 23:59 IST | 1
People ops | Regularisation | Missing-punch requests routed to HR with approval | 1
People ops | Leave | Annual quotas, half days, business-day counting, holidays excluded | 1
People ops | Comp-off | Claim a worked weekend, HR approves, credit spent as CO leave | 1
People ops | Expenses | Submit to reimbursement; the submitter cannot approve their own | 1
People ops | People directory | Personal details restricted to Admin, Super Admin and HR — removed server-side | 1
People ops | Appraisals | Structured cycles: self-assessment, manager review, acknowledgement | 1
People ops | Policies | Library with version control, so an acknowledgement means something | 1
Insight | Performance | Output-based scoring, charts, contribution heatmap | 1
Insight | Team capacity | Who is free and when; click a day to allot | 1
Insight | Reports | Per-project and range reports, CSV and PDF export | 1
Insight | Daily digest | Admin summary at a configurable hour, everything deep-linked | 1
Insight | Calendars | Personal and team; holidays, leave, WFH, birthdays and anniversaries | 1
Clients | Client ledger | Work and value per client, recomputed live; billing rate makes value derived | 2
Clients | Client records | Contact, country, industry, account manager, rate, engagement start | 2
Non-delivery | Team spaces | Somewhere for HR/BD work — no PID, no client, out of both ledgers | 2
Non-delivery | BD pipeline | Deals, stages, activity history, forecasting, win/loss reporting | 2
Org | Departments | Full management screen with a named head | 2
Org | Org chart | Built from the reporting lines | 2
People ops | Feedback | Any colleague about any colleague; author, HR and reporting manager can read it | 2
Patents | Patent lookup | Handle to number and back, open to the whole firm; client stays restricted | 2

## Open Items
Ref | Item | Position | Status | Input required
Phase 2 / 7 | Training module | Deferred on instruction 22 Jul 2026. Nothing built | DEFERRED | Go-ahead, and what a training record holds
Phase 2 / 3 | Sales as a separate function | One BD role, no Sales role. Treated as one desk | Open — decision | Is Sales separate from BD?
Phase 2 / 11 | 360° project feedback | General feedback complete; the project-scoped round is not built. No longer blocked | Open — ready to build | Everyone rates each other, or manager rates team?
Phase 2 / 12 | Productivity "Input" | Billable hours complete. "Input" has never been defined | Open — needs definition | One sentence: what does Input count?
Phase 1 debt | 2027 holidays | Zero rows loaded. From 1 Jan 2027 every holiday counts as a working day | Open — HIGH, by 31 Dec 2026 | The dated list, and which are optional
Phase 1 debt | Email transport | Notifications are in-app only | Open | Do you want it? SMTP credentials?
Phase 1 debt | Exit process | Access is withdrawn immediately on deactivation; reassigning open work is manual | Open | Build a reassignment flow?
Phase 1 debt | Shared HR account | hr@squarkip.com acts with no individual attribution in the audit log | Open | Who inherits it, or keep as-is?
Phase 1 debt | Punch location retention | Home coordinates kept indefinitely on WFH punches | Open | Retention period — 90 days? 1 year?
Phase 1 debt | Fixed escalation address | Was hardcoded in source; now configurable by environment | Resolved 25 Aug 2026 | —
Phase 1 debt | Reporting lines | Were absent, blocking appraisals and the org chart | Resolved 17 Aug 2026 | —
Security | Legacy client codes | 6 of 11 codes derive from client names (MLK to Malikie). Script built and dry-runs clean | Open — your call | Approval to re-code; changes IDs on future documents
Delivery | Unmerged branch | 5 commits including two defect fixes affecting daily use | Awaiting merge | Approval to merge and deploy

## Bugs Found & Fixed
Found | Area | Defect | Impact | Status
2026-08-19 | Performance | Hours logged always zero — a NULL-unsafe filter excluded every ordinary entry | 1,509 hours invisible; one person ranked second having completed nothing | Fixed
2026-08-19 | Concurrency | Four races on check-then-write | The 16-hour daily cap could be breached; duplicate leave for one absence | Fixed
2026-08-19 | Auth | Signing out did not end the session | The access token stayed usable for up to fifteen minutes | Fixed
2026-08-19 | Deployment | A missing flag blanked every secret | Took the live site down; the on-screen error pointed at the database | Fixed
2026-08-23 | Projects | "May run a project" and "may mint a PID" were one flag | Managers and Senior Consultants told to hand their own matter to an Admin | Fixed
2026-08-23 | Patents | Number search validated the typed string, not the normalised one | "%%%" became a match-everything wildcard — the lookup handed out the list | Fixed
2026-08-23 | Patents | 404 for unknown vs 403 for not-yours | Told apart, the route became a directory of which patent IDs are real | Fixed
2026-08-24 | Patents | Seed wrote unpadded handles, the formatter minted padded ones | Typing Pat_MLK_001 failed to find Pat_MLK_1 — a patent plainly on screen | Fixed
2026-08-25 | Settings | Logo upload and Archive Organization were dead buttons | Clicking either did nothing but raise "coming soon" | Fixed
2026-08-26 | Architecture | One PID could end up meaning two different clients | Ledger billed round 1 to one client and round 2 to another under one identifier | Fixed
2026-08-26 | Attendance | Ten call sites used the UTC day instead of the IST day | For 5.5h every night: marking attendance for TODAY refused as "in the future" | Fixed
2026-08-26 | Leave | Quota year read from today, not from the leave | In December nobody could book January leave — refused against the old quota | Fixed
2026-08-26 | Patents | Deleted patents still listed as live tags on projects | A handle shown on screen that resolved to nothing | Fixed
2026-08-26 | Reporting | chainGaps counted a patent used when its only project was deleted | Two screens gave opposite answers about the same patent | Fixed

## Pull Requests
PR | Created | Merged | Title | Branch | Status
1 | 2026-06-25 | 2026-07-06 | Build out SquarkIP dashboard: live API integration, real seed data, c… | Admin---Module | Merged
2 | 2026-07-08 | 2026-07-08 | Squarkip dashboard snapshot | squarkip-dashboard-snapshot | Merged
3 | 2026-07-08 | 2026-07-08 | feat(auth): self-service change-password + org password-reset script | squarkip-dashboard-snapshot | Merged
4 | 2026-07-10 | 2026-07-10 | feat: file attachments/media + organization step-up passcode(after discussion with Ajay Sir) | fix/deep-audit-2026-07 | Merged
5 | 2026-07-13 | 2026-07-13 | Team capacity, dual deadlines, overdue alerts, project requests — plus 5 fixes | fix/deep-audit-2026-07 | Merged
6 | 2026-07-13 | 2026-07-13 | Password recovery that actually works, and un-freeze the task/project plan | fix/planning-and-password-recovery | Merged
7 | 2026-07-13 | 2026-07-13 | Harden Team Capacity for production: close a cross-tenant leak, fix edges, open it from projects | fix/capacity-hardening | Merged
8 | 2026-07-14 | 2026-07-14 | Roster: offboard Riya Bhola, intern-cohort designations, add Geetesh Rathore | chore/roster-2026-07 | Merged
9 | 2026-07-14 | 2026-07-14 | User profiles: collect joining details on first sign-in, with a hard PII boundary | feat/user-profile | Merged
10 | 2026-07-14 | 2026-07-14 | docs: knowledge-transfer guide for the whole system | docs/kt | Merged
11 | 2026-07-14 | 2026-07-14 | chore: never let dashboard screenshots reach the public repo | chore/ignore-kt-shots | Merged
12 | 2026-07-14 | 2026-07-14 | Fix: modal action buttons could scroll off-screen | fix/modal-overflow | Merged
13 | 2026-07-14 | 2026-07-14 | Make the data tables usable on mobile | fix/mobile-tables | Merged
14 | 2026-07-15 | 2026-07-15 | feat(attendance): regularization requests with HR approval + fixes | feat/attendance-regularization-holidays-notif-autoread | Merged
15 | 2026-07-15 | 2026-07-15 | feat(projects,capacity): completion lifecycle, deadline extend, emergency-leave coverage | feat/project-lifecycle-capacity-extend-coverage | Merged
16 | 2026-07-15 | 2026-07-15 | feat(capacity,attendance): retrospective view, comp-off, drop Overloaded | feat/capacity-history-compoff | Merged
17 | 2026-07-16 | 2026-07-16 | feat(capacity,tasks,auth): sticky dates, deadline cleanup, drill-down, idle logout, assigned-by | feat/capacity-deadlines-assignee-autologout | Merged
18 | 2026-07-17 | 2026-07-17 | feat(ui,projects): rename to Squark Dashboard, meaningful icons, billable review, cleanups | feat/rename-icons-billable-cleanups | Merged
19 | 2026-07-17 | 2026-07-17 | feat(performance): clearer layout, interactive donuts, explained metrics | feat/performance-charts-metrics | Merged
20 | 2026-07-17 | 2026-07-17 | fix(tasks,billable,capacity): dropdown overlay, subtask uncheck, plan align, billable inheritance, leave visibility | fix/task-panel-billable-capacity | Merged
21 | 2026-07-17 | 2026-07-17 | feat(projects,capacity): drop approval gate, fix designations, detach capacity date bar | feat/no-approval-designations-fixed-datebar | Merged
22 | 2026-07-17 | 2026-07-17 | feat(auth): recover a forgotten organization passcode via account password | feat/org-passcode-recovery | Merged
23 | 2026-07-17 | 2026-07-17 | chore(db): compile update-designations script into the prod image | chore/compile-designation-script | Merged
24 | 2026-07-17 | 2026-07-17 | feat(expenses,attendance,discuss): expense module, WFH work mode, punch validation, weekend comp-off, channel rename | feat/expenses-wfh-punch-compoff-rename | Merged
25 | 2026-07-22 | 2026-07-22 | fix: QA findings remediation — object-level authz, validation, cross-tenant scoping (P1–P8) | fixes-attendance-leaves-projects | Merged
26 | 2026-07-22 | 2026-07-22 | feat(rbac): add Senior Research Associate role + align roster to designations | roster-senior-research-associate | Merged
27 | 2026-07-22 | 2026-07-22 | chore(db): clear the 9 members' personal activity for a clean test slate | clear-seed-activity | Merged
28 | 2026-07-22 | 2026-07-22 | feat(home,timesheets): punch from Home + Timesheets sidebar module | feat-punch-home-timesheets-module | Merged
29 | 2026-07-22 | 2026-07-22 | docs(research): patent HML ranking + claim-chart system research brief | docs-patent-hml-research | Merged
30 | 2026-07-22 | 2026-07-22 | feat(projects): project type on creation + auto-generated task workflow | feat-project-types-templates | Merged
31 | 2026-07-22 | 2026-07-22 | fix(home): move the Punch In card to the top of the dashboard | fix-home-punch-top | Merged
32 | 2026-07-22 | 2026-07-22 | feat(patents,projects): PID + confidential Patent portal + project-module fixes | feat-pid-patent-portal | Merged
33 | 2026-07-23 | 2026-07-23 | feat(patents): patent documents (upload-to-create + attach) + passcode/home tweaks | feat-patent-documents | Merged
34 | 2026-07-23 | 2026-07-23 | fix(patents,documents): robustness — disk storage, dedup, re-creatable codes, doc passcode | fix-patent-robustness | Merged
35 | 2026-07-23 | 2026-07-23 | fix(patents): filename-gated uploads + editable client codes + non-stale project client | fix-patent-small-fixes | Merged
36 | 2026-07-24 | 2026-07-24 | feat: workspace rebuild — PID flow, offices, profile gate, capacity, timesheets | feat-rebuild-pid-offices-timesheets | Merged
37 | 2026-07-25 | 2026-07-25 | QA remediation: deep-test (P0/B/C) + Home module + 9-6 IST | qa-deeptest-workhours | Merged
38 | 2026-07-27 | 2026-07-27 | Timesheets "Other" category + QA Rounds 2-3 remediation (Patents + Tasks) | qa-deeptest-workhours | Merged
39 | 2026-07-27 | 2026-07-27 | Log Time: 2 options (Project task w/ Assign-PID-later toggle) + Other with Title | qa-deeptest-workhours | Merged
40 | 2026-07-27 | 2026-07-27 | Log Time: Project title + auto-filled mandatory PID | qa-deeptest-workhours | Merged
41 | 2026-07-27 | 2026-07-27 | Log Time: keep Project + Task when "Assign PID later" is on (hide only PID) | qa-deeptest-workhours | Merged
42 | 2026-07-27 | 2026-07-27 | PID lifecycle + PM picker + review-before-attach + role-based task staffing | qa-deeptest-workhours | Merged
43 | 2026-07-27 | 2026-07-27 | PID: continuing-series (destroy-on-expiry, tail-reclaim); drop give-back; hide type+PM from reviewer | qa-deeptest-workhours | Merged
44 | 2026-07-27 | 2026-07-27 | PID reviewer can set project type + manager on attach | qa-deeptest-workhours | Merged
45 | 2026-07-27 | 2026-07-27 | Fix PID Ledger crash on legacy/unknown reservation status | qa-deeptest-workhours | Merged
46 | 2026-07-27 | 2026-07-27 | reset-keep-one-project: delete all projects except one (keep users/RBAC) | qa-deeptest-workhours | Merged
47 | 2026-07-28 | 2026-07-28 | Task screen: single page, dropdown progress, auto-sum est. hours | qa-deeptest-workhours | Merged
48 | 2026-07-28 | 2026-07-28 | Task PM defaults to project manager; remove progress dropdown | qa-deeptest-workhours | Merged
49 | 2026-07-28 | 2026-07-28 | Enforce task-assignment for time logging + capacity/performance consistency | qa-deeptest-workhours | Merged
50 | 2026-07-28 | 2026-07-28 | Batch A: expense placeholder, capacity per-project filter, remove Discuss | qa-deeptest-workhours | Merged
51 | 2026-07-28 | 2026-07-28 | Batch B: PID export CSV + Super-Admin PID detail + re-initialize completed project | qa-deeptest-workhours | Merged
52 | 2026-07-28 | 2026-07-28 | Batch C: mandatory location on attendance punch in/out | qa-deeptest-workhours | Merged
53 | 2026-07-28 | 2026-07-28 | Batch D: new project-type task lists + custom project types | qa-deeptest-workhours | Merged
54 | 2026-07-28 | 2026-07-28 | RBAC: additive permission-matrix grants (calendar/issue/tasklist/timesheet) | qa-deeptest-workhours | Merged
55 | 2026-07-29 | 2026-07-29 | Second feedback round: PID reopen/detail, timesheet calendar+reminder, expense currency, punch locations, daily digest | qa-deeptest-workhours | Merged
56 | 2026-07-29 |  | Timesheet backfill windows + Super-Admin approval flow | qa-deeptest-workhours | Closed
57 | 2026-07-29 | 2026-07-29 | Timesheet backfill windows + Super-Admin approval flow | timesheet-backfill-approval | Merged
58 | 2026-07-29 | 2026-07-29 | Third feedback round: optional hours, graded/compact calendars, expense notify, subtasks, admin PM delegation, PID Ledger module | feedback-batch3-tasks-timesheets-pid | Merged
59 | 2026-07-29 | 2026-07-29 | Team Calendar tab + redesigned timesheet/attendance calendars | calendar-team-tab-ui-redesign | Merged
60 | 2026-07-29 | 2026-07-29 | Team Calendar: multi-month scrollable timeline (1mo back / 3mo ahead) | team-calendar-multimonth | Merged
61 | 2026-07-29 | 2026-07-29 | Subtasks: add / rename / delete from the task page | subtask-edit-delete | Merged
62 | 2026-07-29 | 2026-07-29 | Project chat: @mention project members in the Discussion tab | project-chat-mentions | Merged
63 | 2026-07-29 | 2026-07-29 | Permission Matrix (New): apply role permission removals | permission-matrix-removals | Merged
64 | 2026-07-30 | 2026-07-30 | PID Ledger: lifecycle states (completed/closed) + search by PID/client | pid-ledger-states-search | Merged
65 | 2026-07-30 | 2026-07-30 | Timesheets rewrite + attendance 24h fix + project fixes (batch 1 of feedback) | timesheets-attendance-projects-fixes | Merged
66 | 2026-07-30 | 2026-07-30 | Attendance team-location: area field, full labels, 1-year view + CSV export | attendance-team-location | Merged
67 | 2026-07-30 | 2026-07-30 | Team Calendar: frozen date bar rewrite + upcoming = this/next month | team-calendar-rewrite | Merged
68 | 2026-07-30 | 2026-07-30 | Profile wedding anniversary → birthdays/anniversaries in calendar + Jaipur area | profile-anniversary-celebrations | Merged
69 | 2026-07-30 | 2026-07-30 | Role-first task staffing (multi-role, per-role hours+deadline) + capacity assign + assign-error fix | roles-based-staffing | Merged
70 | 2026-07-30 | 2026-07-30 | Comp-off: half/full day + timesheet & attendance integration + pending asterisk | compoff-halfday-integration | Merged
71 | 2026-07-30 | 2026-07-30 | Daily digest: editable time + detail screen; login punch-in prompt | digest-punchprompt | Merged
72 | 2026-07-30 | 2026-07-30 | Colour consistency pass: align calendar + PID-ledger status palettes | color-consistency | Merged
73 | 2026-07-31 | 2026-07-31 | Fix 3 bugs: regularization enum, project/task date pickers, super-admin comp-off visibility | three-bug-fixes | Merged
74 | 2026-07-31 | 2026-07-31 | Capacity single-person allocation + dynamic attendance area + custom-range export | capacity-attendance-features | Merged
75 | 2026-07-31 | 2026-07-31 | Homepage requests hub + Reports project detail + range activity digest | requests-hub-reports | Merged
76 | 2026-08-04 | 2026-08-04 | Bigger Team Calendar cells + real-time/stale-data fixes | calendar-size-realtime | Merged
77 | 2026-08-04 | 2026-08-04 | Team Calendar: start on today + real ‹ › navigation (range model fix) | team-calendar-today-first | Merged
78 | 2026-08-04 |  | Calendar: collapsible Upcoming rail + remove Compact density | calendar-collapsible-rail | Closed
79 | 2026-08-04 | 2026-08-04 | Calendar: collapsible Upcoming rail + remove Compact density | calendar-rail-collapse-v2 | Merged
80 | 2026-08-04 | 2026-08-05 | 14-item feedback batch: attendance truth, calendar foundation, half-day leave & WFH, project/PID UX | feedback-batch-2026-08 | Merged
81 | 2026-08-11 | 2026-08-11 | One status for a task, wherever you look at it | matrix-and-module-fixes-2026-08 | Merged
82 | 2026-08-13 | 2026-08-19 | Phase 2 — clients and patents: identity, tagging, and a client ledger | phase2-clients-patents-ledger | Merged
83 | 2026-08-13 | 2026-08-19 | Squark Dashboard — clients & patents, team spaces, BD pipeline, calendar, appraisals | phase3-team-spaces | Merged
84 | 2026-08-19 | 2026-08-19 | Release 2026 08 19 | release-2026-08-19 | Merged
85 | 2026-08-19 | 2026-08-19 | Business Development is a role, and a manager is not a project manager | fix-bd-role-reporting-lines | Merged
86 | 2026-08-19 | 2026-08-19 | Departments you can actually manage, an org chart that exists, policies with something in them | departments-orgchart-policies | Merged
87 | 2026-08-19 |  | Four races that were one bug, and five smaller findings from testing | fix-races-and-test-findings | Closed
88 | 2026-08-19 | 2026-08-19 | Four races that were one bug, and five smaller findings from testing | fix-races-and-test-findings | Merged
89 | 2026-08-19 | 2026-08-19 | A runbook for deploying #85, #86 and #88 to Contabo | deploy-runbook-0819 | Merged
90 | 2026-08-19 |  | The deploy command was missing -f docker-compose.prod.yml | fix-deploy-runbook | Closed
91 | 2026-08-19 | 2026-08-19 | The deploy command was missing -f docker-compose.prod.yml | fix-deploy-runbook | Merged
92 | 2026-08-19 | 2026-08-19 | The env file is .env.production, and compose only auto-reads .env | fix-runbook-envfile2 | Merged
93 | 2026-08-19 | 2026-08-19 | The pipeline now says something back | bd-pipeline-intelligence | Merged
94 | 2026-08-19 | 2026-08-19 | Performance was measuring the wrong things, and one metric was always zero | performance-metric-fixes | Merged
95 | 2026-08-19 | 2026-08-19 | Parameters you can edit, policies that know what people agreed to, reports with a period | module-improvements | Merged
96 | 2026-08-19 | 2026-08-19 | The four ledgers were islands: connect them, and say where the chain breaks | connect-the-ledgers | Merged
97 | 2026-08-19 |  | One runbook covering everything on main, not just the first three PRs | runbook-complete | Closed
98 | 2026-08-19 | 2026-08-19 | One runbook covering everything on main, not just the first three PRs | runbook-complete-v2 | Merged
99 | 2026-08-19 | 2026-08-19 | The deploy that took the site down cannot happen again, and two other loose ends | close-open-issues | Merged
100 | 2026-08-23 | 2026-08-24 | The analyst could see the handle and never the patent it stood for | self-pm-feedback-ledger-patent-mapping | Merged
101 | 2026-08-24 | 2026-08-24 | Anyone can manage their own project, and anyone can resolve a patent ID | patent-directory-and-self-pm | Merged
102 | 2026-08-24 | 2026-08-24 | Fix the container build: the re-code script could not compile | fix-container-build-seed | Merged

## Commits
Date | SHA | Author | Subject
2026-06-24 | 5fb2e03 | Anant Gupta | Initial commit — SquarkIP pdash project management system
2026-06-25 | bb01082 | Anant Gupta | Build out SquarkIP dashboard: live API integration, real seed data, collapsible sidebar, interactive Kanban/Gantt/Calendar, progress color scale
2026-06-28 | 4f9a5b0 | Anant Gupta | Add auth, RBAC, attendance, and performance modules; live API + real Postgres
2026-07-06 | 3401e42 | Anant Gupta | Production deploy: Docker stack, security hardening, RBAC guards, health checks, migrations
2026-07-06 | c79e5dc | Anant Gupta | Add one-command Contabo deploy script + docs; harden web port to localhost bind
2026-07-06 | 7f9609a | Anant Gupta | contabo-deploy: keep current SSH port open in ufw (SSH is on 2222, not 22); make Caddy start non-fatal
2026-07-06 | 08f2db5 | Anant Gupta | fix(web): bake API_ORIGIN at build time so Next standalone proxies /api to the api service
2026-07-06 | cf36e52 | Anant Gupta | fix(seed): run ts-node with --skip-project so the DB seed works in the api container
2026-07-06 | c0b93e0 | Anant Gupta | fix(seed): pass ALLOW_PROD_SEED=true so the first-run seed clears the prod guard
2026-07-06 | 18a1396 | Anant Gupta | refactor(seed): compile the seed to JS at build time; run with plain node (no ts-node)
2026-07-07 | dd32cc8 | Anant Gupta | fix(ui): portal notifications + user menu; task assignee avatars + overflow; shared primitives
2026-07-08 | 975401b | Anant Gupta | fix(tasks): assignees tab + inline status/progress everywhere + real activity + a11y
2026-07-08 | 3b17d0a | Anant Gupta | fix(ui): use DateField for all date/time inputs (click anywhere opens picker)
2026-07-08 | 74d2c7b | AnantSQIP | Merge pull request #2 from AnantSQIP/squarkip-dashboard-snapshot
2026-07-08 | 748af24 | Anant Gupta | feat(auth): self-service change-password + org password-reset script
2026-07-08 | 5a36632 | AnantSQIP | Merge pull request #3 from AnantSQIP/squarkip-dashboard-snapshot
2026-07-09 | d4e3d50 | Anant Gupta | fix(audit): remediate deep-audit findings (~87/88)
2026-07-10 | 53f623d | Anant Gupta | feat: file attachments/media + organization step-up passcode
2026-07-11 | e0978ef | AnantSQIP | Merge pull request #4 from AnantSQIP/fix/deep-audit-2026-07
2026-07-13 | d66c041 | Anant Gupta | fix(ops): supervisor could never restart the app after a reboot
2026-07-13 | 4fe96a3 | Anant Gupta | feat: team capacity, dual deadlines, overdue alerts, project requests
2026-07-13 | 92c08e7 | Anant Gupta | fix(deadlines): a date could never be removed once set
2026-07-13 | 89b1637 | Anant Gupta | fix(deploy): make permission re-grants runnable in prod, and stop pinning the stale branch
2026-07-13 | 119d4f5 | Anant Gupta | fix(rbac): regrant-roles could deny every live user mid-run
2026-07-13 | c32d40a | Anant Gupta | fix(security): the step-up passcode shipped as a known default in a public repo
2026-07-13 | b1582f5 | AnantSQIP | Merge pull request #5 from AnantSQIP/fix/deep-audit-2026-07
2026-07-13 | 3e02da1 | Anant Gupta | fix(auth): a password reset did not actually let anyone back in
2026-07-13 | 9c14592 | Anant Gupta | fix(planning): a task's and a project's plan were frozen at creation
2026-07-13 | 00b1b5b | AnantSQIP | Merge pull request #6 from AnantSQIP/fix/planning-and-password-recovery
2026-07-13 | 2411969 | Anant Gupta | fix(capacity): production hardening — close a cross-tenant leak, plus edges; open it from projects
2026-07-14 | a0cbc7e | AnantSQIP | Merge pull request #7 from AnantSQIP/fix/capacity-hardening
2026-07-14 | 2a59792 | Anant Gupta | chore(roster): offboard Riya Bhola; intern cohort designations; add Geetesh Rathore
2026-07-14 | 6cd7ab8 | AnantSQIP | Merge pull request #8 from AnantSQIP/chore/roster-2026-07
2026-07-14 | 03ac5d4 | Anant Gupta | feat(profile): collect joining details on first sign-in, with a hard PII boundary
2026-07-14 | d7b0d3e | AnantSQIP | Merge pull request #9 from AnantSQIP/feat/user-profile
2026-07-14 | f35e108 | Anant Gupta | docs: knowledge-transfer guide for the whole system
2026-07-14 | eb416ab | AnantSQIP | Merge pull request #10 from AnantSQIP/docs/kt
2026-07-14 | ec49016 | Anant Gupta | chore: never let dashboard screenshots reach the public repo
2026-07-14 | c0c3ddf | AnantSQIP | Merge pull request #11 from AnantSQIP/chore/ignore-kt-shots
2026-07-14 | 26a83d2 | Anant Gupta | fix(ui): modal action buttons could scroll off-screen — bound every dialog
2026-07-14 | 201719a | AnantSQIP | Merge pull request #12 from AnantSQIP/fix/modal-overflow
2026-07-14 | 84fea12 | Anant Gupta | fix(mobile): make the data tables usable on a phone
2026-07-14 | 9f2c7ec | AnantSQIP | Merge pull request #13 from AnantSQIP/fix/mobile-tables
2026-07-15 | 579aad6 | AnantSQIP | feat(attendance): regularization requests with HR approval + fixes (#14)
2026-07-15 | 09e66a2 | AnantSQIP | feat(projects,capacity): completion lifecycle, deadline extend, emergency-leave coverage (#15)
2026-07-16 | 5cee74a | AnantSQIP | feat(capacity,attendance): retrospective view, comp-off, drop Overloaded (#16)
2026-07-16 | 55e2184 | AnantSQIP | feat(capacity,tasks,auth): sticky dates, deadline cleanup, drill-down, idle logout, assigned-by (#17)
2026-07-17 | dc64342 | AnantSQIP | feat(ui,projects): rename to Squark Dashboard, meaningful icons, billable review, cleanups (#18)
2026-07-17 | fa8a4b9 | AnantSQIP | feat(performance): clearer layout, interactive donuts, explained metrics (#19)
2026-07-17 | f918c12 | AnantSQIP | fix(tasks,billable,capacity): dropdown overlay, subtask uncheck, plan align, billable inheritance, leave visibility (#20)
2026-07-17 | f43d53c | AnantSQIP | feat(projects,capacity): drop project approval gate, fix designations, detach capacity date bar (#21)
2026-07-17 | 36456b1 | AnantSQIP | feat(auth): recover a forgotten organization passcode via account password (#22)
2026-07-17 | f499e50 | AnantSQIP | chore(db): compile update-designations script into the prod image (#23)
2026-07-17 | 7ea44ae | AnantSQIP | feat(expenses,attendance,discuss): expense module, WFH work mode, punch validation, weekend comp-off, channel rename (#24)
2026-07-19 | 6d860e3 | Anant Gupta | feat(discuss,presence,search,calendar,attendance): Teams-inspired Phase 1 + WFH request flow
2026-07-19 | fffb7b3 | Anant Gupta | feat(discuss,calendar): Phase 2 — polls, saved messages, recurring meetings, meeting notes/chat, ICS export
2026-07-19 | e613478 | Anant Gupta | feat(discuss,settings): Phase 3 — voice clips, @channel/tag mentions, read receipts, governance
2026-07-19 | bcb6410 | Anant Gupta | feat(lifecycle): TeamNest TN Phase 1 — employee onboarding, offboarding & HR letters
2026-07-19 | 88fbfea | Anant Gupta | feat(company): TeamNest TN Phase 2 — announcements, HR policy library & org chart
2026-07-20 | 83dd8da | Anant Gupta | feat(appraisals): TeamNest TN Phase 3 — structured performance appraisal cycles
2026-07-20 | 0dfce04 | Anant Gupta | revert(lifecycle): remove the Employee Lifecycle module; enforce @squarkip.com on add-member
2026-07-20 | 165c747 | Anant Gupta | feat(attendance): avg punch in/out, regularisation routes to HR+Yash only, show punch times
2026-07-20 | e72e782 | Anant Gupta | feat(leaves,compoff): rename leave heading, one-leave-per-day guard, comp-off PID + HR/Manager/Yash routing
2026-07-20 | b79a4ec | Anant Gupta | feat(billable): projects billable by default; each person sets billability on their own time
2026-07-20 | b75e23a | Anant Gupta | feat(projects): remove milestones entirely (model + logic)
2026-07-20 | 1334228 | Anant Gupta | feat(issues): repurpose Issues as technical issues → non-billable time entries
2026-07-20 | 66aa6a6 | Anant Gupta | feat(ui): alphabetical people lists everywhere + bottom-left notification pop-ups
2026-07-20 | 83cb84f | Anant Gupta | feat(company): replace Org chart with a Company Directory (name, designation, email, contact)
2026-07-20 | cc40a91 | Anant Gupta | feat(discuss): remove lock icons, discoverable rename, paste screenshots (SNIPPET)
2026-07-20 | 4128bb3 | Anant Gupta | feat(company): Recognition / Rewards tab (per financial year, visible to all)
2026-07-20 | 1935e34 | Anant Gupta | fix(search): guardrail global search — never surface results a user can't access
2026-07-22 | ed4ede7 | AnantSQIP | fix: QA findings remediation — object-level authz, validation, cross-tenant scoping (P1-P8) (#25)
2026-07-22 | d4b8de9 | AnantSQIP | feat(rbac): add Senior Research Associate role + align roster to designations (#26)
2026-07-22 | 0569ced | AnantSQIP | chore(db): clear the 9 members' personal activity for a clean test slate (#27)
2026-07-22 | e507cf0 | AnantSQIP | feat(home,timesheets): punch from Home + Timesheets sidebar module (#28)
2026-07-22 | 524728b | Anant Gupta | docs(research): patent HML ranking + claim-chart system research brief
2026-07-22 | f5ed3ec | AnantSQIP | Merge pull request #29 from AnantSQIP/docs-patent-hml-research
2026-07-22 | 85d315c | AnantSQIP | feat(projects): project type on creation + auto-generated task workflow (#30)
2026-07-22 | 771c90a | AnantSQIP | fix(home): move the Punch In card to the top of the dashboard (#31)
2026-07-23 | feb9271 | AnantSQIP | feat(patents,projects): PID + confidential Patent portal + project-module fixes (#32)
2026-07-23 | 9955034 | AnantSQIP | feat(patents): patent documents + passcode/home tweaks (#33)
2026-07-23 | 9f69ec5 | AnantSQIP | fix(patents,documents): robustness — disk storage, dedup, re-creatable codes, doc passcode (#34)
2026-07-23 | 955eeb8 | AnantSQIP | fix(patents): filename-gated uploads + editable client codes + non-stale project client (#35)
2026-07-24 | 78bbd9c | AnantSQIP | feat: workspace rebuild — PID flow, offices, profile gate, capacity, timesheets (#36)
2026-07-24 | 5aea39f | Anant Gupta | chore(hours): set the working day to 9am–6pm IST (8 working hrs) for capacity + performance
2026-07-24 | 19ff0de | Anant Gupta | docs(qa): deep-test plan + Squark IP domain brief
2026-07-24 | aec8caf | Anant Gupta | docs(qa): Batch 1 (Projects) findings — 4 HIGH, 6 MED + verified-good
2026-07-24 | 39afc2f | Anant Gupta | docs(qa): Batches 2-5 findings (Patents CRIT x2, Timesheets/Attendance HIGH, HR)
2026-07-24 | a5c54e4 | Anant Gupta | docs(qa): complete 8-agent deep-test sweep — synthesis + fix plan
2026-07-24 | 1492cbc | Anant Gupta | docs(qa): launch second agent wave (6 agents: 4 gap-closing + 2 dedicated capacity)
2026-07-24 | 4b95f1b | Anant Gupta | docs(qa): complete second wave (6 agents) — full 14-agent sweep synthesis
2026-07-24 | 41037be | Anant Gupta | fix(security): P0 batch — close the 4 CRIT confidentiality holes + 2 integrity bypasses
2026-07-24 | 6254bdc | Anant Gupta | docs(qa): mark P0 fix batch done (commit 41037be)
2026-07-24 | 0991785 | Anant Gupta | fix(security): Batch B (1/2) — search scoping, departments authz, admin-reset rank, calendar
2026-07-24 | dc34ab6 | Anant Gupta | fix(capacity,tasks,rewards): Batch B (2/2) — capacity load-math, retrospective, workflow, rewards
2026-07-24 | e5c1ac4 | Anant Gupta | feat(aws): Batch C1 — health 503, background-job runner gate, boot-migrate gate (config-gated)
2026-07-24 | 6776f94 | Anant Gupta | feat(aws): Batch C2 — pluggable document storage with an S3 driver (config-gated)
2026-07-24 | b4c935c | Anant Gupta | docs(qa): mark Batch B + C done; document AWS-readiness env switches
2026-07-25 | 34c10f3 | Anant Gupta | fix(home): root-cause Home-module QA remediation (28-tester sweep)
2026-07-25 | 27abd6c | AnantSQIP | QA remediation: deep-test (P0/B/C) + Home module + 9-6 IST (#37)
2026-07-27 | 5e50029 | Anant Gupta | feat(timesheets)+fix(qa): "Other" non-project time + Rounds 2-3 QA remediation
2026-07-27 | e501d85 | AnantSQIP | Timesheets "Other" category + QA Rounds 2-3 remediation (#38)
2026-07-27 | 4a01184 | Anant Gupta | feat(timesheets): 2-option Log Time — Project task (w/ Assign-PID-later toggle) + Other (titled)
2026-07-27 | 0768067 | AnantSQIP | Log Time: 2 options — Project task (Assign-PID-later toggle) + Other with Title (#39)
2026-07-27 | 74dc6bd | Anant Gupta | fix(timesheets): Project-task layout — Project title + auto-filled mandatory PID
2026-07-27 | 26f150f | AnantSQIP | Merge pull request #40 from AnantSQIP/qa-deeptest-workhours
2026-07-27 | 2646372 | Anant Gupta | fix(timesheets): keep Project + Task when "Assign PID later" is on — hide only the PID
2026-07-27 | 74aeb95 | AnantSQIP | Merge pull request #41 from AnantSQIP/qa-deeptest-workhours
2026-07-27 | ab1a20e | Anant Gupta | feat(projects,tasks): PID lifecycle + PM picker + review-before-attach + role-based task staffing
2026-07-27 | d0340d0 | AnantSQIP | Merge pull request #42 from AnantSQIP/qa-deeptest-workhours
2026-07-27 | 01e9c3b | Anant Gupta | feat(pid): continuing-series allocator (destroy-on-expiry, tail-reclaim); drop give-back; hide type+PM from reviewer
2026-07-27 | 6bdf598 | AnantSQIP | Merge pull request #43 from AnantSQIP/qa-deeptest-workhours
2026-07-27 | 7180a4d | Anant Gupta | fix(pid): reviewer can set the project type + project manager on the PID attach screen
2026-07-27 | 1d7851d | AnantSQIP | Merge pull request #44 from AnantSQIP/qa-deeptest-workhours
2026-07-27 | ae24f0b | Anant Gupta | fix(pid): PID Ledger no longer crashes on a legacy/unknown reservation status
2026-07-27 | 21a627d | AnantSQIP | Merge pull request #45 from AnantSQIP/qa-deeptest-workhours
2026-07-27 | ec26c3b | Anant Gupta | chore(db): reset-keep-one-project script — delete all projects except one, keep users/RBAC
2026-07-28 | 2e10c09 | AnantSQIP | Merge pull request #46 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | b8bc72e | Anant Gupta | feat(tasks): single-page task screen — dropdown progress, auto-sum est. hours, tidier layout
2026-07-28 | 9f8af12 | AnantSQIP | Merge pull request #47 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | cddb023 | Anant Gupta | feat(tasks): task PM defaults to the project manager; remove the progress dropdown
2026-07-28 | 3c75e79 | AnantSQIP | Merge pull request #48 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | 62ff4f1 | Anant Gupta | fix(timesheets,capacity,performance): enforce task-assignment for time logging + consistency fixes
2026-07-28 | 1a734ad | AnantSQIP | Merge pull request #49 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | 0b15557 | Anant Gupta | feat(batch-a): expense placeholder, capacity per-project filter, remove Discuss
2026-07-28 | 5d2e09d | AnantSQIP | Merge pull request #50 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | fbe891a | Anant Gupta | feat(batch-b): PID export CSV + Super-Admin PID detail + re-initialize completed project
2026-07-29 | aeb1d46 | AnantSQIP | Merge pull request #51 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | bf97f67 | Anant Gupta | feat(batch-c): mandatory location capture on attendance punch in/out
2026-07-29 | ed74ad6 | AnantSQIP | Merge pull request #52 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | 6b3138f | Anant Gupta | feat(batch-d): new project-type task lists + custom project types (one-off or saved org-wide)
2026-07-29 | 5aebe2e | AnantSQIP | Merge pull request #53 from AnantSQIP/qa-deeptest-workhours
2026-07-28 | e0cf6ce | Anant Gupta | feat(rbac): apply additive permission-matrix grants (calendar/issue/tasklist/timesheet)
2026-07-29 | ffc399e | AnantSQIP | Merge pull request #54 from AnantSQIP/qa-deeptest-workhours
2026-07-29 | 3d3e149 | AnantSQIP | Second feedback round: PID reopen/detail, timesheet calendar, expense currency, punch locations, daily digest (#55)
2026-07-29 | 9ffde6c | AnantSQIP | Timesheet backfill windows + Super-Admin approval flow (#57)
2026-07-29 | 13d1f1c | AnantSQIP | Third feedback round: hours/calendars/expenses/subtasks/PM-delegation/PID-ledger (#58)
2026-07-29 | 23d48d3 | AnantSQIP | Team Calendar tab + redesigned timesheet/attendance calendars (#59)
2026-07-29 | 439f4f8 | AnantSQIP | Team Calendar: multi-month scrollable timeline (#60)
2026-07-29 | d2ad351 | AnantSQIP | Subtasks: add / rename / delete from the task page (#61)
2026-07-29 | 70d972c | AnantSQIP | Project chat: @mention project members (#62)
2026-07-29 | 9adcaef | AnantSQIP | Permission Matrix (New): apply role permission removals (#63)
2026-07-30 | 4495206 | AnantSQIP | PID Ledger: lifecycle states + search (#64)
2026-07-30 | bec21cd | AnantSQIP | Timesheets rewrite + attendance 24h fix + project fixes (#65)
2026-07-30 | f665401 | AnantSQIP | Attendance team-location: area, full labels, 1-year view + CSV (#66)
2026-07-30 | 936f0a7 | AnantSQIP | Team Calendar: frozen date bar rewrite + upcoming scope (#67)
2026-07-30 | 2bafbaa | AnantSQIP | Profile wedding anniversary + calendar celebrations + Jaipur area (#68)
2026-07-30 | 5c7db42 | AnantSQIP | Role-first task staffing + capacity assign + assign-error fix (#69)
2026-07-30 | 8ffcb2e | AnantSQIP | Comp-off: half/full day + timesheet & attendance integration (#70)
2026-07-30 | 946f42f | AnantSQIP | Daily digest detail screen + editable time + login punch prompt (#71)
2026-07-30 | c37c846 | AnantSQIP | Colour consistency pass: calendars + PID ledger (#72)
2026-07-31 | 98ec416 | AnantSQIP | Fix 3 bugs: regularization enum, date pickers, super-admin comp-off visibility (#73)
2026-07-31 | 9777b11 | AnantSQIP | Capacity single-person allocation + dynamic attendance area + custom-range export (#74)
2026-07-31 | 8b6027f | AnantSQIP | Homepage requests hub + Reports project detail + range digest (#75)
2026-08-04 | 3a0137d | AnantSQIP | Bigger Team Calendar cells + real-time/stale-data fixes (#76)
2026-08-04 | ac4a12a | AnantSQIP | Team Calendar: start on today + real navigation (#77)
2026-08-04 | fbcdbe6 | AnantSQIP | Calendar: collapsible Upcoming rail + remove Compact density (#79)
2026-08-05 | e718252 | AnantSQIP | Attendance truth, calendars, leave, projects, Daily Digest module, multi-round PIDs (#80)
2026-08-05 | db3b9df | Anant Gupta | Project type never reached the cards; task groups could not be renamed
2026-08-05 | 669cd89 | Anant Gupta | Multi-round consistency: capacity, timesheet↔ledger reconciliation, performance attribution
2026-08-05 | a9da94c | Anant Gupta | One bar per task group, and the new-project form captures the full detail
2026-08-05 | 5946250 | Anant Gupta | A PID with live work no longer reads as closed or retired
2026-08-05 | 0eea5f1 | Anant Gupta | Remove the empty "General" group that sat above every typed project's real work
2026-08-05 | b5327e9 | Anant Gupta | Delivery clients: one client, many PIDs, code shareable and identity restricted (backend)
2026-08-05 | 34b353d | Anant Gupta | Client ledger UI: codes across the dashboard, identity behind a lock
2026-08-05 | db7cb90 | Anant Gupta | A project's client can be changed after creation
2026-08-05 | bf0c9cc | Anant Gupta | Take the Gurgaon client system off main — it is a local demo, not a Contabo deploy
2026-08-07 | 4cac73a | Anant Gupta | Multi-project PIDs for everyone, one end state instead of two, and one colour for WFH
2026-08-07 | 54a8a63 | Anant Gupta | Leaves, Attendance and Expenses in the shape the team already reads
2026-08-07 | 5a17850 | Anant Gupta | Link a person's page across to their roles and permissions
2026-08-07 | c5edac4 | Anant Gupta | Comp-off moves in Credit and Debit, and the balance card says what it means
2026-08-07 | 682f890 | Anant Gupta | Leave is whole days and half days, and nothing in between
2026-08-07 | 7e267a9 | Anant Gupta | Technology domains, an order for the project list, client-call time, and no more encashment
2026-08-11 | d642707 | Anant Gupta | One status for a task, wherever you look at it
2026-08-11 | 73ddb4a | Anant Gupta | Leave you no longer need can be called off, by you or by HR
2026-08-12 | e5ff124 | Anant Gupta | Saying where your work has got to is not editing the task
2026-08-12 | dc8dfbf | Anant Gupta | The PID ledger asks two questions about hours, not three
2026-08-12 | fa0b0f4 | Anant Gupta | Who issues a PID, who can be a Project Manager, and who sees the capacity board
2026-08-12 | 29dc114 | Anant Gupta | "Send now" sends now
2026-08-12 | 44e1e0b | Anant Gupta | Working from home is a button again, not a form
2026-08-12 | 8e220e8 | Anant Gupta | Work from home is asked once, when the day starts
2026-08-12 | 830c618 | Anant Gupta | The roster decides the roles, not the seed
2026-08-12 | bcfdd69 | Anant Gupta | A job title is not a permission
2026-08-12 | d272ad1 | Anant Gupta | Three things found by actually using the thing
2026-08-12 | 4af65c0 | Anant Gupta | Phase 1 is closed; write down where the line falls
2026-08-12 | 79c4a9b | Anant Gupta | Put the Phase 1 paperwork under version control
2026-08-13 | fb42c2d | Anant Gupta | A client is more than a code on a patent
2026-08-13 | bc554bd | Anant Gupta | Somewhere for work that is not a client project
2026-08-13 | 30cb3a0 | Anant Gupta | Three bugs the review found, one of them mine from an hour ago
2026-08-13 | 2cbb7f3 | Anant Gupta | Team spaces: the module, not just the tables
2026-08-13 | b397828 | Anant Gupta | A pipeline is a forecast, not a promise
2026-08-13 | 2f5d56b | Anant Gupta | Write down what Phase 3 turned into
2026-08-13 | 74db31e | Anant Gupta | Withdraw the "Phase 3" label — this is Phase 2, part two
2026-08-16 | 7bc41bc | Anant Gupta | Internal work counts, without pretending to be client work
2026-08-16 | 6d13a46 | Anant Gupta | Everything agreed for Phase 2 is now built
2026-08-16 | 35db28e | Anant Gupta | No, it was not complete: team tasks could never be closed
2026-08-16 | 14ed82f | Anant Gupta | A plan for appraisals, and the reason it cannot start yet
2026-08-17 | 60b8efd | Anant Gupta | The real 2026 calendar, and optional holidays that are actually optional
2026-08-17 | a96c6b0 | Anant Gupta | Reporting lines, and the appraisal module works for the first time
2026-08-17 | 74d3d82 | Anant Gupta | Appraisals: what people are rated on, not just a number
2026-08-18 | 3d2a958 | Anant Gupta | Keep the source calendar next to the data derived from it
2026-08-18 | 7f99833 | Anant Gupta | The reporting-lines script would not have existed in production
2026-08-18 | 3b7d9fe | Anant Gupta | A runbook for this release, in the order the steps actually depend on
2026-08-19 | c006c3d | Anant Gupta | The appraisal screen — the part that made the rest usable
2026-08-19 | 40c4bb7 | AnantSQIP | Clients & patents, team spaces, the BD pipeline, the 2026 calendar and appraisals (#83)
2026-08-19 | 73aaffc | AnantSQIP | Business Development is a role, and a manager is not a project manager (#85)
2026-08-19 | e7f4995 | AnantSQIP | Departments you can actually manage, an org chart that exists, policies with something in them (#86)
2026-08-19 | d2fda5f | AnantSQIP | Four races that were one bug, and five smaller findings from testing (#88)
2026-08-19 | 0bcf201 | AnantSQIP | A runbook for deploying #85, #86 and #88 to Contabo (#89)
2026-08-19 | 6d59d0c | AnantSQIP | The deploy command was missing -f docker-compose.prod.yml (#91)
2026-08-19 | b06c76c | AnantSQIP | The env file is .env.production, and compose only auto-reads .env (#92)
2026-08-19 | 6c509d8 | AnantSQIP | The pipeline now says something back (#93)
2026-08-19 | 6644a42 | AnantSQIP | Performance was measuring the wrong things, and one metric was always zero (#94)
2026-08-19 | 7bce2da | AnantSQIP | Parameters you can edit, policies that know what people agreed to, reports with a period (#95)
2026-08-19 | e532adf | AnantSQIP | The four ledgers were islands: connect them, and say where the chain breaks (#96)
2026-08-19 | 5185e92 | AnantSQIP | One runbook covering everything on main, not just the first three PRs (#98)
2026-08-19 | ecd707c | AnantSQIP | The deploy that took the site down cannot happen again, and two other loose ends (#99)
2026-08-24 | e7a9419 | AnantSQIP | Patent ID to number mapping, feedback, client ledger detail, self-as-PM (#100)
2026-08-24 | 7ad581d | AnantSQIP | Anyone can manage their own project, and anyone can resolve a patent ID (#101)
2026-08-24 | 6c47219 | AnantSQIP | Fix the container build: the re-code script could not compile (#102)2026-08-25¦da77a6e¦Anant Gupta¦Two dead buttons in Settings, and an address that needed a release to change
2026-08-25 | 5e7a4cd | Anant Gupta | Cut the status report from five pages to three
2026-08-26 | 482b09a | Anant Gupta | One PID could end up meaning two different clients
2026-08-26 | 788dde5 | Anant Gupta | Between midnight and 05:30 IST the system used yesterday's date
2026-08-26 | a943cd4 | Anant Gupta | In December, nobody could book January's leave

## Daily Activity
Date | Commits | Phase
2026-06-24 | 1 | Phase 1
2026-06-25 | 1 | Phase 1
2026-06-28 | 1 | Phase 1
2026-07-06 | 7 | Phase 1
2026-07-07 | 1 | Phase 1
2026-07-08 | 5 | Phase 1
2026-07-09 | 1 | Phase 1
2026-07-10 | 1 | Phase 1
2026-07-11 | 1 | Phase 1
2026-07-13 | 11 | Phase 1
2026-07-14 | 13 | Phase 1
2026-07-15 | 2 | Phase 1
2026-07-16 | 2 | Phase 1
2026-07-17 | 7 | Phase 1
2026-07-19 | 5 | Phase 1
2026-07-20 | 12 | Phase 1
2026-07-22 | 8 | Phase 1
2026-07-23 | 4 | Phase 1
2026-07-24 | 15 | Phase 1
2026-07-25 | 2 | Phase 1
2026-07-27 | 17 | Phase 1
2026-07-28 | 13 | Phase 1
2026-07-29 | 12 | Phase 1
2026-07-30 | 9 | Phase 1
2026-07-31 | 3 | Phase 1
2026-08-04 | 3 | Phase 1
2026-08-05 | 10 | Phase 1
2026-08-07 | 6 | Phase 1
2026-08-11 | 2 | Phase 1
2026-08-12 | 11 | Phase 2
2026-08-13 | 7 | Phase 2
2026-08-16 | 4 | Phase 2
2026-08-17 | 3 | Phase 2
2026-08-18 | 3 | Phase 2
2026-08-19 | 14 | Phase 2
2026-08-24 | 3 | Phase 2
2026-08-25 | 2 | Phase 2
2026-08-26 | 3 | Phase 2

## Branches
Branch | Last commit | Subject
cmp/admin | 2026-06-25 | Build out SquarkIP dashboard: live API integration, real seed data, collapsible sidebar, interactive Kanban/Gantt/Calendar, progress color scale
cmp/main | 2026-06-24 | Initial commit — SquarkIP pdash project management system
origin/Admin---Module | 2026-06-25 | Build out SquarkIP dashboard: live API integration, real seed data, collapsible sidebar, interactive Kanban/Gantt/Calendar, progress color scale
origin/attendance-team-location | 2026-07-30 | feat(attendance): team-location area + full Punch In/Out labels + 1-year view + CSV export
origin/calendar-collapsible-rail | 2026-08-04 | feat(calendar): collapsible Upcoming rail + drop the Compact density
origin/calendar-rail-collapse-v2 | 2026-08-04 | feat(calendar): collapsible Upcoming rail + drop the Compact density
origin/calendar-size-realtime | 2026-08-04 | fix(calendar,realtime): bigger readable Team Calendar cells + close the stale-data gaps
origin/calendar-team-tab-ui-redesign | 2026-07-29 | feat(calendar,timesheets,attendance): Team Calendar tab + redesigned calendar layouts
origin/capacity-attendance-features | 2026-07-31 | feat(attendance): dynamic area from punch coords (reverse-geocode) + custom-range CSV export
origin/chore/compile-designation-script | 2026-07-17 | chore(db): compile update-designations script into the prod image
origin/chore/ignore-kt-shots | 2026-07-14 | chore: never let dashboard screenshots reach the public repo
origin/chore/roster-2026-07 | 2026-07-14 | chore(roster): offboard Riya Bhola; intern cohort designations; add Geetesh Rathore
origin/clear-seed-activity | 2026-07-22 | chore(db): also clear the 9 members' personal activity/content for a clean test slate
origin/client-system-demo | 2026-08-05 | A project's client can be changed after creation
origin/color-consistency | 2026-07-30 | style(colors): align status palettes so the same meaning is the same colour
origin/compoff-halfday-integration | 2026-07-30 | feat(compoff): half/full day + timesheet & attendance integration + pending asterisk
origin/digest-punchprompt | 2026-07-30 | feat(attendance): first-login-of-the-day punch-in prompt (with "punch in later")
origin/docs-patent-hml-research | 2026-07-22 | docs(research): Squark IP full service-domain brief (FTO, invalidity/novelty, RE, risk & strategy)
origin/docs/kt | 2026-07-14 | docs: knowledge-transfer guide for the whole system
origin/feat-patent-documents | 2026-07-23 | feat(patents): patent documents (upload-to-create + attach) + friendlier passcode & home tweaks

## Architecture — PID & Patents
Concept | Format / rule | Explanation
Client | Code of 2–5 characters | The grouping a patent belongs to. New codes are OPAQUE so they say nothing about the client
Client identity | Super Admin only | Which company a code stands for is the confidential fact this system protects
Patent handle | Pat_<clientCode>_<serial> | The shareable identifier. Appears in task titles, pickers and project pages
Patent number | e.g. US 10,123,456 | NOT confidential in itself — patents are published documents. The client ASSOCIATION is what is secret
formerHandles | Array of retired handles | A client-code rename re-mints every handle; the old ones stay resolvable so documents already sent still work
PID | SQ_<FY>_<serial> | The Project ID quoted on reports and invoices. Never auto-assigned — someone generates it deliberately
PID rounds | Same code, roundSeq 1..N | A returning client's next job is a new project under the SAME PID. Every round is one client's work
RULE | One PID, one client | Enforced on both write paths. Previously a round could be re-tagged to another client, splitting the PID
RULE | One project, one client | All patents tagged to a project must belong to the same client
RULE | Tagged patents decide the client | With patents, the client is derived and locked. With none, it is named directly
Visibility tier 1 | patent.view — every role but HR | Handle only, plus resolve one patent either direction. Never the client
Visibility tier 2 | Members of the project | The full list of that project's patents with numbers. Never the client
Visibility tier 3 | patent.manage + passcode | Browse the portfolio, see the client, export. Super Admin only
Anti-harvest | 120 lookups per person per hour | Counted from the audit log, so it survives restarts and cannot be reset by logging out
Audit | Count and project, never numbers | A log that quotes the secret has copied the leak somewhere longer-lived
NOTE | Actual number-to-handle pairs are deliberately NOT reproduced in this workbook | Putting the mapping in a shared spreadsheet would defeat the confidentiality design it documents. It is available in the system to those entitled to it