## Read me
Squark Dashboard — review actions
Feedback from the dashboard review. Every item checked against the code on 08 September 2026.
What is in here
Action list — all 34 items, each with the feedback exactly as it was raised, what it was taken to mean, and a status that was checked against the running system rather than assumed. The "Checked" column says what was looked at, so a verdict can be argued with.
Decisions needed — the items that cannot move until somebody decides something.
By module — the same list counted up, so you can see where the work sits.
Where it stands
10 of 34 are already done. 9 are partly there. 9 have not been started. 6 are waiting on a decision.
Done means done
An item is marked Done only where the behaviour exists in the code today and the "Checked" column names where. Several were built in the last few days: the clock filling the timesheet, the resumed clock reading on from where it stopped, the timesheet gate before punching out, the circle on a task row becoming a mark rather than a button, and the per-project capacity view.
Partly done means the honest half
Where something exists but not as asked, the row says what is there and what is missing, rather than claiming either extreme. Two items turned out to rest on something that does not exist at all — read PPL-01 and TSK-03 before planning them.
One contradiction to settle
PERF-02 says Performance is Super Admin only. PERF-03 says who can see Performance is still open for discussion. Both were raised in the same review. One of them has to win before either can be built.

## Action list
ID | Module | Area / screen | Feedback as raised | What it means | Type | Priority | Status | Checked — what the system does today | What remains
CAP-01 | Team Capacity | Capacity board | Team capacity issue | A problem was reported on the capacity board but not written down. The exact screen, role and behaviour need capturing before anything can be fixed. | Question | High | Decision needed | Nothing to check — the complaint itself was never recorded. | Say what went wrong, on which screen and as which role. Everything else in this module is guesswork until then.
CAP-02 | Team Capacity | Capacity board | Capacity - should be date wise as per project | The board should read date by date within a project, so a project manager sees the load their own project puts on each person on each day. | Change | High | Done | A project’s Capacity tab (components/projects/ProjectCapacityTab.tsx, added in PR #120) is the same board scoped to that project’s members, one column per day. This project’s work is pinned so its segments stay at full strength and everything else fades, each row ends with "Nh on this project", and a summary line answers the deadline question: hours left, working days remaining, hours a day needed, and hours the team can give it before the deadline. A Days/Weeks control switches the columns at the 30-day range. | —
CAP-03 | Team Capacity | Access | Team capacity - only to SRA above | Restrict the capacity board to Senior Research Associate and above. | Change | High | Not started | The board is open to everyone. capacity.view sits inside VIEW_BASICS (permissions-catalog.ts:126), which every role inherits, and the comment above it records why: "Matrix 2026-08-12: the capacity board is open to the whole organisation — knowing who is free this week is not privileged." Worth knowing: the Senior Research Associate block still carries a stale comment saying "no capacity board" (:204), which the inheritance three lines later contradicts — so the intent has already drifted once. | Restricting it reverses a decision the permission matrix took deliberately in August, so it needs saying out loud rather than quietly changing. Take capacity.view out of VIEW_BASICS and grant it from Senior Research Associate upwards, fix the stale comment, and regrant on Contabo. It also removes the project Capacity tab from everyone below that line.
CAP-04 | Team Capacity | Assignment | Task - wise how to check who is free when | Starting from a task, show who has room and on which days, so the task can be staffed from the task itself. | New | High | Partly done | One narrow case already works. The coverage-at-risk panel starts from a task and offers a "Reassign to…" list of free teammates with their free hours beside them (app/capacity/page.tsx:433-462, fed by capacity.module.ts:744-753), and BD deal staffing exposes the same free-hours figure. Everywhere else is person-first: the board is rows of people, and neither the task detail panel nor the add-task flow consults availability at all. | Generalise what the coverage panel already does to any task, not only a task caught behind someone’s leave. On the assignee picker, show each candidate’s free hours over the task’s own date range, most free first — the capacity API already returns exactly that per person per day.
CAP-05 | Team Capacity | Person view | Multi task into single person | See every task stacked on one person, and give one person several tasks without leaving the board. | Change | Medium | Done | One segment per task per person per day, widths in proportion to the hours, so several tasks on one person read as a stack inside that day’s box (components/capacity/grid.tsx). Hovering lists every task on the day; clicking the person opens a panel with all their tasks grouped by project, a per-task timeline, and the days they are over capacity. Assigning is on the board: the + on a row and "Assign a task to …" in the panel. | —
CAP-06 | Team Capacity | Capacity board | Remove unnecessary legends | The board carries more legend than it needs. Cut it back to what a reader actually uses. | Change | Medium | Not started | The legend currently carries: a chip per project, a four-step priority ramp, two deadline rails, five day states (free, leave, leave pending, holiday, weekend), an over-8h mark and a caption sentence (components/capacity/BoardLegend.tsx). That is seven groups. | Decide which of the seven a reader actually uses. The project chips earn their place — they are also the filter — and the deadline rails cannot be read without a key. The day states are largely self-evident from the icons, and the caption repeats what the marks already say.
CAP-07 | Team Capacity | Capacity board | Keep task and project info only | Each block on the board should carry the task and its project, and nothing else. | Change | Medium | Partly done | Each block already carries its task and project: the segment prints the PID’s serial when wide enough, and the hover card names the project, the PID and the task title. But it also carries the priority word, the due date, the hours left, and the hours logged against the estimate. | Decide whether the extra lines go. They were added deliberately so a manager does not have to open the task, so cutting to "task and project only" is a real trade rather than a tidy-up.
PPL-01 | People & HR | Client-facing views | client based - Details sharing limitation (Employee details) | When a view is client-facing, employee details must be withheld. Only what the client is entitled to sees the wire. | Change | High | Not started | There is no client-facing surface in the application at all: no client portal, no share link, no external view. The routes under apps/web/app are all staff-authenticated. | This cannot be built as stated until something client-facing exists. Decide whether that is a client portal, an exported report, or a shared project view — the answer changes what has to be withheld.
PPL-02 | People & HR | Profiles | User details at HR end | The full personal record lives with HR, and is read there rather than on an ordinary profile. | Change | Medium | Done | apps/api/src/modules/profile/profile.module.ts:20-27,56,92 — the PERSONAL tier (personal email, alternate phone, address, date of birth, next of kin) is present in a response ONLY for holders of profile.view.personal, and is removed server-side by key deletion for everybody else. Held by HR, Admin and Super Admin. | —
PPL-03 | People & HR | People directory | Person tag with domain | Tag each person with the technology domain they work in, so staffing can be filtered by expertise. | New | High | Not started | A person carries no domain, expertise or skill of any kind — the User model has no such field. Technology domain exists, but only on a project (Project.technologyDomain, added in the August batch), so the system knows a matter is about batteries and nothing about who knows batteries. | Add the tag to a person and reuse the project’s domain list, so the two vocabularies stay the same word. Then it can filter the directory and, more usefully, the assignee picker in CAP-04.
PPL-04 | People & HR | People directory | Searchable list of person | A people list that can be searched, wherever a person has to be picked. | New | High | Partly done | Two of the four places already search, and neither searches enough. The People directory filters on name and email only (app/users/page.tsx:84-87) — not designation, department, office or status, though it shows all four in the table. The task assignee picker has its own search over name and email (TaskDetailPanel.tsx:139,250-251). The two with no search at all are both on projects: the Project Manager dropdown on the create form and the add-member dropdown on the Overview tab. The capacity board’s own people search is name-only. | Make one searchable person picker, matching name, email, designation and department, and use it in all four places. The patent picker on the project form is already this shape and is the thing to copy.
PERF-01 | Performance | Whole module | performance module can be more enhanced | The module is thin. It needs to say more than it currently does before it can be relied on. | Change | Medium | Decision needed | The module is not as thin as the note suggests. Per person it already computes tasks assigned, completed, open and overdue, on-time completion rate, completion rate, hours logged, billable hours, client hours and cycle time (performance.service.ts:141-180). The org view adds breakdowns by department, a leaderboard, an activity heatmap and trend lines. | Blocked by PERF-03 and PERF-04. What is missing cannot be listed until it is agreed who reads this and which aggregates count — otherwise "more" means more of something nobody chose.
PERF-02 | Performance | Access | Performance - Super admin level only | Performance is visible to Super Admin and to nobody else, at least for now. | Change | High | Not started | Not Super Admin only, and there is a dead permission in the way. The org-wide routes are gated on analytics.view.organization (performance.module.ts:49-73), held by Manager (permissions-catalog.ts:154), Admin and Super Admin. Everyone else holds analytics.view.own and sees themselves. Separately, HR is granted performance.view.organization (:287) — a code that is never checked anywhere in the codebase, so it grants nothing; HR sees only its own figures. | If it is to be Super Admin alone, take analytics.view.organization off Manager and off Admin, which the August matrix deliberately gave them, and decide whether people keep analytics.view.own for their own figures. Delete the dead performance.view.organization grant while you are there. Needs a regrant on Contabo.
PERF-03 | Performance | Access | Performance who can see need to discuss | Who is allowed to see performance figures is an open question and was parked for a discussion. | Decision | High | Decision needed | Today the answer is: Manager, Admin and Super Admin see everybody (analytics.view.organization, permissions-catalog.ts:154); everyone else sees only themselves (analytics.view.own). That was set deliberately by the August permission matrix, so the discussion is about changing a decision rather than filling a gap. | Decide. PERF-02 states Super Admin only; this item says it is still open. The two contradict each other and one of them has to win.
PERF-04 | Performance | Metrics | Discussion on Aggregates of performance (Task, hours, overdue) | Agree which aggregates performance is judged on: tasks, hours and overdue work were the three named. | Decision | High | Decision needed | All three named aggregates already exist and are computed per person: task counts (assigned, completed, open, overdue), hours (logged, billable, client) and overdue work (performance.service.ts:141-180). So this is not a build question but a question of which of them the judgement rests on. | Pick the aggregates that count and, more importantly, say how they combine. Hours logged without on-time delivery rewards slowness; tasks completed without hours rewards picking small work.
PERF-05 | Performance | Metrics | Under who task breached count that | A breached deadline is counted against the person the task was sitting with when it breached. | Change | High | Partly done | A per-person overdue count exists — tasksOverdue counts tasks assigned to the person that are past due and not closed (performance.service.ts:145), shown as "Open · Overdue" on the personal panel. But it counts by who holds the task NOW, not who held it when it breached, so reassigning a late task moves the breach onto whoever inherited it, and a task closed late stops being counted the moment it closes. The org leaderboard carries no overdue figure at all (performance.service.ts:438-444), and nothing in the codebase records a breach as an event. | Decide what "under who" means, then record it when it happens rather than recomputing it. The overdue sweep already runs daily and already knows which tasks have just gone past their date — that is the natural place to write down who was holding it.
PERF-06 | Performance | Charts | Trends can be remove | The trend charts are not earning their space and can go. | Change | Low | Not started | Trend charts are there and are a substantial part of the org view: a sparkline on each KPI tile (OrgView.tsx:129,195-196) and a "Team trends" block of line totals plus a stacked area by department (:202). | Straightforward to remove, but confirm it is the org trends you mean and not the per-person ones, and that the sparklines on the tiles go with them.
PRJ-01 | Projects | Project creation | Project creation - share list of person | Creating a project should offer the list of people to staff it, in the creation flow itself. | Change | High | Partly done | NewProjectModal.tsx asks for a Project Manager (one plain dropdown, :470-484) and, when the creator cannot mint a PID, who to request it from (:500-510). CreateProjectDto carries managerId and pidAssigneeId only (projects/dto.ts:111,132) — no member list. Members are added AFTER creation from the Overview tab, through a dropdown of teammates that cannot be searched (views.tsx:170-178). | Add a multi-person picker to the creation form, searchable, writing members in the same call that creates the project. The only searchable picker on that form today is the patent one, which is the pattern to copy.
PRJ-02 | Projects | Lifecycle | Project complete can be done by whom? | Decide who is allowed to mark a project complete. | Decision | High | Decision needed | Today it is anyone with project.update: Super Admin, Admin, Manager and Senior Consultant (permissions-catalog.ts:141,224,334,344). The button is on the project header for ACTIVE and ON_HOLD projects (ProjectDetailClient.tsx:361-370) and the route is POST /projects/:id/complete @RequirePermission("project.update"). There is no check that the person is the project’s own manager. | Decide whether that list is right. The obvious tightening is "the project’s manager, plus Admin and Super Admin" — which would need a per-project check the route does not have today.
PRJ-03 | Projects | Overview | Single screen to ongoing Project | One screen that shows every ongoing project at once, rather than opening them one at a time. | New | High | Partly done | /projects lists every project with a phase filter (ALL / ACTIVE / ON_HOLD / COMPLETED, ProjectsClient.tsx:20-25,143), a domain filter, a search and a sort, plus counts of total/active/completed/on-hold. Active work is one click away but is not what the screen opens on (default ALL, :86). | Decide whether "one screen for ongoing projects" means defaulting this screen to Active, or a different screen that shows each ongoing project’s state side by side. The first is a one-line change; the second is a new view.
GAN-01 | Gantt & planning | Gantt chart | gantt - week wise? | A week scale on the Gantt, not only the current scale. | Change | Medium | Partly done | The Gantt is a fixed day grid — DAY_WIDTH = 24px is a module constant with no setter (GanttView.tsx:11). It already draws month bands (:141-158) and week gridlines anchored to real Mondays (:173-180), so the week is visible, but there is no day/week/month control to switch to. | Make the scale selectable. The week gridlines are already computed, so this is a width-per-unit change and a control, not a rewrite.
GAN-02 | Gantt & planning | Gantt chart | pallel task how to look | Decide how tasks that run at the same time are drawn, so overlap reads clearly instead of as a pile. | Decision | Medium | Decision needed | Tasks that overlap in time are drawn as separate rows, one per task, so they stack vertically rather than colliding. Nothing is hidden today. | Say what "parallel" should look like instead — lanes per person, a merged row per project, or a marker where two bars share days. The current drawing is legible but says nothing about the overlap being deliberate.
GAN-03 | Gantt & planning | Gantt chart | Two color task - Gantt chart | A task bar carries two colours, so two facts show on one bar. | Change | Medium | Done | A Gantt bar already carries two tones: a translucent track in the status colour with a solid progress fill inside it (GanttView.tsx:340-358), the percentage label flipping to white past the halfway mark, and a dashed border when the start date was inferred rather than set. | If "two colour" meant planned versus actual dates rather than progress within the plan, that is a different feature and is not built — there is no baseline stored to compare against.
TSK-01 | Tasks | My Tasks | Prioiry order of task - to infrom person which task is prioirty? | The person doing the work is told which task comes first, rather than reading a list and guessing. | New | High | Partly done | apps/web/lib/tasks.ts nextUpFirst() already orders every list: open before closed, then overdue, then priority (Critical→Low), then due date, then title. Used by My Tasks (app/tasks/page.tsx:144) and the Home card (components/home/sections.tsx:201). The order is right. | Nothing SAYS which one is next — the reader has to infer it from position. A "next up" marker on the top row, or a line naming the task, is what is missing.
TSK-02 | Tasks | Notifications | If two task ask into same prioirrt critical then notify to user | When two tasks are both marked Critical, tell the person, because the ordering no longer decides itself. | New | Medium | Not started | No priority-aware notification exists. The only task notification is task.assigned (tasks.service.ts:318, 597, 654), which carries the title and nothing about priority. | Detect a second open Critical task on the same person and notify. Decide whether it fires on assignment, on a priority change, or both.
TSK-03 | Tasks | Start of day | Start day - window - task summary of prioirity basis | A window at the start of the day summarising the day’s tasks in priority order. | New | High | Not started | No start-of-day summary exists. The catch-up banner added in PR #122 is the nearest thing, but it reports YESTERDAY’s loose ends (a short timesheet, a clock left running), not today’s work. | Build it. Note that the first-login pop-up was deliberately removed in PR #119 — this needs to be a banner or a card, not a modal, unless you decide otherwise.
TSK-04 | Tasks | My Tasks | My Task window - With task list - hours - actual hours | My Tasks shows the task, the hours expected and the hours actually recorded, side by side. | Change | High | Not started | The My Tasks table columns are Task, Project, Priority, Status, Assignees, Due, Progress, Work (app/tasks/page.tsx:464). Neither estimated nor actual hours appears on a row. The day total added in PR #122 is a bar above the list, not a per-task figure. | Add two columns: this person’s estimated hours (TaskAssignee.estimatedHours) and the hours recorded against the task (Task.actualHours, the ledger sum). Both figures already exist server-side.
TSK-05 | Tasks | Timer | Clock to fill | The clock fills the timesheet, rather than the time being typed a second time. | Change | High | Done | PR #122. Finish files the day’s tracked time with nothing typed (task-time.service.ts settleClose → fileDay, a top-up against what is already logged). The day bar on My Tasks files any tracked time not yet filed in one click (components/tasks/TrackedTodayBar.tsx), and the punch-out check offers the same button. | —
TSK-06 | Tasks | Timer | When resuming a task the time starts from 0m instead of continuing from where it stopped | A resumed clock read zero, which looked as though the earlier sitting had been thrown away. The time was always safe in the closed sessions; only the reading was wrong. | Bug | High | Done | PR #124. running() returns priorMinutes beside each clock and the bar counts on from it. The pause toast now names this sitting and the person’s own total separately. | —
TSK-07 | Tasks | My Tasks | I need to refresh every time I log the time in timesheet from my task module to see the updates in real time | Logging time from a task row left the day bar showing the old figures until the page was reloaded. | Bug | High | Done | PR #124. The day bar’s cache key is in TASK_INVALIDATES (lib/task-cache.ts), which TIMESHEET_INVALIDATES spreads, so filing time from anywhere refreshes it at once. | —
TSK-08 | Tasks | My Tasks and project task list | The left-hand radio button that closes and opens the task should not act — only a tick when complete and a dot when open | The circle at the left of a task row was a button that closed or reopened the task in one click. It becomes a mark that only reports the state. | Change | High | Done | PR #124. components/tasks/TaskStateMark.tsx replaced the button on the My Tasks table, the phone card and the project task list. Closing is now the status dropdown, Finish, or Mark Complete. | —
TIM-01 | Timesheets & attendance | Punch out | Notify for task fill before punch out to fill timesheet | Before punching out, the person is reminded to fill the timesheet for the day’s tasks. | Change | High | Done | PR #122. Punching out is refused while the day is short of its target (8h, 4h on an approved half day, 0 on leave or a holiday), enforced on the punch itself and previewed by GET /attendance/me/punch-out-check. The refusal lists the tracked-but-unfiled time per task with one button that files it, and "I have to leave now" always lets the person out with a reason recorded on the day. | —
TIM-02 | Timesheets & attendance | Client calls | Call - Project ID/ Name with Hours fill | A client call is filed against a project ID and name with its hours, like any other entry. | Change | Medium | Done | A CLIENT_CALL timesheet category already exists: timesheets.service.ts:276-305 books the hours against the project (PID) with a title, and components/timesheets/LogTimeStandaloneModal.tsx:125 offers it. A client call cannot be re-assigned to a PID later because it already carries one (timesheets.service.ts:406). | —
UX-01 | Navigation & UX | Whole app | Try 1-2 tab to do things | Ordinary jobs should take one or two moves, not a walk through several screens. | Change | High | Partly done | Several journeys were shortened in PRs #118, #122 and #123: time is logged and tasks finished from the row in My Tasks, punch in/out is on every page from the new top bar, and the capacity board assigns work without leaving it. | No measure of "one or two moves" has been agreed, so there is nothing to test against. Name the three or four journeys that still feel long and they can be counted and cut.

## Decisions needed
ID | Module | What has to be decided | Why it is open | Who decides
CAP-01 | Team Capacity | A problem was reported on the capacity board but not written down. The exact screen, role and behaviour need capturing before anything can be fixed. | Say what went wrong, on which screen and as which role. Everything else in this module is guesswork until then. | Review group
PERF-01 | Performance | The module is thin. It needs to say more than it currently does before it can be relied on. | Blocked by PERF-03 and PERF-04. What is missing cannot be listed until it is agreed who reads this and which aggregates count — otherwise "more" means more of something nobody chose. | Review group
PERF-03 | Performance | Who is allowed to see performance figures is an open question and was parked for a discussion. | Decide. PERF-02 states Super Admin only; this item says it is still open. The two contradict each other and one of them has to win. | Review group
PERF-04 | Performance | Agree which aggregates performance is judged on: tasks, hours and overdue work were the three named. | Pick the aggregates that count and, more importantly, say how they combine. Hours logged without on-time delivery rewards slowness; tasks completed without hours rewards picking small work. | Review group
PRJ-02 | Projects | Decide who is allowed to mark a project complete. | Decide whether that list is right. The obvious tightening is "the project’s manager, plus Admin and Super Admin" — which would need a per-project check the route does not have today. | Review group
GAN-02 | Gantt & planning | Decide how tasks that run at the same time are drawn, so overlap reads clearly instead of as a pile. | Say what "parallel" should look like instead — lanes per person, a merged row per project, or a marker where two bars share days. The current drawing is legible but says nothing about the overlap being deliberate. | Review group

## By module
Module | Items | Done | Partly done | Not started | Decision needed | High priority
Team Capacity | 7 | 2 | 2 | 2 | 1 | 4
People & HR | 4 | 1 | 1 | 2 | 0 | 3
Performance | 6 | 0 | 1 | 2 | 3 | 4
Projects | 3 | 0 | 2 | 0 | 1 | 3
Gantt & planning | 3 | 1 | 1 | 0 | 1 | 0
Tasks | 8 | 4 | 1 | 3 | 0 | 7
Timesheets & attendance | 2 | 2 | 0 | 0 | 0 | 1
Navigation & UX | 1 | 0 | 1 | 0 | 0 | 1
All modules | 34 | 10 | 9 | 9 | 6 | 23